## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
Adhoc Testing | 10 | Johnson Benjamin | 32 | Regression Testing | In Progress | 2023-04-21 |  | Test case update (Select Approved Payment Instruction Template to Create New Payment Request section) | In Progress | 2023-04-21 |  | Hom page Keeps loading | Low | Open | Garg Nikhil |  | To be Tested once fixed by Dev | Total Manual Execution | 108
New Module Testing | 12 | Kathhir | 22 | Select Approved Payment Instruction Template to Create New Payment Request section | Completed |  |  | Regression Testing | In Progress | 2023-04-21 |  | Space Required | Low | Closed | Garg Nikhil |  |  | Total Automation Execution | 296
Regression Testing | 25 | Vignesh | 15 | 6 Test Scenarios provided by LIPI related to regression | Completed |  |  | Bug Retesting | In Progress |  |  | User able to submit payment req. although user doesn’t have requestor role | High | Closed | Garg Nikhil |  |  | Bugs Identified | 17
Bug Retesting | 22 |  |  | DEV bugs / changes Retesting | Completed |  | 4 new changes given by DEV team | Approve Payment Request section | Yet to Start |  | Development In Progress | Added Rush Request Comments showing error | High | Closed | Garg Nikhil |  |  | Total Bugs | 180
|  |  |  | Bug Created | In Progress |  | Total 11 Resolved 8 Open 3 |  |  |  |  | Amount – Not Support Decimal | High | Closed | Garg Nikhil |  |  | Manual Test Created | 8
[12 empty] | Error Message not Displayed | High | Closed | Garg Nikhil |  |  | Total Manual Case | 116
[12 empty] | Template Not visible in Edit Existing Grid | Medium | Closed | Garg Nikhil |  |  | Automation Scripts Created | 10
[12 empty] | Template Not Visible in Approval Panel But Visible in Track/Edit Grid | High | Open | Garg Nikhil |  | To be Tested once fixed by Dev | Total Automation Scripts | 306
[12 empty] | Delete Button in Edit Existing Payment | Medium | Closed | Garg Nikhil
[12 empty] | Particular BIC value is not accepted | Medium | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Discard Status should be removed | Medium | Closed | Garg Nikhil
[12 empty] | Application takes more time to load during login | Low | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Optimization - On Click of Submit in Create Template | Low | Open | Mukherjee Trishit |  | To be Tested once fixed by Dev
[12 empty] | Sometimes we get a message when we login after the application is timed out | Low | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Performance Issue in File Upload | Low | Open | Mukherjee Trishit |  | To be Tested once fixed by Dev
[12 empty] | Existing Attachment should be loaded when an Approved Template is edited | Medium | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Error message is displayed when Template is Saved from Draft | Medium | Open | Garg Nikhil |  | To be Tested once fixed by Dev

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
Adhoc Testing | 5 | Johnson Benjamin | 28 | Regression Testing | In Progress | 2023-04-21 |  | Test case update (Select Approved Payment Instruction Template to Create New Payment Request section) | In Progress | 2023-04-21 |  | Hom page Keeps loading | Low | Open | Garg Nikhil |  | To be Tested once fixed by Dev | Total Manual Execution | 109
New Module Testing | 17 | Kathhir | 20 | Select Approved Payment Instruction Template to Create New Payment Request section | Completed |  |  | Regression Testing | In Progress | 2023-04-21 |  | Space Required | Low | Closed | Garg Nikhil |  |  | Total Automation Execution | 297
Regression Testing | 15 | Vignesh | 11 | 6 Test Scenarios provided by LIPI related to regression | Completed |  |  | Bug Retesting | In Progress |  |  | User able to submit payment req. although user doesn’t have requestor role | High | Closed | Garg Nikhil |  |  | Bugs Identified | 18
Bug Retesting | 22 |  |  | DEV bugs / changes Retesting | Completed |  | 4 new changes given by DEV team | Approve Payment Request section | Yet to Start |  | Development In Progress | Added Rush Request Comments showing error | High | Closed | Garg Nikhil |  |  | Total Bugs | 181
|  |  |  | Bug Created | In Progress |  | Total 11 Resolved 8 Open 3 |  |  |  |  | Amount – Not Support Decimal | High | Closed | Garg Nikhil |  |  | Manual Test Created | 9
[12 empty] | Error Message not Displayed | High | Closed | Garg Nikhil |  |  | Total Manual Case | 117
[12 empty] | Template Not visible in Edit Existing Grid | Medium | Closed | Garg Nikhil |  |  | Automation Scripts Created | 11
[12 empty] | Template Not Visible in Approval Panel But Visible in Track/Edit Grid | High | Open | Garg Nikhil |  | To be Tested once fixed by Dev | Total Automation Scripts | 307
[12 empty] | Delete Button in Edit Existing Payment | Medium | Closed | Garg Nikhil
[12 empty] | Particular BIC value is not accepted | Medium | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Discard Status should be removed | Medium | Closed | Garg Nikhil
[12 empty] | Application takes more time to load during login | Low | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Optimization - On Click of Submit in Create Template | Low | Open | Mukherjee Trishit |  | To be Tested once fixed by Dev
[12 empty] | Sometimes we get a message when we login after the application is timed out | Low | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Performance Issue in File Upload | Low | Open | Mukherjee Trishit |  | To be Tested once fixed by Dev
[12 empty] | Existing Attachment should be loaded when an Approved Template is edited | Medium | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Error message is displayed when Template is Saved from Draft | Medium | Open | Garg Nikhil |  | To be Tested once fixed by Dev

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
Adhoc Testing | 5 | Johnson Benjamin | 28 | Regression Testing | In Progress | 2023-04-21 |  | Test case update (Select Approved Payment Instruction Template to Create New Payment Request section) | In Progress | 2023-04-21 |  | Hom page Keeps loading | Low | Open | Garg Nikhil |  | To be Tested once fixed by Dev | Total Manual Execution | 110
New Module Testing | 17 | Kathhir | 20 | Select Approved Payment Instruction Template to Create New Payment Request section | Completed |  |  | Regression Testing | In Progress | 2023-04-21 |  | Space Required | Low | Closed | Garg Nikhil |  |  | Total Automation Execution | 298
Regression Testing | 15 | Vignesh | 11 | 6 Test Scenarios provided by LIPI related to regression | Completed |  |  | Bug Retesting | In Progress |  |  | User able to submit payment req. although user doesn’t have requestor role | High | Closed | Garg Nikhil |  |  | Bugs Identified | 19
Bug Retesting | 22 | [6 empty] | Approve Payment Request section | Yet to Start |  | Development In Progress | Added Rush Request Comments showing error | High | Closed | Garg Nikhil |  |  | Total Bugs | 182
[12 empty] | Amount – Not Support Decimal | High | Closed | Garg Nikhil |  |  | Manual Test Created | 10
[12 empty] | Error Message not Displayed | High | Closed | Garg Nikhil |  |  | Total Manual Case | 118
[12 empty] | Template Not visible in Edit Existing Grid | Medium | Closed | Garg Nikhil |  |  | Automation Scripts Created | 12
[12 empty] | Template Not Visible in Approval Panel But Visible in Track/Edit Grid | High | Open | Garg Nikhil |  | To be Tested once fixed by Dev | Total Automation Scripts | 308
[12 empty] | Delete Button in Edit Existing Payment | Medium | Closed | Garg Nikhil
[12 empty] | Particular BIC value is not accepted | Medium | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Discard Status should be removed | Medium | Closed | Garg Nikhil
[12 empty] | Application takes more time to load during login | Low | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Optimization - On Click of Submit in Create Template | Low | Open | Mukherjee Trishit |  | To be Tested once fixed by Dev
[12 empty] | Sometimes we get a message when we login after the application is timed out | Low | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Performance Issue in File Upload | Low | Open | Mukherjee Trishit |  | To be Tested once fixed by Dev
[12 empty] | Existing Attachment should be loaded when an Approved Template is edited | Medium | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Error message is displayed when Template is Saved from Draft | Medium | Open | Garg Nikhil |  | To be Tested once fixed by Dev

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
Adhoc Testing | 10 | Johnson Benjamin | 32 | Regression Testing | In Progress | 2023-04-21 |  | Test case update (Select Approved Payment Instruction Template to Create New Payment Request section) | In Progress | 2023-04-21 |  | Hom page Keeps loading | Low | Open | Garg Nikhil |  | To be Tested once fixed by Dev | Total Manual Execution | 111
New Module Testing | 12 | Kathhir | 22 | Select Approved Payment Instruction Template to Create New Payment Request section | Completed |  |  | Regression Testing | In Progress | 2023-04-21 |  | Space Required | Low | Closed | Garg Nikhil |  |  | Total Automation Execution | 299
Regression Testing | 25 | Vignesh | 15 | 6 Test Scenarios provided by LIPI related to regression | Completed |  |  | Bug Retesting | In Progress |  |  | User able to submit payment req. although user doesn’t have requestor role | High | Closed | Garg Nikhil |  |  | Bugs Identified | 20
Bug Retesting | 22 |  |  | DEV bugs / changes Retesting | Completed |  | 4 new changes given by DEV team | Approve Payment Request section | Yet to Start |  | Development In Progress | Added Rush Request Comments showing error | High | Closed | Garg Nikhil |  |  | Total Bugs | 183
|  |  |  | Bug Created | In Progress |  | Total 11 Resolved 8 Open 3 |  |  |  |  | Amount – Not Support Decimal | High | Closed | Garg Nikhil |  |  | Manual Test Created | 11
[12 empty] | Error Message not Displayed | High | Closed | Garg Nikhil |  |  | Total Manual Case | 119
[12 empty] | Template Not visible in Edit Existing Grid | Medium | Closed | Garg Nikhil |  |  | Automation Scripts Created | 13
[12 empty] | Template Not Visible in Approval Panel But Visible in Track/Edit Grid | High | Open | Garg Nikhil |  | To be Tested once fixed by Dev | Total Automation Scripts | 309
[12 empty] | Delete Button in Edit Existing Payment | Medium | Closed | Garg Nikhil
[12 empty] | Particular BIC value is not accepted | Medium | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Discard Status should be removed | Medium | Closed | Garg Nikhil
[12 empty] | Application takes more time to load during login | Low | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Optimization - On Click of Submit in Create Template | Low | Open | Mukherjee Trishit |  | To be Tested once fixed by Dev
[12 empty] | Sometimes we get a message when we login after the application is timed out | Low | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Performance Issue in File Upload | Low | Open | Mukherjee Trishit |  | To be Tested once fixed by Dev
[12 empty] | Existing Attachment should be loaded when an Approved Template is edited | Medium | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Error message is displayed when Template is Saved from Draft | Medium | Open | Garg Nikhil |  | To be Tested once fixed by Dev

## 8 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Test Issuer performance, portfolio management, portfolio snapshot, investment deal performance screens | 4 | Elakkiya | 4 | Test Issuer performance, portfolio management, portfolio snapshot, investment deal performance screens | Completed |  |  | Data validation for portfolio snapshot | In progress | TBD | [7 empty] | Manual created | 38 | Total manual | 38
Review the test execution | 0.5 | Meenakshi | 0.5 | [14 empty] | Manual execution | 38 | Total manual execution | 38
[18 empty] | Automation created | 0 | Total automation | 0
[18 empty] | Automation execution | 0 | Total automation execution | 0
[18 empty] | Bugs Identified | 0 | Total bugs | 0
[20 empty] | Automation coverage % | 0