## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Connect with Shantanu for KT | 5 | Hrushikesh | 34.5 | 1.HRIS Knowledge transfer | In Progress | 2023-11-17 |  | 1.HRIS knowledge transfer | In Progress | 2023-11-17 |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 6
SQL Training/Learning | 29 |  |  | 2.Sprint Retrospective session | Completed | [13 empty] | Manual execution | 0 | Total manual execution | 6
WSR | 0.5 |  |  | 3.Sprint planning session | Completed | [13 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Connect with Shantanu for KT | 2 | Hrushikesh | 16 | 1.HRIS Knowledge transfer | In Progress |  |  | 1.HRIS knowledge transfer | In Progress | 2023-11-24 |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 6
SQL Training/Learning | 13.5 |  |  | 2.Sprint sizing session | Completed |  |  | 2.SQL trainings &learning activity | In Progress | 2023-11-24 | [8 empty] | Manual execution | 0 | Total manual execution | 6
WSR | 0.5 | [6 empty] | 3.Sprint retrospective &planning sessions | Yet to attend | [9 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Connect with Shantanu for KT | 1 | Hrushikesh | 8 | 1.HRIS Knowledge transfer | In Progress | 2023-12-08 |  | 1.HRIS knowledge transfer | In Progress | 2023-12-01 |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 6
SQL Training/Learning | 6.5 | [6 empty] | 2.SQL trainings &learning activity | In Progress | 2023-12-01 | [8 empty] | Manual execution | 0 | Total manual execution | 6
WSR | 0.5 | [6 empty] | 3.Sprint sizing sessions | Yet to attend | [9 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
SQL learning | 10 | Hrushikesh | 10 | SQL learning | In progress |  |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 6
[8 empty] | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 6
[19 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 4 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
SQL learning | 8 | Hrushikesh | 8 | 1.HRIS Knowledge transfer | In Progress |  |  | 1.HRIS knowledge transfer | In Progress |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 6
|  |  |  | 2.SQL trainings & learnings | In Progress |  |  | 2.SQL trainings &learning activity | In Progress | [9 empty] | Manual execution | 0 | Total manual execution | 6
|  |  |  | 3.Sprint retrospective & planning sessions | Completed |  |  | 3.Sprint sizing sessions | Yet to attend | [9 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 11 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
SQL learning | 8 | Hrushikesh | 8 | 1.HRIS Knowledge transfer | In Progress |  |  | 1.HRIS knowledge transfer | In Progress |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 6
|  |  |  | 2.SQL trainings & learnings | In Progress |  |  | 2.SQL trainings &learning activity | In Progress | [9 empty] | Manual execution | 0 | Total manual execution | 6
|  |  |  | 3.Sprint retrospective & planning sessions | Completed |  |  | 3.Sprint sizing sessions | Yet to attend | [9 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 18 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
HICA-2933 (KT) | 24 | Hrushikesh | 24 | HICA-2933 (KT) | In progress |  |  | 1.HICA-2933 (KT) | In Progress |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 6
[8 empty] | 2.SQL trainings &learning activity | In Progress | [9 empty] | Manual execution | 0 | Total manual execution | 6
[8 empty] | 3.Sprint sizing sessions | Yet to attend | [9 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 26 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
SQL learning | 11 | Hrushikesh | 22 | HICA-2933 (KT) | Inprogress | 2024-01-18 |  | Attend Sprint review and retrospective meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 6
HICA-2933 (KT training) | 11 | [6 empty] | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 6
[19 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 2 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
HICA-2933 (KT) | 25 | Hrushikesh | 25 | Attended Daily Standup calls | Completed |  |  | Attend Sizing and backlog refinement | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 6
|  |  |  | Sprint Review & Retrospective meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 6
|  |  |  | Sprint planning meeting | Completed | [13 empty] | Automation created | 0 | Total automation | 0
|  |  |  | HICA-2933 (KT) | Inprogress | 18-01-2024 | [12 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 8 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
HICA-2933 (KT) | 33 | Hrushikesh | 33 | Attended Daily Standup calls | Completed |  |  | Attend Sizing and backlog refinement | Yet to attend |  |  |  | No defects logged for the week. | [5 empty] | Manual created | 0 | Total manual | 6
|  |  |  | Sizing and Backlog Refinement meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 6
|  |  |  | HICA-2933 (KT) | Completed | [13 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 15 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
Exploring th HRIS DB& Reference tickets | 9 | Hrushikesh | 9 | Exploring the HRIS DB& Reference tickets | In Progress |  |  | Attend Sizing and backlog refinement | Yet to attend |  |  |  | No defects logged for the week. | [5 empty] | Manual created | 0 | Total manual | 6
[8 empty] | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 6
[19 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 22 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
Exploring th HRIS DB& Reference tickets | 8 | Hrushikesh | 8 | Exploring th HRIS DB& Reference tickets | In Progress |  |  | Attend Sprint Review and Retrospective meeting | Yet to attend |  |  |  | No defects logged for the week. | [5 empty] | Manual created | 0 | Total manual | 6
[8 empty] | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 6
[19 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0