## 2 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
Test Issuer performance, portfolio management, portfolio snapshot, investment deal performance screens | 4 | Elakkiya | 4 | Test Issuer performance, portfolio management, portfolio snapshot, investment deal performance screens | Completed |  |  | Data validation for portfolio snapshot | In progress | TBD |  |  | No defect logged for the week | [5 empty] | Manual created | 38 | Total manual | 38
Review the test execution | 0.5 | Meenakshi | 0.5 | [15 empty] | Manual execution | 38 | Total manual execution | 38
[19 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 8 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
Data validation for portfolio snapshot screen | 12 | Elakkiya | 12 | Data validation for portfolio snapshot screen | Completed |  |  | Have to pick up next task | Yet to start |  |  |  | No defect logged for the week | [5 empty] | Manual created | 5 | Total manual | 43
Review the test execution | 1 | Meenakshi | 1 | [15 empty] | Manual execution | 5 | Total manual execution | 43
[19 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0