## 2 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Meetings | 7 | Johnson Benjamin | 53 | Bug Retesting | In-progress. |  | 3 issues raised, 5 closed. | Swift payment testing | In-progress. | 2023-10-10 |  | 177 | If we update a ticket in Treasury Reprocessing screen and click on Approve/Recommend for Rejection button, we are getting error message | High | Closed | Nikhil Garg |  |  | Manual created | 0 | Total manual | 316
Bug Retesting | 61.5 | Kathir | 53.5 |  |  |  | 2 re-open | UAT log fixes / JIRA Tickets | In-progress. |  | 9 in progress, 6 Jira Closed, 3 Jira re-open | 178 | If we open a ticket from "In Setup Review" and directly click on Final Review tab, error message is displayed, the Error message is not displayed if we navigate using the Next button in the first tab. | Low | Open | Nikhil Garg |  | To be tested once Dev provides fix | Manual execution | 233 | Total manual execution | 3565
Reprocessing | 24 | Vignesh | 6 | Reprocessing | Completed. |  |  | Bug Retesting | In Progress. |  | 10 in progress | 179 | If the amount is too big the search is not working, if the amount is small it is working as expected. It is the same for other grids also | Normal | Closed | Garg, Nikhil |  |  | Automation created | 0 | Total automation | 0
Swift Payment testing | 32 | Kalyan Gopi | 12 | Swift payment testing | In-progress. | 2023-10-10 | [5 empty] | 180 | In PPT it is mentioned that only Processor and Approver can see this page | High | Closed | Garg, Nikhil |  |  | Automation execution | 0 | Total automation execution | 0
|  |  |  | UAT log fixes / JIRA Tickets | In-progress. | [13 empty] | Bugs Identified | 4 | Total bugs | 153
[21 empty] | Automation coverage % | 0%

## 9 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Meetings | 7 | Johnson Benjamin | 65 | Bug Retesting | Completed. |  | 1 issue raised, 13 closed. | High Level Regression on Step 2 process. | In-progress. | 16-10-2023 |  |  | No defect logged for the week. | [5 empty] | Manual created | 0 | Total manual | 316
Bug Retesting | 73 | Kathir | 63.5 | Reprocessing | Completed. |  |  | Detailed Regression on Step 2 process | Yet To Start | 20-10-2023 | [8 empty] | Manual execution | 200 | Total manual execution | 3765
Swift Payment testing | 51.5 | Vignesh | 2 | Swift payment testing | Completed. | [13 empty] | Automation created | 0 | Total automation | 0
High Level Regression | 17 | Kalyan Gopi | 18 | UAT log fixes / JIRA Tickets | Completed. |  | 13 closed | [11 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 153
[21 empty] | Automation coverage % | 0%

## 16 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Meetings | 3 | Johnson Benjamin | 46 | Testing the Audit changes from dev for Nov 2nd release | Completed |  |  | Testing the Audit changes from dev. | Yet to Start |  | Will test once the dev team provides it | 181 | Suggestion: By default values are displaying when the ticket is reprocessed for the second time. | Low | Open |  |  |  | Manual created | 0 | Total manual | 316
Regression Testing | 107 | Kathir | 46.6 | Test cases updating for step 2. | In progress |  |  | Test cases updating for step 2 | In progress | [9 empty] | Manual execution | 80 | Total manual execution | 3845
|  | Vignesh | 2.5 |  |  |  |  | UAT logs | Yet to Start |  | Will test once t | [7 empty] | Automation created | 0 | Total automation | 0
|  | Kalyan Gopi | 15 | [15 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 1 | Total bugs | 154
[21 empty] | Automation coverage % | 0%

## 23 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Meetings | 3 | Johnson Benjamin | 20 | Testing the Audit changes from dev for Nov 2nd release | Completed |  |  | Testing the Audit changes from dev for Nov 2nd release | Completed |  |  |  | No defect logged for the week | [5 empty] | Manual created | 84 | Total manual | 400
Audit Enhancement Testing | 57 | Kathir | 32 | Test cases updating for step 2. | In progress |  |  | Test cases updating for step 2 | In progress | [9 empty] | Manual execution | 90 | Total manual execution | 3935
|  | Vignesh | 2 |  |  |  |  | UAT logs | Yet to Start |  | We will test once the dev team provides it. | [7 empty] | Automation created | 0 | Total automation | 0
|  | Kalyan | 6 | [15 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 154
[21 empty] | Automation coverage % | 0%

## 30 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Meetings | 1 | Johnson Benjamin | 41 | Testing the Audit changes from dev for Nov 2nd release | Completed |  |  | Test cases updating for Step 2 | In progress |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 400
New Changes Nov2 Release | 20 | Kathir | 41 | Test cases updating for step 2. | In progress |  |  | Additional Approval process in Call-back. | Yet to Start |  | We will test once the dev team provides it. | [7 empty] | Manual execution | 135 | Total manual execution | 4070
Test case updating for step 2 process. | 63 | Vignesh | 2 |  |  |  |  | Warning box in both the Business Approver and Treasury Approver for payments over $1M+ or $50K. | Yet to Start |  | We will test once the dev team provides it. | [7 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 154
[21 empty] | Automation coverage % | 0%

## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Meetings | 3 | Johnson Benjamin | 24 | Solution Update testing | In progress | 14/11/2023 |  | Test cases updating for Step 2 | In progress |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 400
Solution Update testing | 33 | Kathir | 42 | Test cases updating for step 2. | In progress |  |  | Solution Update testing | In progress | 14/11/2023 | [8 empty] | Manual execution | 120 | Total manual execution | 4190
Test case updation for step 2 process. | 31 | Vignesh | 1 |  |  |  |  | Additional Approval process in Call-back. | Yet to Start |  | We will test once the dev team provides it. | [7 empty] | Automation created | 0 | Total automation | 0
[8 empty] | Making Beneficiary Address and City for HSBC bank accounts. | Yet to start |  | We will test once the dev team provides it. | [7 empty] | Automation execution | 0 | Total automation execution | 0
[8 empty] | Warning box in both the Business Approver and Treasury Approver for payments over $1M+ or $50K. | Yet to Start |  | We will test once the dev team provides it. | [7 empty] | Bugs Identified | 0 | Total bugs | 154
[21 empty] | Automation coverage % | 0%

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Meetings | 3 | Johnson Benjamin | 34 | Solution Upgrade testing | In progress | 20/11/2023 | Testing completed; Issues assigned to Dev. | Test cases update for Step 2 | In progress |  |  | 182 | Requestor is able to submit a payment request without entering Financial approver. | High | Closed | Nikhil Garg |  |  | Manual created | 0 | Total manual | 400
Solution Update testing | 16 | Kathir | 34 | Audit Enhancement testing - Warning box in both the Business Approver and Treasury Approver for payments over $1M+ | Completed |  |  | Solution Upgrade testing | In progress | 20/11/2023 |  | 183 | Value Date is accepting Sat and Sun in Payment Failed - Treasury Reprocessing Status | Normal | New | Garg, Nikhil |  |  | Manual execution | 230 | Total manual execution | 4420
Audit Enhancement testing | 22 | Vignesh | 1 | Testing Edit existing template and Revise payment template. | In progress | 20/11/2023 |  | Testing Edit existing template and Revise payment template. | In progress | 20/11/2023 |  | 184 | Edit an Existing template not working if SWIFT payment successful | High | New | Garg, Nikhil |  |  | Automation created | 0 | Total automation | 0
Testing Edit and Revise payment templates | 28 |  |  | Test cases updating for step 2. | In progress |  |  | Value date should not be weekend. | In progress | 21/11/2023 |  | 185 | Validation message should not be displayed when we enter amount as “-1” In the 2nd validation the message should be “Amount should be between 1 and 100 trillion”, attached screenshot | Normal | New | Garg, Nikhil |  |  | Automation execution | 0 | Total automation execution | 0
[8 empty] | Select all check box in Payment staging interface | In progress | 20/11/2023 |  | 186 | When Age is given in two or three digit issue is still occurring. Also Age field should not be less than 0, currently when decremental button is clicked from 0 negative values are displayed. | Normal | New | Garg, Nikhil |  |  | Bugs Identified | 8 | Total bugs | 162
[8 empty] | Max length Validation message In Amount field. | In progress | 21/11/2023 |  | 187 | Payment tag type should not be displayed in green color, attached screenshot of New version and old version. | Normal | New | Garg, Nikhil |  |  |  |  | Automation coverage % | 0%
[8 empty] | Additional Approval process in Call-back. | Yet to Start | 23/11/2023 | Testing will be started once deployment is done. | 188 | Calendar icon issue | Normal | New | Garg, Nikhil
[12 empty] | 189 | Age field issue. | Normal | New | Garg, Nikhil

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Meetings | 5 | Johnson Benjamin | 51 | Solution Upgrade testing | In progress | 28/11/2023 |  | Test cases update for Step 2 | In progress |  |  | 190 | Calendar icon issue. | Normal | New | Garg, Nikhil |  |  | Manual created | 48 | Total manual | 448
Solution Update testing | 11 | Kathir | 51 | Audit Enhancement testing - Warning box in both the Business Approver and Treasury Approver for payments over $1M+ | In progress | 27/11/2023 |  | Solution Upgrade testing | In progress | 28/11/2023 | [8 empty] | Manual execution | 163 | Total manual execution | 4583
Audit Enhancement testing | 70.5 | Vignesh | 5.5 | Value date should not be weekend. | Completed |  |  | Audit Enhancement testing - Warning box in both the Business Approver and Treasury Approver for payments over $1M+ | Completed | [9 empty] | Automation created | 0 | Total automation | 0
Testing Edit and Revise payment templates | 35 | Kalyan Gopi | 35 | Testing Edit existing template and Revise payment template. | In progress | 27/11/2023 |  | JIRA tickets testing. | In progress | 28/11/2023 | [8 empty] | Automation execution | 0 | Total automation execution | 0
JIRA tickets | 21 |  |  | Audit Enhancement testing - Additional Approval process in Call-back Verification. | In progress | 27/11/2023 |  | Testing Edit existing template and Revise payment template. | Completed | [9 empty] | Bugs Identified | 1 | Total bugs | 163
|  |  |  | JIRA tickets testing. | In progress | 28/11/2023 |  | Audit Enhancement testing - Additional Approval process in Call-back Verification. | Completed | [11 empty] | Automation coverage % | 0%
|  |  |  | Max length Validation message In Amount field. | Completed
|  |  |  | Added Required to label for Beneficiary Address and City in Step 1 | Completed
|  |  |  | Test cases updating for step 2. | In progress

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Meetings | 2 | Johnson Benjamin | 43 | Solution Upgrade testing. | Completed |  |  | Test cases update for Step 2 | In progress |  |  | 191 | User has Treasury processor and Call back verifier and user has not submitted call back verifier and approving as Treasury processor. | High | Closed | Nikhil Garg |  |  | Manual created | 36 | Total manual | 484
Solution Update testing | 4 | Kathir | 43 | JIRA tickets testing. | Completed |  |  | Role based testing in Grids. | In progress |  |  | 192 | Rush mail is triggered when, fund approver approves from Teams or Emails | High | Open | Nikhil Garg |  |  | Manual execution | 140 | Total manual execution | 4723
Audit Enhancement testing | 28 | Vignesh | 4.5 | Audit Enhancement testing – Call back verification. | Completed |  |  | Led - User Address update. | Yet to Start |  | Will be tested, once it is deployed. | [7 empty] | Automation created | 0 | Total automation | 0
Testing Edit and Revise payment templates | 16.5 | Kalyan Gopi | 4 | Edit Existing and Revise template testing. | Completed | [13 empty] | Automation execution | 0 | Total automation execution | 0
Role based testing | 30 |  |  | Bugs retesting. | Completed. | [13 empty] | Bugs Identified | 1 | Total bugs | 164
JIRA tickets | 14 |  |  | Role based testing in Grids. | In progress. | [15 empty] | Automation coverage % | 0%
|  |  |  | Test cases updating for step 2. | In progress
|  |  |  | Added Required to label for Beneficiary Address and City in Step 1 | Completed
|  |  |  | Test cases updating for step 2. | In progress

## 4 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Meetings | 2 | Johnson Benjamin | 40 | JIRA tickets testing. | Completed |  |  | Test cases update for Step 2. | In progress |  |  | 193 | LED Address is getting updated for Status: Payment Sent for SWIFT Processing | Medium | Open | Nikhil Garg |  |  | Manual created | 56 | Total manual | 540
Testcase updation | 12 | Kathir | 32 | Role based testing. | In progress. | 15-12-2023 |  | Role based testing. | In progress | 15-12-2023 | [8 empty] | Manual execution | 120 | Total manual execution | 4843
Role based testing | 26 | Vignesh | 1.5 | Led - User Address update. | In progress | 2023-12-12 |  | Led - User Address update. | In progress | 2023-12-12 | [8 empty] | Automation created | 0 | Total automation | 0
Led – Address change testing | 29.5 |  |  | Test cases updating for step 2. | In progress | [13 empty] | Automation execution | 0 | Total automation execution | 0
Bug retesting | 4 | [17 empty] | Bugs Identified | 1 | Total bugs | 165
[21 empty] | Automation coverage % | 0%

## 11 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Meetings | 5 | Johnson Benjamin | 32 | Role based testing. | In progress. |  |  | Test cases update for Step 2. | In progress | 22/12/2023 |  |  | No defect logged for the week | [5 empty] | Manual created | 30 | Total manual | 570
Testcase updating | 12 | Kathir | 23 | Led - User Address update. | In progress |  | One open ticket | Role based testing. | In progress | [9 empty] | Manual execution | 110 | Total manual execution | 4953
Led – Address change testing | 36 | Vignesh | 2 | Test cases updating for step 2. | In progress | 22/12/2023 |  | Led - User Address update. | In progress |  | One open ticket, waiting for Dev to fix the issue | [7 empty] | Automation created | 0 | Total automation | 0
Bug retesting | 4 | [6 empty] | POP (Purpose of Payment) | Yet to start |  | Will start once deployment is done | [7 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 165
[21 empty] | Automation coverage % | 0%

## 18 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Meetings | 2 | Johnson Benjamin | 14 | Role based testing. | In progress. | 29/12/2023 |  | Test cases update for Step 2. | In progress | 29/12/2023 |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 570
Testcase updating | 10 | Kathir | 30 | Led - User Address update. | In progress |  | One open ticket | Role based testing. | In progress | 29/12/2023 | [8 empty] | Manual execution | 0 | Total manual execution | 4953
Led – Address change testing | 17 | Vignesh | 2.5 | Call back verifier testing | Completed |  |  | Led - User Address update. | In progress |  | One open ticket, waiting for Dev to fix the issue | [7 empty] | Automation created | 0 | Total automation | 0
Call back verifier testing | 17.5 |  |  | Test cases updating for step 2. | In progress | 29/12/2023 |  | Call back verifier testing | Completed | [9 empty] | Automation execution | 0 | Total automation execution | 0
[8 empty] | POP (Purpose of Payment) | Yet to start |  | Testing to be initiated on Jan 2 | [7 empty] | Bugs Identified | 0 | Total bugs | 165
[21 empty] | Automation coverage % | 0%

## 26 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
Meetings | 2 | Johnson Benjamin | 28 | Role based testing. | In progress. | 12/01/2024 |  | Test cases update for Step 2. | In progress | 2024-12-01 |  |  | No defect logged for the week | [5 empty] | Manual created | 16 | Total manual | 586
Testcase updating | 12 | Kathir | 28 | Led - User Address update (Regression). | In progress | 05/01/2024 |  | Role based testing. | In progress | 2024-12-01 | [8 empty] | Manual execution | 120 | Total manual execution | 5073
Led – Address change testing | 17 | Vignesh | 2 | POP testing | In progress | 2024-08-01 |  | Bug retesting | In progress | 2024-08-01 | [8 empty] | Automation created | 0 | Total automation | 0
POP testing | 10 |  |  | Bug retesting | In progress | 2024-08-01 |  | Led - User Address update (Regression). | In progress | 2024-05-01 | [8 empty] | Automation execution | 0 | Total automation execution | 0
Bugs retesting | 17 |  |  | Test cases updating for step 2. | In progress | 2024-12-01 |  | Call back verifier – Regression | In progress | 2024-05-01 | [8 empty] | Bugs Identified | 0 | Total bugs | 165
[8 empty] | POP (Purpose of Payment) | In progress | 2024-08-01 | [10 empty] | Automation coverage % | 0%

## 2 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
Meetings | 2 | Johnson Benjamin | 32 | Led - User Address update (Regression). | In progress | 2024-09-01 |  | Test cases update for Step 2. | In progress | 2024-12-01 |  | WMT-2975 | If only FFC Account Name is provided in OT Step 1, it is not added to SWIFT file. | Medium | New | Swikriti |  |  | Manual created | 0 | Total manual | 586
Led – Address change testing | 5 | Kathir | 32 | POP testing - (Purpose of Payment) | In progress | 2024-09-01 |  | Role based testing. | In progress | 2024-12-01 | [8 empty] | Manual execution | 180 | Total manual execution | 5253
POP testing | 57 | Vignesh | 2 | Jira tickets/Bug retesting | In progress | 2024-12-01 |  | Jira tickets/Bug retesting | In progress | 2024-12-01 | [8 empty] | Automation created | 0 | Total automation | 0
Bugs retesting | 2 | [6 empty] | Led - User Address update (Regression). | In progress | 2024-09-01 | [8 empty] | Automation execution | 0 | Total automation execution | 0
[8 empty] | Call back verifier – Regression | In progress | 2024-09-01 | [8 empty] | Bugs Identified | 1 | Total bugs | 166
[8 empty] | POP testing - (Purpose of Payment) | In progress | 2024-09-01 | [10 empty] | Automation coverage % | 0%

## 8 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
Meetings | 2 | Johnson Benjamin | 45 | Led - User Address update (Regression). | Completed |  |  | Test cases update for Step 2. | In progress | 19/01/2024 |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 586
Led – Address change testing | 33 | Kathir | 45 | POP testing - (Purpose of Payment) | Completed |  |  | Role based testing. | In progress | 19/01/2024 | [8 empty] | Manual execution | 160 | Total manual execution | 5413
POP testing | 41.5 | Vignesh | 2.5 | Call back verification (Regression) | Completed |  |  | Jira tickets/Bug retesting | In progress | 16/01/2024 | [8 empty] | Automation created | 0 | Total automation | 0
Call back verification | 12 |  |  | Jira tickets/Bug retesting | In progress | 16/01/2024 | [12 empty] | Automation execution | 0 | Total automation execution | 0
Bug retesting | 4 | [17 empty] | Bugs Identified | 0 | Total bugs | 166
[21 empty] | Automation coverage % | 0%

## 15 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
Meetings | 1 | Johnson Benjamin | 14 | Test cases update for Step 2. | Completed |  |  | Role based testing. | In progress | 2024-01-25 |  |  | No defect logged for the week | [5 empty] | Manual created | 50 | Total manual | 636
Test cases update for Step 2. | 24 | Kathir | 22 | Sanity test for Jan 22 release | Completed | [13 empty] | Manual execution | 90 | Total manual execution | 5503
POP testing | 3 | Vignesh | 2 | Jira tickets/Bug retesting | Completed | [13 empty] | Automation created | 0 | Total automation | 0
Jira ticket/Bug retesting | 10 | [17 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 166
[21 empty] | Automation coverage % | 0%

## 22 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
Meetings | 1 | Johnson Benjamin | 29 | CFU document review | Completed |  |  | Jira/Bug retesting | In progress | 2024-02-01 |  | WMT-3230 | Warning message is displayed as Swift BIC is not available in LED | Medium | Open | Lipi |  |  | Manual created | 0 | Total manual | 636
Role based testing | 55 | Kathir | 29 | Role based testing. | In progress | 29/01/2024 |  | Role based testing. | In progress | 29/01/2024 |  | WMT- 3232 | User is able to edit Calendar in Read Only screens | Medium | Open | Lipi |  |  | Manual execution | 110 | Total manual execution | 5613
CFU document review | 4 | Vignesh | 2 |  |  |  |  | CFU testing | Yet to Start |  | Will start the testing once it is deployed. | WMT - 3275 | User is able to Submit a ticket as Requestor and Callback Verifier | Medium | Open | Lipi |  |  | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 3 | Total bugs | 169
[21 empty] | Automation coverage % | 0%