## 2 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
vEMS:Daily StandUp - Internal | 4.5 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 73
Test Case design/ Defect Tracker Update/ Jira Update | 1.5 | Saravanan munikrishnan | 8.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Manual execution | 5 | Total manual execution | 613
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation created | 0 | Total automation | 73
vEMS: AR/AP Dashboard | 2.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation execution | 16 | Total automation execution | 816
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 3.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs Identified | 0 | Total bugs | 41
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 3.5 | [19 empty] | Automation coverage % | 100%
vEMS: Ad-hoc testing request | 5.5
vEMS: WOR-512 (Refund Status as paid) | 1.5
vEMS: Automation Script Enhancement | 6.5
vEMS: Automation(Multi SR & Power Bi) | 1

## 9 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
vEMS:Daily StandUp - Internal | 4.5 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 73
Test Case design/ Defect Tracker Update/ Jira Update | 1.5 | Saravanan munikrishnan | 8.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Manual execution | 6 | Total manual execution | 619
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation created | 0 | Total automation | 73
vEMS: AR/AP Dashboard | 2.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation execution | 18 | Total automation execution | 834
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 3.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs Identified | 0 | Total bugs | 41
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 3.5 | [19 empty] | Automation coverage % | 100%
vEMS: Ad-hoc testing request | 5.5
vEMS: WOR-512 (Refund Status as paid) | 1.5
vEMS: Automation Script Enhancement | 6.5
vEMS: Automation(Multi SR & Power Bi) | 1

## 16 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
vEMS:Daily StandUp - Internal | 4.5 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 73
Test Case design/ Defect Tracker Update/ Jira Update | 1.5 | Saravanan munikrishnan | 8.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Manual execution | 7 | Total manual execution | 626
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation created | 0 | Total automation | 73
vEMS: AR/AP Dashboard | 2.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation execution | 20 | Total automation execution | 854
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 3.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs Identified | 0 | Total bugs | 41
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 3.5 | [19 empty] | Automation coverage % | 100%
vEMS: Ad-hoc testing request | 5.5
vEMS: WOR-512 (Refund Status as paid) | 1.5
vEMS: Automation Script Enhancement | 6.5
vEMS: Automation(Multi SR & Power Bi) | 1

## 23 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
vEMS:Daily StandUp - Internal | 4.5 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 73
Test Case design/ Defect Tracker Update/ Jira Update | 1.5 | Saravanan munikrishnan | 8.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Manual execution | 6 | Total manual execution | 632
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation created | 0 | Total automation | 73
vEMS: AR/AP Dashboard | 2.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation execution | 18 | Total automation execution | 872
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 3.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs Identified | 0 | Total bugs | 41
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 3.5 | [19 empty] | Automation coverage % | 100%
vEMS: Ad-hoc testing request | 5.5
vEMS: WOR-512 (Refund Status as paid) | 1.5
vEMS: Automation Script Enhancement | 6.5
vEMS: Automation(Multi SR & Power Bi) | 1

## 30 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
vEMS:Daily StandUp - Internal | 4.5 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 73
Test Case design/ Defect Tracker Update/ Jira Update | 1.5 | Saravanan munikrishnan | 8.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Manual execution | 6 | Total manual execution | 638
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation created | 0 | Total automation | 73
vEMS: AR/AP Dashboard | 2.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation execution | 14 | Total automation execution | 886
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 3.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs Identified | 0 | Total bugs | 41
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 3.5 | [19 empty] | Automation coverage % | 100%
vEMS: Ad-hoc testing request | 5.5
vEMS: WOR-512 (Refund Status as paid) | 1.5
vEMS: Automation Script Enhancement | 6.5
vEMS: Automation(Multi SR & Power Bi) | 1

## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
vEMS:Daily StandUp - Internal | 5 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 73
Test Case design/ Defect Tracker Update/ Jira Update | 2.5 | Saravanan munikrishnan | 5 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Regression Testing will be done, once issue fixed | [7 empty] | Manual execution | 5 | Total manual execution | 643
vEMS: Triage / Review Meeting - Testing and Defects | 2.5 | Vignesh dhakshnamoorthy | 9.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Requirement got changed, waiting for new changes | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation created | 0 | Total automation | 73
vEMS: AR/AP Dashboard | 9.5 |  |  | WD-Regression Suite | Blocked | TBD | Phase-5:- Power Bi validation: Blocked due to INT101D issue | WD-Regression Suite | Blocked | TBD | Phase-5- Power Bi: Blocked by INT101D issue | [7 empty] | Automation execution | 12 | Total automation execution | 898
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 2 |  |  | AR/AP Dashboard | In Progress | 2023-11-21 | FIN Reports: Worked on Requirement gathering & Access Working on Table design | AR/AP Dashboard | In Progress | 2023-11-21 | FIN Reports: Work on Table design and waiting for Data from vEMS | [7 empty] | Bugs Identified | 0 | Total bugs | 41
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 3 | [19 empty] | Automation coverage % | 100%
vEMS: Automation Script Enhancement | 2.5
vEMS: Automation(Multi SR & Power Bi) | 7.5

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
vEMS:Daily StandUp - Internal | 3 | Pramod rayate | 8 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 73
Test Case design/ Defect Tracker Update/ Jira Update | 1 | Saravanan munikrishnan | 8.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Functionality working as expected, Pending to check in FPNA | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Will check FPNA and start Full regression | [7 empty] | Manual execution | 7 | Total manual execution | 650
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 14 | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Functionality working as expected, Pending to check in FPNA | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Will check FPNA and start Full regression | [7 empty] | Automation created | 0 | Total automation | 73
vEMS: AR/AP Dashboard | 14 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | [7 empty] | Automation execution | 16 | Total automation execution | 914
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 2 | [5 empty] | creating fresh data for validation |  |  |  | Prepare data and put more validation | [7 empty] | Bugs Identified | 0 | Total bugs | 41
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 2 |  |  | AR/AP Dashboard | In Progress | 2023-11-24 | FIN Reports: Worked on Requirement gathering & Access | AR/AP Dashboard | In Progress | 2023-11-24 | FIN Reports: Get data & Access for vEMS | [9 empty] | Automation coverage % | 100%
vEMS: Automation Script Enhancement | 3 | [5 empty] | Worked on Table design, able to receive data for Workday |  |  |  | Work on feeding data in dashboard
vEMS: Automation(Multi SR & Power Bi) | 4.5

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
vEMS:Daily StandUp - Internal | 5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | 2023-12-05 | started Full regression in OAK-2 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 73
Test Case design/ Defect Tracker Update/ Jira Update | 1 | Saravanan munikrishnan | 19.5 | WOR-823, 824: Refund to use Bank Rate | Completed | 2023-11-21 | Functionality working as expected, Issue found in FPNA | WOR-882: Refund to use Bank Rate | In Progress | 2023-12-05 | Continue Full regression in OAK-2 and OAK-1 | [7 empty] | Manual execution | 4 | Total manual execution | 654
vEMS: Triage / Review Meeting - Testing and Defects | 2 | Vignesh dhakshnamoorthy | 8 | WOR-817, 818: ADJ to use Bank Rate | Completed | 2023-11-21 | Functionality working as expected, Issue found in FPNA | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | [7 empty] | Automation created | 0 | Total automation | 73
vEMS: AR/AP Dashboard | 8 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress |  |  |  | Prepare data and put more validation | [7 empty] | Automation execution | 8 | Total automation execution | 922
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 2 | [5 empty] | creating fresh data for validation | AR/AP Dashboard | In Progress | 2023-12-01 | FIN Reports: Get data & Access for vEMS | [7 empty] | Bugs Identified | 0 | Total bugs | 41
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 2 |  |  | AR/AP Dashboard | In Progress | 2023-12-01 | FIN Reports: Worked on Requirement gathering & Access |  |  |  | Waiting for data from vEMS & Navision | [9 empty] | Automation coverage % | 100%
vEMS: WOR-882 (Refund to use Bank rate) | 4 | [5 empty] | Table design completed, waiting for vEMS & Navision
vEMS: Automation Script Enhancement | 5
vEMS: Automation(Multi SR & Power Bi) | 18.5

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
vEMS:Daily StandUp - Internal | 2.5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | 2023-12-05 | started Full regression in OAK-2, Faced issue in INT0209 & INT0210a | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 73
Test Case design/ Defect Tracker Update/ Jira Update | 2.5 | Saravanan munikrishnan | 17 | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress. created fresh data for validation | WOR-882: Refund to use Bank Rate | Blocked | TBD | Waiting for fix on issue with INT0209 & INT0210a | [7 empty] | Manual execution | 4 | Total manual execution | 658
vEMS: Triage / Review Meeting - Testing and Defects | 1.5 | Vignesh dhakshnamoorthy | 8 | AR/AP Dashboard | In Progress | 2023-12-05 | FIN Reports Phase-1: Ready to consume Prod data | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress created fresh data for validation | [7 empty] | Automation created | 0 | Total automation | 73
vEMS: AR/AP Dashboard | 8 | [6 empty] | AR/AP Dashboard | In Progress | 2023-12-05 | FIN Reports Phase-1: Ready to consume Prod data | [7 empty] | Automation execution | 10 | Total automation execution | 932
vEMS: WOR-882 (Refund to use Bank rate) | 3.5 | [17 empty] | Bugs Identified | 0 | Total bugs | 41
vEMS: Automation Script Enhancement | 5 | [19 empty] | Automation coverage % | 100%
vEMS: Automation(Multi SR & Power Bi) | 22

## 4 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
vEMS:Daily StandUp - Internal | 3.5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | TBD | Found issue in INT0209 & INT0210a, waiting for fix | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_288 | ER Line count was complete mismatch with Finsmart | Low | Closed | Vikas |  |  | Manual created | 20 | Total manual | 93
Test Case design/ Defect Tracker Update/ Jira Update | 1.5 | Saravanan munikrishnan | 2 | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress Preparing additional validation list | WOR-882: Refund to use Bank Rate | Blocked | TBD | Found issue in INT0209 & INT0210a, waiting for fix | [7 empty] | Manual execution | 5 | Total manual execution | 663
vEMS: Triage / Review Meeting - Testing and Defects | 2 | Vignesh dhakshnamoorthy | 5 | AR/AP Dashboard | In Progress | 2023-12-11 | FIN Reports Phase-1: Ready to consume Prod data | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress Preparing additional validation list | [7 empty] | Automation created | 10 | Total automation | 83
vEMS: AR/AP Dashboard | 5 | [6 empty] | AR/AP Dashboard | In Progress | 2023-12-11 | FIN Reports Phase-1: Ready to consume Prod data. will work on vEMS data at FTP | [7 empty] | Automation execution | 20 | Total automation execution | 952
vEMS: WOR-882 (Refund to use Bank rate) | 4.5 | [17 empty] | Bugs Identified | 1 | Total bugs | 42
vEMS: Ad-hoc business requests | 3 | [19 empty] | Automation coverage % | 89.25%
vEMS: Automation(Multi SR & Power Bi) | 7.5

## 11 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
vEMS:Daily StandUp - Internal | 3.5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | TBD | Found issue in INT0209 & INT0210a, waiting for fix | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_289 | Missing Fx journal(Boomerang) entries in FPNA report | Medium | Open | William |  |  | Manual created | 12 | Total manual | 105
Test Case design/ Defect Tracker Update/ Jira Update | 2 | Saravanan munikrishnan | 14.5 | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress Preparing additional validation list | WOR-882: Refund to use Bank Rate | Blocked | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | Observation_290 | CPAY not populating at Allocation Key in FPNA report | Medium | Open | William |  |  | Manual execution | 3 | Total manual execution | 666
vEMS: Triage / Review Meeting - Testing and Defects | 2 | Vignesh dhakshnamoorthy | 5 | AR/AP Dashboard | In Progress | 2023-12-18 | FIN Reports Phase-1: Completed Analyzed schedule time to run scripts for WD & vEMS | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress Review additional validation list with William | [7 empty] | Automation created | 20 | Total automation | 103
vEMS: AR/AP Dashboard | 6 | [6 empty] | AR/AP Dashboard | In Progress | 2023-12-19 | FIN Reports Phase-1: will work on vEMS data at FTP & Set up the schedule run at right time | [7 empty] | Automation execution | 24 | Total automation execution | 976
vEMS: WOR-882 (Refund to use Bank rate) | 4.5 | [17 empty] | Bugs Identified | 2 | Total bugs | 44
vEMS: Ad-hoc business requests | 5 | [19 empty] | Automation coverage % | 98.1%
vEMS: Automation Script Enhancement | 7.5
vEMS: Automation(Multi SR & Power Bi) | 9

## 18 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
vEMS:Daily StandUp - Internal | 3.5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | TBD | worked on WOR-927 with Ramesh, issue not yet resolved | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual created | 10 | Total manual | 115
Test Case design/ Defect Tracker Update/ Jira Update | 3 | Saravanan munikrishnan | 15.5 | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Adding scripts for vEMS allocation variants | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | [7 empty] | Manual execution | 4 | Total manual execution | 670
vEMS: Triage / Review Meeting - Testing and Defects | 3 | Vignesh dhakshnamoorthy | 7.5 | AR/AP Dashboard | In Progress | 2023-12-19 | FIN Reports Phase-1: Completed | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Adding scripts for vEMS allocation variants | [7 empty] | Automation created | 12 | Total automation | 115
vEMS: AR/AP Dashboard | 11.5 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Initial analysis done on Test scripts from Business side and Environment readiness | AR/AP Dashboard | In Progress | 2023-12-29 | FIN Reports Phase-1: will work on vEMS data at FTP & Set up the schedule run at right time | [7 empty] | Automation execution | 20 | Total automation execution | 996
vEMS: WOR-882 (Refund to use Bank rate) | 0.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | TBD | Work on keeping the test Pre-requisites ready | [7 empty] | Bugs Identified | 0 | Total bugs | 44
vEMS: Ad-hoc business requests | 4.5 | [19 empty] | Automation coverage % | 100%
vEMS: Automation Script Enhancement | 11
vEMS: Automation(Multi SR & Power Bi) | 6

## 26 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
vEMS: Daily Stand Up - Internal | 3.5 | Pramod rayate | 12 | WOR-882: Refund to use Bank Rate | In Progress | TBD | worked on WOR-927 with Ramesh, issue not yet resolved | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual created | 8 | Total manual | 123
Test Case design/ Defect Tracker Update/ Jira Update | 1 | Saravanan munikrishnan | 7.5 | WD-Regression Suite | In Progress | TBD | Phase-5:- Added scripts for vEMS allocation variations | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | [7 empty] | Manual execution | 4 | Total manual execution | 674
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 4 | AR/AP Dashboard | Completed | 2024-12-29 | FIN Reports Phase-1: Completed | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Will verify scripts for WD & vEMS allocation variants | [7 empty] | Automation created | 8 | Total automation | 123
vEMS: AR/AP Dashboard | 4 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Prepared and checked feasibility of the business scenarios in OAK-2 | AR/AP Dashboard | In Progress | 2024-01-04 | FIN Reports Phase-1: will work on vEMS data at FTP & Set up the schedule run at right time | [7 empty] | Automation execution | 16 | Total automation execution | 1012
vEMS: WOR-939 SC, BR, COA mapping | 5.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-15 | Work on keeping the test Pre-requisites ready and kick off once we final review completed | [7 empty] | Bugs Identified | 0 | Total bugs | 44
vEMS: Automation Script Enhancement | 5.5 | [19 empty] | Automation coverage % | 100%
vEMS: Automation(Multi SR & Power Bi) | 3

## 2 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
vEMS:Daily StandUp - Internal | 4 | Pramod rayate | 16 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 123
Test Case design/ Defect Tracker Update/ Jira Update | 1 | Saravanan munikrishnan | 7 | WD-Regression Suite | In Progress | TBD | Phase-5:- Added scripts for WOR-939 having WD & vEMS allocation variations | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | [7 empty] | Manual execution | 2 | Total manual execution | 676
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 4 | AR/AP Dashboard | Completed | 2024-01-02 | FIN Reports Phase-1: Completed. Monitoring data count & performance | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Will enhance scripts for WD & vEMS allocation variants | [7 empty] | Automation created | 0 | Total automation | 123
vEMS: AR/AP Dashboard | 4 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Discussed & Reviewed the business scenarios in OAK-2 | AR/AP Dashboard | In Progress | TBD | FIN Reports Phase-1: will work on vEMS data at FTP & Set up the schedule run at right time | [7 empty] | Automation execution | 14 | Total automation execution | 1026
vEMS: WOR-939 SC, BR, COA mapping | 7.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-15 | Work on keeping the test Pre-requisites ready and kick off once we final review completed | [7 empty] | Bugs Identified | 0 | Total bugs | 44
vEMS: Automation Script Enhancement | 5 | [19 empty] | Automation coverage % | 100%
vEMS: Automation(Multi SR & Power Bi) | 4.5

## 8 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count |  | Project Metrics | Total Count
vEMS:Daily StandUp - Internal | 5 | Pramod rayate | 30 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_298 | SINV & ER Allocation Count mis-matches with Finsmart count at vEMS side | Medium | Open | Vikas |  |  | Manual created |  | 0 | Total manual | 123
Test Case design/ Defect Tracker Update/ Jira Update | 1 | Saravanan munikrishnan | 17.5 | WD-Regression Suite | In Progress | TBD | Phase-5:- Added scripts for WOR-939 having WD & vEMS allocation variations- Checked & verified | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | Observation_302 | Spend Category / Expense Item not found in vEMS | High | Open | Vikas |  |  | Manual execution |  | 0 | Total manual execution | 676
vEMS: Triage / Review Meeting - Testing and Defects | 2 | Vignesh dhakshnamoorthy | 4 | AR/AP Dashboard | Completed |  | FIN Reports Phase-1: Completed Monitoring data count & performance | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Enhance scripts for WD & vEMS allocation variants as needed | Observation_303 | SC and BR not a valid combination as per Allowability matrix | High | Open | Vikas |  |  | Automation created |  | 0 | Total automation | 123
vEMS: AR/AP Dashboard | 4 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Test execution - In Progress (Blocked due to issue) | AR/AP Dashboard | In Progress | TBD | FIN Reports Phase-1: Merge Prod & Dev in single to make it centralized | [7 empty] | Automation execution |  | 10 | Total automation execution | 1036
vEMS: WOR-939 SC, BR, COA mapping | 27 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-19 | Will get issues resolved and complete testing | [7 empty] | Bugs Identified |  | 3 | Total bugs | 47
vEMS: Automation Script Enhancement | 3 | [20 empty] | Automation coverage % | 100%
vEMS: Automation(Multi SR & Power Bi) | 9.5

## 15 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
vEMS:Daily StandUp - Internal | 3 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_307 | CINV Issue- getting error as "Validation error occurred. Invalid ID value. '' is not a valid ID value for type = 'Revenue_Category_ID'" | Critical | Open |  |  |  | Manual created | 0 | Total manual | 123
Test Case design/ Defect Tracker Update/ Jira Update | 1 | Saravanan munikrishnan | 17 | WD-Regression Suite | In Progress | TBD | Phase-5:- Added scripts for WOR-939 having WD & vEMS allocation variations- Checked & verified | WOR-882: Refund to use Bank Rate | On Hold | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | [7 empty] | Manual execution | 0 | Total manual execution | 676
vEMS: Triage / Review Meeting - Testing and Defects | 4.5 | Vignesh dhakshnamoorthy | 2 | AR/AP Dashboard | Completed |  | FIN Reports Phase-1: Completed | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold | [7 empty] | Automation created | 0 | Total automation | 123
[7 empty] | Monitoring data count & performance |  |  |  | Enhance scripts for WD & vEMS allocation variants as needed
vEMS: AR/AP Dashboard | 2 |  |  | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-25 | Test execution - In Progress (Impacted due to issue) | AR/AP Dashboard | In Progress | 2024-01-30 | FIN Reports Phase-1: Merge Prod & Dev in single to make it centralized - ETA-30-Jan | [7 empty] | Automation execution | 30 | Total automation execution | 1066
vEMS: WOR-939 SC, BR, COA mapping | 11.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-25 | Will get issues resolved and complete testing | [7 empty] | Bugs Identified | 1 | Total bugs | 48
vEMS: Automation Script Enhancement | 8 | [19 empty] | Automation coverage % | 100%
vEMS: Automation(Multi SR & Power Bi) | 9

## 22 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
vEMS:Daily StandUp - Internal | 4 | Pramod rayate | 18 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_308 | Vichara team did not send latest prod count to FTP location | Medium | Closed | Vikas |  |  | Manual created | 0 | Total manual | 123
Test Case design/ Defect Tracker Update/ Jira Update | 3 | Saravanan munikrishnan | 16.5 | WD-Regression Suite | In Progress | TBD | Phase-5:- Fine tuned scripts for WOR-939 having WD & vEMS allocation variations- Checked & verified | WOR-882: Refund to use Bank Rate | On Hold | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | [7 empty] | Manual execution | 0 | Total manual execution | 676
vEMS: Triage / Review Meeting - Testing and Defects | 0.5 | Vignesh dhakshnamoorthy | 2 | AR/AP Dashboard | Completed |  | FIN Reports Phase-1: Completed | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold | [7 empty] | Automation created | 0 | Total automation | 123
[7 empty] | Monitoring data count & performance |  |  |  | Enhance scripts for WD & vEMS allocation variants as needed
vEMS: AR/AP Dashboard | 2 |  |  | WOR-939: SC, BR, COA mapping | In Progress | 2024-02-02 | Test execution - In Progress (Blocked due to issues) | AR/AP Dashboard | In Progress | 2024-02-02 | FIN Reports Phase-1: Merge Prod & Dev in single to make it centralized - ETA-02-Feb | [7 empty] | Automation execution | 29 | Total automation execution | 1095
vEMS: WOR-939 SC, BR, COA mapping | 12.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-02-02 | Will get issues resolved and complete testing | [7 empty] | Bugs Identified | 1 | Total bugs | 49
vEMS: Automation Script Enhancement | 8 | [19 empty] | Automation coverage % | 100%
vEMS: Automation(Multi SR & Power Bi) | 6.5