## 2 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
WD: WD Team Scrum Call | 6 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_272 | No warning or alert displayed if partial reclass initiated again before Geneva accrual response | Low | Open | Vikas |  |  | Manual created | 0 | Total manual | 263
WD: WOR-817, 818 (SINV Adj to use Bank rate) | 5 | Saravanan munikrishnan | 19.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | Observation_273 | Validation error occurred. The Credit and Debit Amounts are both zero. For SINV Fx case SINV-00103856 & SINV-00103858-ADJ | Medium | Closed | Sundeep |  |  | Manual execution | 10 | Total manual execution | 629
WD: WOR-823, 824 (Refund to use Bank rate) | 4.5 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | Observation_274 | Automation- Data creation | Medium | Closed | Sundeep |  |  | Automation created | 0 | Total automation | 262
WD: WOR-512 (Refund Status as paid) | 1.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | Observation_275 | WOR-817 SINV-adj CINV- Bank rate | High | Closed | Sundeep |  |  | Automation execution | 32 | Total automation execution | 858
WD: Ad-Hoc Testing | 16.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs Identified | 4 | Total bugs | 98
WD: AR/AP Dashboard | 2.5 | [19 empty] | Automation coverage % | 99.62%
WD: Automation Script Enhancement | 5
WD: Automation: Multi-SR & Power Bi | 1

## 9 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
WD: WD Team Scrum Call | 6 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_276 | INT-141 did not trigger for SINV/ER | Medium | Closed | Sundeep |  |  | Manual created | 0 | Total manual | 263
WD: WOR-817, 818 (SINV Adj to use Bank rate) | 5 | Saravanan munikrishnan | 19.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Manual execution | 12 | Total manual execution | 641
WD: WOR-823, 824 (Refund to use Bank rate) | 4.5 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation created | 0 | Total automation | 262
WD: WOR-512 (Refund Status as paid) | 1.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation execution | 34 | Total automation execution | 892
WD: Ad-Hoc Testing | 16.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs Identified | 1 | Total bugs | 99
WD: AR/AP Dashboard | 2.5 | [19 empty] | Automation coverage % | 99.62%
WD: Automation Script Enhancement | 5
WD: Automation: Multi-SR & Power Bi | 1

## 16 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
WD: WD Team Scrum Call | 6 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 263
WD: WOR-817, 818 (SINV Adj to use Bank rate) | 5 | Saravanan munikrishnan | 19.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Manual execution | 20 | Total manual execution | 661
WD: WOR-823, 824 (Refund to use Bank rate) | 4.5 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation created | 0 | Total automation | 262
WD: WOR-512 (Refund Status as paid) | 1.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation execution | 46 | Total automation execution | 938
WD: Ad-Hoc Testing | 16.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs Identified | 0 | Total bugs | 99
WD: AR/AP Dashboard | 2.5 | [19 empty] | Automation coverage % | 99.62%
WD: Automation Script Enhancement | 5
WD: Automation: Multi-SR & Power Bi | 1

## 23 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
WD: WD Team Scrum Call | 6 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_277 | SFTP was not configured hence Refund status was not reflected as Paid | Medium | Closed | Sundeep |  |  | Manual created | 0 | Total manual | 263
WD: WOR-817, 818 (SINV Adj to use Bank rate) | 5 | Saravanan munikrishnan | 19.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | Observation_278 | SFTP was not configured hence Refund data did not flow to vEMS | Medium | Closed | Sundeep |  |  | Manual execution | 20 | Total manual execution | 681
WD: WOR-823, 824 (Refund to use Bank rate) | 4.5 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | Observation_279 | INT101D is not processing SINV related data properly. It scheduled to process last 1 hour data instead of 24 hours | Medium | Closed | Devendra |  |  | Automation created | 0 | Total automation | 262
WD: WOR-512 (Refund Status as paid) | 1.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation execution | 46 | Total automation execution | 984
WD: Ad-Hoc Testing | 16.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs Identified | 3 | Total bugs | 102
WD: AR/AP Dashboard | 2.5 | [19 empty] | Automation coverage % | 99.62%
WD: Automation Script Enhancement | 5
WD: Automation: Multi-SR & Power Bi | 1

## 30 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
WD: WD Team Scrum Call | 6 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_280 | SINV Adj with JPY/ KRW failed to do Currency conversion for CINV. | Medium | Closed | Sundeep |  |  | Manual created | 0 | Total manual | 263
WD: WOR-817, 818 (SINV Adj to use Bank rate) | 5 | Saravanan munikrishnan | 19.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Manual execution | 12 | Total manual execution | 693
WD: WOR-823, 824 (Refund to use Bank rate) | 4.5 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation created | 0 | Total automation | 262
WD: WOR-512 (Refund Status as paid) | 1.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation execution | 36 | Total automation execution | 1020
WD: Ad-Hoc Testing | 16.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs Identified | 1 | Total bugs | 103
WD: AR/AP Dashboard | 2.5 | [19 empty] | Automation coverage % | 99.62%
WD: Automation Script Enhancement | 5
WD: Automation: Multi-SR & Power Bi | 1

## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
WD: WD Team Scrum Call | 2.5 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_281 | SINV Adj with GBP failed to do Currency conversion for CINV. | Medium | Closed | Sundeep |  |  | Manual created | 0 | Total manual | 263
WD: WOR-817, 818 (SINV Adj to use Bank rate) | 1 | Saravanan munikrishnan | 6 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Regression Testing will be done, once issue fixed | Observation_282 | INT101D is not processing SINV related data properly. It scheduled to process last 1 hour data instead of 24 hours | Medium | Open | Devendra |  |  | Manual execution | 9 | Total manual execution | 702
WD: WOR-823, 824 (Refund to use Bank rate) | 2 | Vignesh dhakshnamoorthy | 10 | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Requirement got changed, waiting for new changes | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation created | 0 | Total automation | 262
WD: AR/AP Dashboard | 20.5 |  |  | WD-Regression Suite | Blocked | TBD | Phase-5:- Power Bi validation: Blocked due to INT101D issue | WD-Regression Suite | Blocked | TBD | Phase-5- Power Bi: Blocked by INT101D issue | [7 empty] | Automation execution | 24 | Total automation execution | 1044
WD: Automation Script Enhancement | 4 |  |  | AR/AP Dashboard | In Progress | 2023-11-21 | FIN Reports: Worked on Requirement gathering & Access Working on Table design | AR/AP Dashboard | In Progress | 2023-11-21 | FIN Reports: Work on Table design and waiting for Data from vEMS | [7 empty] | Bugs Identified | 2 | Total bugs | 105
WD: Automation: Multi-SR & Power Bi | 6 | [19 empty] | Automation coverage % | 99.62%

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
WD: WD Team Scrum Call | 1 | Pramod rayate | 8 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_283 | INT0207 did not trigger and did not process the ER reconciliation | Medium | Open | Sundeep |  |  | Manual created | 0 | Total manual | 263
WD: WOR-817, 818 (SINV Adj to use Bank rate) | 3 | Saravanan munikrishnan | 8.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Functionality working as expected, Pending to check in FPNA | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Will check FPNA and start Full regression | Observation_284 | Refund status not reflecting as paid | Medium | Closed | Sundeep |  |  | Manual execution | 14 | Total manual execution | 716
WD: WOR-823, 824 (Refund to use Bank rate) | 2.5 | Vignesh dhakshnamoorthy | 17 | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Functionality working as expected, Pending to check in FPNA | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Will check FPNA and start Full regression | Observation_285 | INT0210a and INT0209 getting failed and not processing Fx journal entries to FPNA | Medium | Open | Ramesh |  |  | Automation created | 0 | Total automation | 262
WD: AR/AP Dashboard | 18.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | [7 empty] | Automation execution | 38 | Total automation execution | 1082
WD: Automation Script Enhancement | 4 | [5 empty] | creating fresh data for validation |  |  |  | Prepare data and put more validation | [7 empty] | Bugs Identified | 3 | Total bugs | 108
WD: Automation: Multi-SR & Power Bi | 4.5 |  |  | AR/AP Dashboard | In Progress | 2023-11-24 | FIN Reports: Worked on Requirement gathering & Access | AR/AP Dashboard | In Progress | 2023-11-24 | FIN Reports: Get data & Access for vEMS | [9 empty] | Automation coverage % | 99.62%
[7 empty] | Worked on Table design, able to receive data for Workday |  |  |  | Work on feeding data in dashboard

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
WD: WD Team Scrum Call | 3.5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | 2023-12-05 | started Full regression in OAK-2 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 263
WD: WOR-817, 818 (SINV Adj to use Bank rate) | 2 | Saravanan munikrishnan | 20 | WOR-823, 824: Refund to use Bank Rate | Completed | 2023-11-21 | Functionality working as expected, Issue found in FPNA | WOR-882: Refund to use Bank Rate | In Progress | 2023-12-05 | Continue Full regression in OAK-2 and OAK-1 | [7 empty] | Manual execution | 18 | Total manual execution | 734
WD: WOR-823, 824 (Refund to use Bank rate) | 1 | Vignesh dhakshnamoorthy | 8 | WOR-817, 818: ADJ to use Bank Rate | Completed | 2023-11-21 | Functionality working as expected, Issue found in FPNA | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | [7 empty] | Automation created | 0 | Total automation | 262
WD: WOR-882 (Refund to use Bank rate) | 6 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress |  |  |  | Prepare data and put more validation | [7 empty] | Automation execution | 22 | Total automation execution | 1104
WD: AR/AP Dashboard | 13 | [5 empty] | creating fresh data for validation | AR/AP Dashboard | In Progress | 2023-12-01 | FIN Reports: Get data & Access for vEMS | [7 empty] | Bugs Identified | 0 | Total bugs | 108
WD: Automation Script Enhancement | 9 |  |  | AR/AP Dashboard | In Progress | 2023-12-01 | FIN Reports: Worked on Requirement gathering & Access |  |  |  | Waiting for data from vEMS & Navision | [9 empty] | Automation coverage % | 99.62%
WD: Automation: Multi-SR & Power Bi | 13.5 | [5 empty] | Table design completed, waiting for vEMS & Navision

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
WD: WD Team Scrum Call | 5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | 2023-12-05 | started Full regression in OAK-2, Faced issue in INT0209 & INT0210a | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_286 | SINV lines count populated as Zero in file | High | Closed | Sundeep |  |  | Manual created | 0 | Total manual | 263
WD: WOR-823, 824 (Refund to use Bank rate) | 1.5 | Saravanan munikrishnan | 20 | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress. created fresh data for validation | WOR-882: Refund to use Bank Rate | Blocked | TBD | Waiting for fix on issue with INT0209 & INT0210a | Observation_287 | All count files in FTP location was not in Sync as per date. Integration was failing to post files in FTP location | Medium | Closed | Sundeep |  |  | Manual execution | 4 | Total manual execution | 738
WD: WOR-882 (Refund to use Bank rate) | 4 | Vignesh dhakshnamoorthy | 8 | AR/AP Dashboard | In Progress | 2023-12-05 | FIN Reports Phase-1: Ready to consume Prod data | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress created fresh data for validation | [7 empty] | Automation created | 0 | Total automation | 262
WD: AR/AP Dashboard | 13 | [6 empty] | AR/AP Dashboard | In Progress | 2023-12-05 | FIN Reports Phase-1: Ready to consume Prod data | [7 empty] | Automation execution | 20 | Total automation execution | 1124
WD: Automation Script Enhancement | 9 | [17 empty] | Bugs Identified | 2 | Total bugs | 110
WD: Automation: Multi-SR & Power Bi | 15.5 | [19 empty] | Automation coverage % | 99.62%
vEMS: Automation(Multi SR & Power Bi) | 22

## 4 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
WD: WD Team Scrum Call | 2.5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | TBD | Found issue in INT0209 & INT0210a, waiting for fix | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual created | 12 | Total manual | 275
WD: Ad-hoc business requests | 2.5 | Saravanan munikrishnan | 2.5 | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress Preparing additional validation list | WOR-882: Refund to use Bank Rate | Blocked | TBD | Found issue in INT0209 & INT0210a, waiting for fix | [7 empty] | Manual execution | 5 | Total manual execution | 743
WD: WOR-882 (Refund to use Bank rate) | 3.5 | Vignesh dhakshnamoorthy | 5 | AR/AP Dashboard | In Progress | 2023-12-11 | FIN Reports Phase-1: Ready to consume Prod data | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress Preparing additional validation list | [7 empty] | Automation created | 6 | Total automation | 268
WD: AR/AP Dashboard | 12.5 | [6 empty] | AR/AP Dashboard | In Progress | 2023-12-11 | FIN Reports Phase-1: Ready to consume Prod data. will work on vEMS data at FTP | [7 empty] | Automation execution | 45 | Total automation execution | 1169
WD: Automation: Multi-SR & Power Bi | 6.5 | [17 empty] | Bugs Identified | 0 | Total bugs | 110
[21 empty] | Automation coverage % | 97.5%

## 11 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
WD: WD Team Scrum Call | 5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | TBD | Found issue in INT0209 & INT0210a, waiting for fix | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_291 | INT0209 delay time for BP integration trigger is very high, need to reduce to 5 sec or less | High | Open | Ramesh |  |  | Manual created | 13 | Total manual | 288
WD: Ad-hoc business requests | 3 | Saravanan munikrishnan | 17 | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress Preparing additional validation list | WOR-882: Refund to use Bank Rate | Blocked | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | [7 empty] | Manual execution | 3 | Total manual execution | 746
WD: WOR-882 (Refund to use Bank rate) | 1.5 | Vignesh dhakshnamoorthy | 5 | AR/AP Dashboard | In Progress | 2023-12-18 | FIN Reports Phase-1: Completed Analyzed schedule time to run scripts for WD & vEMS | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress Review additional validation list with William | [7 empty] | Automation created | 10 | Total automation | 278
WD: AR/AP Dashboard | 13 | [6 empty] | AR/AP Dashboard | In Progress | 2023-12-19 | FIN Reports Phase-1: will work on vEMS data at FTP & Set up the schedule run at right time | [7 empty] | Automation execution | 58 | Total automation execution | 1227
WD: Automation Script Enhancement | 7 | [17 empty] | Bugs Identified | 1 | Total bugs | 111
WD: Automation: Multi-SR & Power Bi | 12.5 | [19 empty] | Automation coverage % | 96.5%

## 18 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
WD: WD Team Scrum Call | 6 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | TBD | worked on WOR-927 with Ramesh, issue not yet resolved | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_292 | Approval by Cash Manager is missing in latest Settlement Run flow | Medium | Open | Ramesh |  |  | Manual created | 0 | Total manual | 288
WD: Ad-hoc business requests | 2 | Saravanan munikrishnan | 17.5 | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Adding scripts for vEMS allocation variants | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | Observation_293 | Settlement Run for SINV payment is taking more than usual time | High | Open | Ramesh |  |  | Manual execution | 4 | Total manual execution | 750
WD: WOR-927 (Fix INT0209) | 1.5 | Vignesh dhakshnamoorthy | 7.5 | AR/AP Dashboard | In Progress | 2023-12-19 | FIN Reports Phase-1: Completed | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Adding scripts for vEMS allocation variants | Observation_294 | ER Header & Line Count mis-matches with Finsmart count by only 1 record | Low | Open | Sundeep |  |  | Automation created | 5 | Total automation | 283
WD: AR/AP Dashboard | 11.5 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Initial analysis done on Test scripts from Business side and Environment readiness | AR/AP Dashboard | In Progress | 2023-12-29 | FIN Reports Phase-1: will work on vEMS data at FTP & Set up the schedule run at right time | [7 empty] | Automation execution | 25 | Total automation execution | 1252
WD: WOR-939 SC, BR, COA mapping | 4.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | TBD | Work on keeping the test Pre-requisites ready | [7 empty] | Bugs Identified | 3 | Total bugs | 114
WD: Automation Script Enhancement | 11 | [19 empty] | Automation coverage % | 98.3%
WD: Automation: Multi-SR & Power Bi | 8.5

## 26 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
WD: WD Team Scrum Call | 4 | Pramod rayate | 12 | WOR-882: Refund to use Bank Rate | In Progress | TBD | worked on WOR-927 with Ramesh, issue not yet resolved | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 288
WD: WOR-927 (Fix INT0209) | 3 | Saravanan munikrishnan | 9 | WD-Regression Suite | In Progress | TBD | Phase-5:- Added scripts for vEMS allocation variations | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | [7 empty] | Manual execution | 4 | Total manual execution | 754
WD: AR/AP Dashboard | 5.5 | Vignesh dhakshnamoorthy | 4 | AR/AP Dashboard | Completed | 2024-12-29 | FIN Reports Phase-1: Completed | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Will verify scripts for WD & vEMS allocation variants | [7 empty] | Automation created | 4 | Total automation | 287
WD: WOR-939 SC, BR, COA mapping | 4 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Prepared and checked feasibility of the business scenarios in OAK-2 | AR/AP Dashboard | In Progress | 2024-01-04 | FIN Reports Phase-1: will work on vEMS data at FTP & Set up the schedule run at right time | [7 empty] | Automation execution | 20 | Total automation execution | 1272
WD: Automation Script Enhancement | 8.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-15 | Work on keeping the test Pre-requisites ready and kick off once we final review completed | [7 empty] | Bugs Identified | 0 | Total bugs | 114
[21 empty] | Automation coverage % | 99.7%

## 2 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
WD: WD Team Scrum Call | 2.5 | Pramod rayate | 16 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_295 | Ledger period for year 2024 not opened which blocks SINV/ER flow | Low | Closed | Anand |  |  | Manual created | 0 | Total manual | 288
WD: WOR-927 (Fix INT0209) | 1 | Saravanan munikrishnan | 18 | WD-Regression Suite | In Progress | TBD | Phase-5:- Added scripts for WOR-939 having WD & vEMS allocation variations | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | Observation_296 | INT0503 for accounting adjustment is not processing file for InterCo cases | Low | Open | Sundeep |  |  | Manual execution | 3 | Total manual execution | 757
WD: AR/AP Dashboard | 5 | Vignesh dhakshnamoorthy | 4 | AR/AP Dashboard | Completed | 2024-01-02 | FIN Reports Phase-1: Completed. Monitoring data count & performance | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Will enhance scripts for WD & vEMS allocation variants | Observation_297 | CINV & CPAY Count mis-matches with Finsmart count across week | Medium | Open | Sundeep |  |  | Automation created | 0 | Total automation | 287
WD: WOR-939 SC, BR, COA mapping | 9.5 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Discussed & Reviewed the business scenarios in OAK-2 | AR/AP Dashboard | In Progress | TBD | FIN Reports Phase-1: will work on vEMS data at FTP & Set up the schedule run at right time | [7 empty] | Automation execution | 24 | Total automation execution | 1296
WD: Automation Script Enhancement | 9 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-15 | Work on keeping the test Pre-requisites ready and kick off once we final review completed | [7 empty] | Bugs Identified | 3 | Total bugs | 117
WD: Enhancement for SC & COA changes in SINV and ER | 11 | [19 empty] | Automation coverage % | 99.7%

## 8 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
WD: WD Team Scrum Call | 2.5 | Pramod rayate | 30 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_299 | Given data was not available in OAK-2 | Medium | Open | Anand |  |  | Manual created | 0 | Total manual | 288
WD: AR/AP Dashboard | 5 | Saravanan munikrishnan | 27 | WD-Regression Suite | In Progress | TBD | Phase-5:- Added scripts for WOR-939 having WD & vEMS allocation variations- Checked & verified | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | Observation_300 | SC, EAP & BR combination issue at Workday | Medium | Open | Anand |  |  | Manual execution | 0 | Total manual execution | 757
WD: WOR-939 SC, BR, COA mapping | 33.5 | Vignesh dhakshnamoorthy | 4 | AR/AP Dashboard | Completed |  | FIN Reports Phase-1: Completed Monitoring data count & performance | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Enhance scripts for WD & vEMS allocation variants as needed | Observation_301 | Spend Category not found in OAK-2 | Medium | Open | Anand |  |  | Automation created | 0 | Total automation | 287
WD: Automation Script Enhancement | 4.5 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Test execution - In Progress (Blocked due to issue) | AR/AP Dashboard | In Progress | TBD | FIN Reports Phase-1: Merge Prod & Dev in single to make it centralized | Observation_304 | INT141 Issue-Paid status not reflected at vEMS | High | Open | Sundeep |  |  | Automation execution | 76 | Total automation execution | 1372
WD: Enhancement for SC & COA changes in SINV and ER | 15.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-19 | Will get issues resolved and complete testing | Observation_305 | Woakday BP approval process has some issue as approver list is in-accurate and never ending | High | Open | Anand |  |  | Bugs Identified | 5 | Total bugs | 117
| 11 | [19 empty] | Automation coverage % | 99.7%