## 2 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Beqom standup calls | 2 | Hrushikesh | 31 | 1.HICA-2612-Regression for Multiyear report | Completed |  |  | 1.HICA-2663-Workflow additional data report testing | In progress | 2023-10-11 |  |  | No defect logged for the week | [5 empty] | Manual created | 3 | Total manual | 288
Defects Retest(HICA-2594,2282) | 14 |  |  | 2.Defect fixes-(2594,2282) | Completed |  |  | 2.Budget widget validation | Yet to start | [9 empty] | Manual execution | 3 | Total manual execution | 337
HICA-2612-Regression for multiyear Report | 14 | [17 empty] | Automation created | 0 | Total automation | 0
Sprint sizing | 0.5 | [17 empty] | Automation execution | 0 | Total automation execution | 0
WSR | 0.5 | [17 empty] | Bugs Identified | 0 | Total bugs | 118
[21 empty] | Automation coverage % | 0

## 9 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Beqom standup calls | 1.5 | Hrushikesh | 37 | 1.HICA-2663-Workflow additional data report testing | Completed |  |  | 1.HICA-2726-Budget widget validation | In progress | 2023-10-16 |  | HICA-2473 | Audit Report: Department and sub department filters are not showing the correct results | Medium | Done | Lauren |  |  | Manual created | 3 | Total manual | 291
Retesting the bugs/Enhancement tickets | 8.5 |  |  | 2.HICA-2726-Budget widget validation | In progress |  |  | 2.HICA-2731-Enhancements for Individual and multi reports | Yet to start | 2023-10-17 | [8 empty] | Manual execution | 3 | Total manual execution | 340
Call with Lauren on Enhancement tickets | 1 | [6 empty] | 3.HICA-2687-Footnotes issue on Ind and multiyear report | Yet to start | [9 empty] | Automation created | 0 | Total automation | 0
Edit worker report validation | 24.5 | [17 empty] | Automation execution | 0 | Total automation execution | 0
Sprint planning | 1 | [17 empty] | Bugs Identified | 1 | Total bugs | 119
WSR | 0.5 | [19 empty] | Automation coverage % | 0

## 16 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Beqom standup calls | 2.5 | Hrushikesh | 40 | 1.HICA-2726-Budget widget validation | Completed |  |  | 1.Regression testing in progress for the issues listed by Lauren | In progress | 2023-10-25 |  | HICA-2448 | Audit Report: when we make changes Promo (Y/N) and promotion title fields for an employee, changes are not reflected in the audit report | Medium | Done | Lauren |  |  | Manual created | 5 | Total manual | 296
Retesting the bugs/Enhancement tickets | 15.5 |  |  | 2.HICA-2731-Enhancements for Individual and multi reports | Completed |  |  | 2.Sprint Retrospective &backlog refinement | Yet to attend | [9 empty] | Manual execution | 5 | Total manual execution | 345
Call with Lauren on Enhancement tickets | 0.5 |  |  | 3.HICA-2687-Footnotes issue on Ind and multiyear report | Completed |  |  | 3.Sprint planning session | Yet to attend | [9 empty] | Automation created | 0 | Total automation | 0
HICA-2726-Budget widget validation | 20.5 |  |  | 4. Regression testing in progress for the issues listed by Lauren | In Progress | [13 empty] | Automation execution | 0 | Total automation execution | 0
Sprint planning | 0.5 | [17 empty] | Bugs Identified | 1 | Total bugs | 120
WSR | 0.5 | [19 empty] | Automation coverage % | 0

## 23 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Beqom standup calls | 1 | Hrushikesh | 22 | 1. Regression testing for the issues listed by Lauren. | Completed |  |  | 1.HICA-2815-Point payment logic update | Yet to start | 2023-10-31 |  | HICA-2443 | Audit Report: Decimal values are displayed as 0,.00 instead of 0.00 if the value is zero for previous and new value fields | Medium | Done | Lauren |  |  | Manual created | 7 | Total manual | 303
Regression scenarios testing | 18 |  |  | 2.Regression scenarios verification for multiyear report | Completed |  |  | 2.Sprint sizing session | Yet to attend |  |  | HICA-2434 | Audit Report : Audit Report was not visible for comp admin, hrbp admin, manager roles | Medium | Done | Lauren |  |  | Manual execution | 7 | Total manual execution | 352
Call with Lauren on Enhancement tickets | 2 |  |  | 3.Sprint Retrospective session | Completed |  |  | 3.Regression for the new enhancements for multiyear report | Yet to start | [9 empty] | Automation created | 0 | Total automation | 0
Sprint planning | 0.5 | [17 empty] | Automation execution | 0 | Total automation execution | 0
WSR | 0.5 | [17 empty] | Bugs Identified | 2 | Total bugs | 122
[21 empty] | Automation coverage % | 0

## 30 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Beqom standup calls | 2.5 | Hrushikesh | 40 | 1.HICA-2815-point payments update | Completed |  |  | 1.Sprint Retrospective session | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 15 | Total manual | 318
HICA-2815 testing | 18.5 |  |  | 2.Regression for new enhancements | Completed |  |  | 2.Sprint sizing session | Yet to attend | [9 empty] | Manual execution | 15 | Total manual execution | 367
Regression scenarios testing | 18 |  |  | 3.Sprint panning session | Completed | [13 empty] | Automation created | 0 | Total automation | 0
Sprint planning | 0.5 | [17 empty] | Automation execution | 0 | Total automation execution | 0
WSR | 0.5 | [17 empty] | Bugs Identified | 0 | Total bugs | 122
[21 empty] | Automation coverage % | 0

## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Beqom standup calls | 2 | Hrushikesh | 3.5 | 1.There are no testing items planned for the sprint | NA |  |  | 1.HICA-2962-Prod support enhancements | Yet to start |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 318
Sprint planning | 1 |  |  | 2.Sprint Retrospective session | Completed | [13 empty] | Manual execution | 0 | Total manual execution | 367
WSR | 0.5 |  |  | 3.Sprint planning session | Completed | [13 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 122
[21 empty] | Automation coverage % | 0

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Beqom standup calls | 2 | Hrushikesh | 16 | 1.HICA-2962-Special allocations, FX issue fix | In Progress |  |  | 1.HICA-2962- Special allocations, FX issue fix | In Progress | 2023-11-21 |  | HICA-2962 | Special allocation issue | Medium | Done | Lauren |  |  | Manual created | 3 | Total manual | 321
Sprint sizing session | 0.5 |  |  | 2.Sizing session | Completed |  |  | 2.HICA-3023-Walkme implementation testing | Yet to start | [9 empty] | Manual execution | 3 | Total manual execution | 370
HICA-2962 testing | 13 | [6 empty] | 3.Sprint retrospective &planning session | Yet to attend | [9 empty] | Automation created | 0 | Total automation | 0
WSR | 0.5 | [17 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 1 | Total bugs | 123
[21 empty] | Automation coverage % | 0

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Beqom standup calls | 1.5 | Hrushikesh | 32 | 1.HICA-2962-Special allocations, FX issue fix | Completed |  |  | 1.HICA-3048-FX rates testing | In Progress | 2023-11-28 |  | HICA-3048 | Fx rates conversion issue | Medium | Done | Lauren |  |  | Manual created | 17 | Total manual | 338
Sprint planning session | 1 |  |  | 2.HICA-3048-FX rates testing | In Progress |  |  | 2.Sprint sizing session | Yet to attend |  |  | HICA-3026 | Budget widget loading issue | Medium | Done | Lauren |  |  | Manual execution | 17 | Total manual execution | 387
HICA-2962 testing | 15.5 |  |  | 3.HICA-3026-Budget widget testing | On Hold |  | Waiting for the fix | [11 empty] | Automation created | 0 | Total automation | 0
HICA-3026-testing | 13 |  |  | 4.Sprint retrospective session | Completed | [13 empty] | Automation execution | 0 | Total automation execution | 0
Connect with Lauren on the FX issue | 0.5 | [17 empty] | Bugs Identified | 2 | Total bugs | 125
WSR | 0.5 | [19 empty] | Automation coverage % | 0

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Attended Stand up call | 2.5 | Hrushikesh | 30 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 7 | Total manual | 345
Attended Sizing and refinement meeting | 0.5 |  |  | Attended Sizing and Backlog Refinement meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 7 | Total manual execution | 394
HICA-3026 Execution | 15 |  |  | Attended Sprint planning meeting | Completed | [13 empty] | Automation created | 0 | Total automation | 0
HICA-3048 Execution | 12 |  |  | HICA-3026: Test Scenario Execution | Completed | [13 empty] | Automation execution | 0 | Total automation execution | 0
|  |  |  | HICA-3048: Test Scenario Execution | Completed | [13 empty] | Bugs Identified | 0 | Total bugs | 125
[21 empty] | Automation coverage % | 0

## 4 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Attended Stand up call | 1.5 | Hrushikesh | 32 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 6 | Total manual | 351
Attended Sprint Review and Restrospective meeting | 2 |  |  | Attended Sprint Review & Retrospective meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 6 | Total manual execution | 400
Atteneded Sprint planning | 1 |  |  | Attended Sprint planning meeting | Completed |  |  | HICA-3131 Test cases Execution | Inprogress | 2023-12-13 | [8 empty] | Automation created | 0 | Total automation | 0
HICA-3133 Test Scenarios Execution | 15 |  |  | HICA-3024: Test Scenario Execution | Completed | [13 empty] | Automation execution | 0 | Total automation execution | 0
HICA-3024 Test Scenarios Executio | 12.5 |  |  | HICA-3133: Test Scenario Execution | Completed | [13 empty] | Bugs Identified | 0 | Total bugs | 125
[21 empty] | Automation coverage % | 0

## 11 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Attended Stand up call | 1.5 | Hrushikesh | 32 | Attended Stand up call | Completed |  |  | HICA-2691 Test cases Execution | In Progress | 2023-12-18 |  |  | No defect logged for the week | [5 empty] | Manual created | 2 | Total manual | 353
Attended Sizing and backlog Refinement | 1 |  |  | Attended Sizing and backlog Refinement | Completed |  |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend | [9 empty] | Manual execution | 2 | Total manual execution | 402
HICA-3131 Test Scenarios Execution | 15 |  |  | HICA-3131 Test Scenarios Execution | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Automation created | 0 | Total automation | 0
HICA-3134 Test Scenarios Execution | 6.5 |  |  | HICA-3134 Test Scenarios Execution | Completed | [13 empty] | Automation execution | 0 | Total automation execution | 0
HICA-2691 Test Scenarios Execution | 8 |  |  | HICA-2691 Test Scenarios Execution | Completed | [13 empty] | Bugs Identified | 0 | Total bugs | 125
[21 empty] | Automation coverage % | 0

## 18 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
HICA-2691 Execution | 8 | Hrushikesh | 8 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 1 | Total manual | 354
|  |  |  | Attended Sprint Review and Retrospective meeting |  |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 1 | Total manual execution | 403
|  |  |  | Attended Sprint Planning meeting | Completed | [13 empty] | Automation created | 0 | Total automation | 0
|  |  |  | HICA-2691: Test Scenario Preparation | Completed | [13 empty] | Automation execution | 0 | Total automation execution | 0
|  |  |  | HICA-2691: Test Scenario Execution | Completed | [13 empty] | Bugs Identified | 0 | Total bugs | 125
[21 empty] | Automation coverage % | 0

## 26 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Attended Stand up call | 1.5 | Hrushikesh | 2 | Attended Daily Standup calls | Completed |  |  | Attend Sprint review and retrospective meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 354
Attended Sizing and Backlog refinement meeting | 0.5 |  |  | Sizing and Backlog refinement | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 403
[19 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 125
[21 empty] | Automation coverage % | 0

## 2 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Attended Daily Standup calls | 1 | Hrushikesh | 4 | Attended Daily Standup calls | Completed |  |  | Attend Sizing and backlog refinement | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 354
Sprint Review & Retrospective meeting | 2 |  |  | Sprint Review & Retrospective meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 403
Sprint planning meeting | 1 |  |  | Sprint planning meeting | Completed | [13 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 125
[21 empty] | Automation coverage % | 0

## 8 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Attended Daily Standup calls | 2 | Hrushikesh | 3 | Attended Daily Standup calls | Completed |  |  | Attend Sizing and backlog refinement | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 354
Sizing and Backlog Refinement | 1 |  |  | Sizing and Backlog Refinement meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 403
[19 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 125
[21 empty] | Automation coverage % | 0