## 6 Nov 2023 (hidden)
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
Adhoc Testing | 10 | Johnson Benjamin | 32 | Regression Testing | In Progress | 2023-04-21 |  | Test case update (Select Approved Payment Instruction Template to Create New Payment Request section) | In Progress | 2023-04-21 |  | Hom page Keeps loading | Low | Open | Garg Nikhil |  | To be Tested once fixed by Dev | Total Manual Execution | 108
New Module Testing | 12 | Kathhir | 22 | Select Approved Payment Instruction Template to Create New Payment Request section | Completed |  |  | Regression Testing | In Progress | 2023-04-21 |  | Space Required | Low | Closed | Garg Nikhil |  |  | Total Automation Execution | 296
Regression Testing | 25 | Vignesh | 15 | 6 Test Scenarios provided by LIPI related to regression | Completed |  |  | Bug Retesting | In Progress |  |  | User able to submit payment req. although user doesn’t have requestor role | High | Closed | Garg Nikhil |  |  | Bugs Identified | 17
Bug Retesting | 22 |  |  | DEV bugs / changes Retesting | Completed |  | 4 new changes given by DEV team | Approve Payment Request section | Yet to Start |  | Development In Progress | Added Rush Request Comments showing error | High | Closed | Garg Nikhil |  |  | Total Bugs | 180
|  |  |  | Bug Created | In Progress |  | Total 11 Resolved 8 Open 3 |  |  |  |  | Amount – Not Support Decimal | High | Closed | Garg Nikhil |  |  | Manual Test Created | 8
[12 empty] | Error Message not Displayed | High | Closed | Garg Nikhil |  |  | Total Manual Case | 116
[12 empty] | Template Not visible in Edit Existing Grid | Medium | Closed | Garg Nikhil |  |  | Automation Scripts Created | 10
[12 empty] | Template Not Visible in Approval Panel But Visible in Track/Edit Grid | High | Open | Garg Nikhil |  | To be Tested once fixed by Dev | Total Automation Scripts | 306
[12 empty] | Delete Button in Edit Existing Payment | Medium | Closed | Garg Nikhil
[12 empty] | Particular BIC value is not accepted | Medium | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Discard Status should be removed | Medium | Closed | Garg Nikhil
[12 empty] | Application takes more time to load during login | Low | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Optimization - On Click of Submit in Create Template | Low | Open | Mukherjee Trishit |  | To be Tested once fixed by Dev
[12 empty] | Sometimes we get a message when we login after the application is timed out | Low | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Performance Issue in File Upload | Low | Open | Mukherjee Trishit |  | To be Tested once fixed by Dev
[12 empty] | Existing Attachment should be loaded when an Approved Template is edited | Medium | Open | Garg Nikhil |  | To be Tested once fixed by Dev
[12 empty] | Error message is displayed when Template is Saved from Draft | Medium | Open | Garg Nikhil |  | To be Tested once fixed by Dev

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Connect with Shantanu for KT | 5 | Hrushikesh | 34.5 | 1.HRIS Knowledge transfer | In Progress | 2023-11-17 |  | 1.HRIS knowledge transfer | In Progress | 2023-11-17 |  |  | No defects have been logged for the week | [5 empty] | Manual created | 0 | Total manual | 6
SQL Training/Learning | 29 |  |  | 2.Sprint Retrospective session | Completed | [13 empty] | Manual execution | 0 | Total manual execution | 6
WSR | 0.5 |  |  | 3.Sprint planning session | Completed | [13 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Connect with Shantanu for KT | 2 | Hrushikesh | 16 | 1.HRIS Knowledge transfer | In Progress |  |  | 1.HRIS knowledge transfer | In Progress | 2023-11-24 |  |  | No defects have been logged for the week. | [5 empty] | Manual created | 0 | Total manual | 6
SQL Training/Learning | 13.5 |  |  | 2.Sprint sizing session | Completed |  |  | 2.SQL trainings &learning activity | In Progress | 2023-11-24 | [8 empty] | Manual execution | 0 | Total manual execution | 6
WSR | 0.5 | [6 empty] | 3.Sprint retrospective &planning sessions | Yet to attend | [9 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Connect with Shantanu for KT | 1 | Hrushikesh | 8 | 1.HRIS Knowledge transfer | In Progress | 2023-12-08 |  | 1.HRIS knowledge transfer | In Progress | 2023-12-01 |  |  | No defects have been logged for the week. | [5 empty] | Manual created | 0 | Total manual | 6
SQL Training/Learning | 6.5 | [6 empty] | 2.SQL trainings &learning activity | In Progress | 2023-12-01 | [8 empty] | Manual execution | 0 | Total manual execution | 6
WSR | 0.5 | [6 empty] | 3.Sprint sizing sessions | Yet to attend | [9 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 4 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
SQL learning | 10 | Hrushikesh | 10 | SQL learning | In progress |  |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend |  |  |  | No defects have been logged for the week. | [5 empty] | Manual created | 0 | Total manual | 6
[8 empty] | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 6
[19 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 11 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
SQL learning | 8 | Hrushikesh | 8 | 1.HRIS Knowledge transfer | In Progress |  |  | 1.HRIS knowledge transfer | In Progress |  |  |  | No defects have been logged for the week. | [5 empty] | Manual created | 0 | Total manual | 6
|  |  |  | 2.SQL trainings & learnings | In Progress |  |  | 2.SQL trainings &learning activity | In Progress | [9 empty] | Manual execution | 0 | Total manual execution | 6
|  |  |  | 3.Sprint retrospective & planning sessions | Completed |  |  | 3.Sprint sizing sessions | Yet to attend | [9 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 18 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
SQL learning | 8 | Hrushikesh | 8 | 1.HRIS Knowledge transfer | In Progress |  |  | 1.HRIS knowledge transfer | In Progress |  |  |  | No defects have been logged for the week. | [5 empty] | Manual created | 0 | Total manual | 6
|  |  |  | 2.SQL trainings & learnings | In Progress |  |  | 2.SQL trainings &learning activity | In Progress | [9 empty] | Manual execution | 0 | Total manual execution | 6
|  |  |  | 3.Sprint retrospective & planning sessions | Completed |  |  | 3.Sprint sizing sessions | Yet to attend | [9 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 26 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
HICA-2933 (KT) | 24 | Hrushikesh | 24 | HICA-2933 (KT) | In progress |  |  | 1.HICA-2933 (KT) | In Progress |  |  |  | No defects have been logged for the week. | [5 empty] | Manual created | 0 | Total manual | 6
[8 empty] | 2.SQL trainings &learning activity | In Progress | [9 empty] | Manual execution | 0 | Total manual execution | 6
[8 empty] | 3.Sprint sizing sessions | Yet to attend | [9 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 2 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
SQL learning | 11 | Hrushikesh | 22 | HICA-2933 (KT) | Inprogress | 2024-01-18 |  | Attend Sprint review and retrospective meeting | Yet to attend |  |  |  | No defects have been logged for the week. | [5 empty] | Manual created | 0 | Total manual | 6
HICA-2933 (KT training) | 11 | [6 empty] | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 6
[19 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 8 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
HICA-2933 (KT) | 25 | Hrushikesh | 25 | Attended Daily Standup calls | Completed |  |  | Attend Sizing and backlog refinement | Yet to attend |  |  |  | No defects have been logged for the week. | [5 empty] | Manual created | 0 | Total manual | 6
|  |  |  | Sprint Review & Retrospective meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 6
|  |  |  | Sprint planning meeting | Completed | [13 empty] | Automation created | 0 | Total automation | 0
|  |  |  | HICA-2933 (KT) | Inprogress | 2024-01-18 | [12 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0