## 8 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
1.Standup /Internal/Dev calls | 5 | Eswara Rao | 19 | WMT-1691 | Completed |  |  | 1.Waiting for Multi-Silo Traders wall classification addition for testing in OASQA | Yet to start |  |  |  | No defect logged for the week | [5 empty] | Manual created | 715 | Total manual | 858
2. Test execution | 41 | Samikruth | 19 | WMT-2846 | Completed |  |  | 2.Production support for SDLC 26972,26763 | Yet to start | [9 empty] | Manual execution | 715 | Total manual execution | 969
|  | Kalyan Gopi | 8 | WMT-2738 | Completed | [13 empty] | Automation created | 0 | Total automation | 0
|  |  |  | SDLC 26972,26763 | Completed | [13 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 24
[21 empty] | Automation coverage % | 0