## 2 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Testcase preparation | 4 | Elakkiya | 1 | Test case preparation for Create Shell Legal entity screen | In progress | 2024-10-01 |  | Test case preparation for Create Shell Legal entity screen | In progress | 2024-10-01 |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 50 | Manual test cases created | 50
Meetings | 4 | Meenakshi | 1.5 | Test case preparation for To Maintain Sheel Legal Entity screen | In progress | 2024-10-01 |  | Test case preparation for To Maintain Sheel Legal Entity screen | In progress | 2024-10-01 | [8 empty] | Manual test cases conducted | 0 | Manual test cases conducted | 0
Review the testcase | 0.5 | Kalyan Gopi | 5 | Test case preparation for Create Legal Entity Relationship- Internal Entity screen | In progress | 2024-10-01 |  | Test case preparation for Create Legal Entity Relationship- Internal Entity screen | In progress | 2024-10-01 | [8 empty] | Automation test cases created | 0 | Automation test cases created | 0
|  | Vignesh | 1 | Test case preparation for Create Legal Entity Relationship- External Entity screen | In progress | 2024-10-01 |  | Test case preparation for Create Legal Entity Relationship- External Entity screen | In progress | 2024-10-01 | [8 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
|  |  |  | Test case preparation for View Legal Entities Relationships List screen | In progress | 2024-10-01 |  | Test case preparation for View Legal Entities Relationships List screen | In progress | 2024-10-01 | [8 empty] | Bugs identified | 0 | Bugs identified | 0
|  |  |  | Test case preparation for View Legal Entities List screen | In progress | 2024-10-01 |  | Test case preparation for View Legal Entities List screen | In progress | 2024-10-01 | [10 empty] | Automation coverage | 0
|  |  |  | Test case preparation for View Legal Entities List (v.2) screen | In progress | 2024-10-01 |  | Test case preparation for View Legal Entities List (v.2) screen | In progress | 2024-10-01
|  |  |  | Test case preparation for View Fund Product Assignment List screen | In progress | 2024-10-01 |  | Test case preparation for View Fund Product Assignment List screen | In progress | 2024-10-01
[8 empty] | Test case review | In progress | 2024-10-01

## 8 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Testcase preparation | 4 | Elakkiya | 1 | Test case preparation for Create Shell Legal entity screen | Completed |  |  | Have to pick up the next task | Yet to start |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 6 | Manual test cases created | 56
Meetings | 4 | Meenakshi | 3 | Test case preparation for To Maintain Shell Legal Entity screen | Completed | [13 empty] | Manual test cases conducted | 0 | Manual test cases conducted | 0
Testcase review | 2 | Kalyan Gopi | 5 | Test case preparation for Create Legal Entity Relationship- Internal Entity screen | Completed | [13 empty] | Automation test cases created | 0 | Automation test cases created | 0
|  | Vignesh | 1 | Test case preparation for Create Legal Entity Relationship- External Entity screen | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[19 empty] | Bugs identified | 0 | Bugs identified | 0
[21 empty] | Automation coverage | 0