## 8 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
1.Standup /Internal/Dev calls | 5 | Eswara Rao | 19 | WMT-1691 | Completed |  |  | 1.Waiting for Multi-Silo Traders wall classification addition for testing in OASQA | Yet to start |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 715 | Manual test cases created | 858
2. Test execution | 41 | Samikruth | 19 | WMT-2846 | Completed |  |  | 2.Production support for SDLC 26972,26763 | Yet to start | [9 empty] | Manual test cases conducted | 715 | Manual test cases conducted | 969
|  | Kalyan Gopi | 8 | WMT-2738 | Completed | [13 empty] | Automation test cases created | 0 | Automation test cases created | 0
|  |  |  | SDLC 26972,26763 | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[19 empty] | Bugs identified | 0 | Bugs identified | 24
[21 empty] | Automation coverage | 0

## 15 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
1.Standup /Internal/Dev calls | 4 | Eswara Rao | 18 | 1. PIW OAS Testing:-WMT-2738 | Completed |  |  | No Planned activities for PIW and PIW OAS |  |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 45 | Manual test cases created | 903
2. Test execution of WNT-2738,PIW Performance SDLC#26763 & 26976 production support | 26 | Samikruth | 12 | 2. PIW Performancereports Testing:-Production support for SDLC#26763 & 26976 | Completed | [13 empty] | Manual test cases conducted | 635 | Manual test cases conducted | 1604
[19 empty] | Automation test cases created | 0 | Automation test cases created | 0
[19 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[19 empty] | Bugs identified | 0 | Bugs identified | 24
[21 empty] | Automation coverage | 0