## 2 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count.. | Backup | Till2023
WD: WD Team Scrum Call | 6 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_272 | No warning or alert displayed if partial reclass initiated again before Geneva accrual response | Low | Open | Vikas |  |  | Manual test cases created | 0 | Manual test cases created | 263 | 263
WD: WOR-817, 818 (SINV Adj to use Bank rate) | 5 | Saravanan munikrishnan | 19.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | Observation_273 | Validation error occurred. The Credit and Debit Amounts are both zero. For SINV Fx case SINV-00103856 & SINV-00103858-ADJ | Medium | Closed | Sundeep |  |  | Manual test cases conducted | 10 | Manual test cases conducted | 2114 | 629 | 1485
WD: WOR-823, 824 (Refund to use Bank rate) | 4.5 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | Observation_274 | Automation- Data creation | Medium | Closed | Sundeep |  |  | Automation test cases created | 0 | Automation test cases created | 262 | 262
WD: WOR-512 (Refund Status as paid) | 1.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | Observation_275 | WOR-817 SINV-adj CINV- Bank rate | High | Closed | Sundeep |  |  | Automation test cases processed | 32 | Automation test cases processed | 8904 | 858 | 8046
WD: Ad-Hoc Testing | 16.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs identified | 4 | Bugs identified | 205 | 98 | 107
WD: AR/AP Dashboard | 2.5 | [19 empty] | Automation coverage | 99.62% | 99.62%
WD: Automation Script Enhancement | 5
WD: Automation: Multi-SR & Power Bi | 1

## 9 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 6 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_276 | INT-141 did not trigger for SINV/ER | Medium | Closed | Sundeep |  |  | Manual test cases created | 0 | Manual test cases created | 263
WD: WOR-817, 818 (SINV Adj to use Bank rate) | 5 | Saravanan munikrishnan | 19.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Manual test cases conducted | 12 | Manual test cases conducted | 2126
WD: WOR-823, 824 (Refund to use Bank rate) | 4.5 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation test cases created | 0 | Automation test cases created | 262
WD: WOR-512 (Refund Status as paid) | 1.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation test cases processed | 34 | Automation test cases processed | 8938
WD: Ad-Hoc Testing | 16.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs identified | 1 | Bugs identified | 206
WD: AR/AP Dashboard | 2.5 | [19 empty] | Automation coverage | 99.62%
WD: Automation Script Enhancement | 5
WD: Automation: Multi-SR & Power Bi | 1

## 16 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 6 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 263
WD: WOR-817, 818 (SINV Adj to use Bank rate) | 5 | Saravanan munikrishnan | 19.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Manual test cases conducted | 20 | Manual test cases conducted | 2146
WD: WOR-823, 824 (Refund to use Bank rate) | 4.5 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation test cases created | 0 | Automation test cases created | 262
WD: WOR-512 (Refund Status as paid) | 1.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation test cases processed | 46 | Automation test cases processed | 8984
WD: Ad-Hoc Testing | 16.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs identified | 0 | Bugs identified | 206
WD: AR/AP Dashboard | 2.5 | [19 empty] | Automation coverage | 99.62%
WD: Automation Script Enhancement | 5
WD: Automation: Multi-SR & Power Bi | 1

## 23 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 6 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_277 | SFTP was not configured hence Refund status was not reflected as Paid | Medium | Closed | Sundeep |  |  | Manual test cases created | 0 | Manual test cases created | 263
WD: WOR-817, 818 (SINV Adj to use Bank rate) | 5 | Saravanan munikrishnan | 19.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | Observation_278 | SFTP was not configured hence Refund data did not flow to vEMS | Medium | Closed | Sundeep |  |  | Manual test cases conducted | 20 | Manual test cases conducted | 2166
WD: WOR-823, 824 (Refund to use Bank rate) | 4.5 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | Observation_279 | INT101D is not processing SINV related data properly. It scheduled to process last 1 hour data instead of 24 hours | Medium | Closed | Devendra |  |  | Automation test cases created | 0 | Automation test cases created | 262
WD: WOR-512 (Refund Status as paid) | 1.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation test cases processed | 46 | Automation test cases processed | 9030
WD: Ad-Hoc Testing | 16.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs identified | 3 | Bugs identified | 209
WD: AR/AP Dashboard | 2.5 | [19 empty] | Automation coverage | 99.62%
WD: Automation Script Enhancement | 5
WD: Automation: Multi-SR & Power Bi | 1

## 30 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 6 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_280 | SINV Adj with JPY/ KRW failed to do Currency conversion for CINV. | Medium | Closed | Sundeep |  |  | Manual test cases created | 0 | Manual test cases created | 263
WD: WOR-817, 818 (SINV Adj to use Bank rate) | 5 | Saravanan munikrishnan | 19.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Manual test cases conducted | 12 | Manual test cases conducted | 2178
WD: WOR-823, 824 (Refund to use Bank rate) | 4.5 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation test cases created | 0 | Automation test cases created | 262
WD: WOR-512 (Refund Status as paid) | 1.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation test cases processed | 36 | Automation test cases processed | 9066
WD: Ad-Hoc Testing | 16.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs identified | 1 | Bugs identified | 210
WD: AR/AP Dashboard | 2.5 | [19 empty] | Automation coverage | 99.62%
WD: Automation Script Enhancement | 5
WD: Automation: Multi-SR & Power Bi | 1

## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 2.5 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_281 | SINV Adj with GBP failed to do Currency conversion for CINV. | Medium | Closed | Sundeep |  |  | Manual test cases created | 0 | Manual test cases created | 263
WD: WOR-817, 818 (SINV Adj to use Bank rate) | 1 | Saravanan munikrishnan | 6 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Regression Testing will be done, once issue fixed | Observation_282 | INT101D is not processing SINV related data properly. It scheduled to process last 1 hour data instead of 24 hours | Medium | Open | Devendra |  |  | Manual test cases conducted | 9 | Manual test cases conducted | 2187
WD: WOR-823, 824 (Refund to use Bank rate) | 2 | Vignesh dhakshnamoorthy | 10 | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Requirement got changed, waiting for new changes | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation test cases created | 0 | Automation test cases created | 262
WD: AR/AP Dashboard | 20.5 |  |  | WD-Regression Suite | Blocked | TBD | Phase-5:- Power Bi validation: Blocked due to INT101D issue | WD-Regression Suite | Blocked | TBD | Phase-5- Power Bi: Blocked by INT101D issue | [7 empty] | Automation test cases processed | 24 | Automation test cases processed | 9090
WD: Automation Script Enhancement | 4 |  |  | AR/AP Dashboard | In Progress | 2023-11-21 | FIN Reports: Worked on Requirement gathering & Access Working on Table design | AR/AP Dashboard | In Progress | 2023-11-21 | FIN Reports: Work on Table design and waiting for Data from vEMS | [7 empty] | Bugs identified | 2 | Bugs identified | 212
WD: Automation: Multi-SR & Power Bi | 6 | [19 empty] | Automation coverage | 99.62%

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 1 | Pramod rayate | 8 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_283 | INT0207 did not trigger and did not process the ER reconciliation | Medium | Open | Sundeep |  |  | Manual test cases created | 0 | Manual test cases created | 263
WD: WOR-817, 818 (SINV Adj to use Bank rate) | 3 | Saravanan munikrishnan | 8.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Functionality working as expected, Pending to check in FPNA | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Will check FPNA and start Full regression | Observation_284 | Refund status not reflecting as paid | Medium | Closed | Sundeep |  |  | Manual test cases conducted | 14 | Manual test cases conducted | 2201
WD: WOR-823, 824 (Refund to use Bank rate) | 2.5 | Vignesh dhakshnamoorthy | 17 | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Functionality working as expected, Pending to check in FPNA | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Will check FPNA and start Full regression | Observation_285 | INT0210a and INT0209 getting failed and not processing Fx journal entries to FPNA | Medium | Open | Ramesh |  |  | Automation test cases created | 0 | Automation test cases created | 262
WD: AR/AP Dashboard | 18.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | [7 empty] | Automation test cases processed | 38 | Automation test cases processed | 9128
WD: Automation Script Enhancement | 4 | [5 empty] | creating fresh data for validation |  |  |  | Prepare data and put more validation | [7 empty] | Bugs identified | 3 | Bugs identified | 215
WD: Automation: Multi-SR & Power Bi | 4.5 |  |  | AR/AP Dashboard | In Progress | 2023-11-24 | FIN Reports: Worked on Requirement gathering & Access | AR/AP Dashboard | In Progress | 2023-11-24 | FIN Reports: Get data & Access for vEMS | [9 empty] | Automation coverage | 99.62%
[7 empty] | Worked on Table design, able to receive data for Workday |  |  |  | Work on feeding data in dashboard

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 3.5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | 2023-12-05 | started Full regression in OAK-2 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 263
WD: WOR-817, 818 (SINV Adj to use Bank rate) | 2 | Saravanan munikrishnan | 20 | WOR-823, 824: Refund to use Bank Rate | Completed | 2023-11-21 | Functionality working as expected, Issue found in FPNA | WOR-882: Refund to use Bank Rate | In Progress | 2023-12-05 | Continue Full regression in OAK-2 and OAK-1 | [7 empty] | Manual test cases conducted | 18 | Manual test cases conducted | 2219
WD: WOR-823, 824 (Refund to use Bank rate) | 1 | Vignesh dhakshnamoorthy | 8 | WOR-817, 818: ADJ to use Bank Rate | Completed | 2023-11-21 | Functionality working as expected, Issue found in FPNA | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | [7 empty] | Automation test cases created | 0 | Automation test cases created | 262
WD: WOR-882 (Refund to use Bank rate) | 6 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress |  |  |  | Prepare data and put more validation | [7 empty] | Automation test cases processed | 22 | Automation test cases processed | 9150
WD: AR/AP Dashboard | 13 | [5 empty] | creating fresh data for validation | AR/AP Dashboard | In Progress | 2023-12-01 | FIN Reports: Get data & Access for vEMS | [7 empty] | Bugs identified | 0 | Bugs identified | 215
WD: Automation Script Enhancement | 9 |  |  | AR/AP Dashboard | In Progress | 2023-12-01 | FIN Reports: Worked on Requirement gathering & Access |  |  |  | Waiting for data from vEMS & Navision | [9 empty] | Automation coverage | 99.62%
WD: Automation: Multi-SR & Power Bi | 13.5 | [5 empty] | Table design completed, waiting for vEMS & Navision

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | 2023-12-05 | started Full regression in OAK-2, Faced issue in INT0209 & INT0210a | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_286 | SINV lines count populated as Zero in file | High | Closed | Sundeep |  |  | Manual test cases created | 0 | Manual test cases created | 263
WD: WOR-823, 824 (Refund to use Bank rate) | 1.5 | Saravanan munikrishnan | 20 | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress. created fresh data for validation | WOR-882: Refund to use Bank Rate | Blocked | TBD | Waiting for fix on issue with INT0209 & INT0210a | Observation_287 | All count files in FTP location was not in Sync as per date. Integration was failing to post files in FTP location | Medium | Closed | Sundeep |  |  | Manual test cases conducted | 4 | Manual test cases conducted | 2223
WD: WOR-882 (Refund to use Bank rate) | 4 | Vignesh dhakshnamoorthy | 8 | AR/AP Dashboard | In Progress | 2023-12-05 | FIN Reports Phase-1: Ready to consume Prod data | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress created fresh data for validation | [7 empty] | Automation test cases created | 0 | Automation test cases created | 262
WD: AR/AP Dashboard | 13 | [6 empty] | AR/AP Dashboard | In Progress | 2023-12-05 | FIN Reports Phase-1: Ready to consume Prod data | [7 empty] | Automation test cases processed | 20 | Automation test cases processed | 9170
WD: Automation Script Enhancement | 9 | [17 empty] | Bugs identified | 2 | Bugs identified | 217
WD: Automation: Multi-SR & Power Bi | 15.5 | [19 empty] | Automation coverage | 99.62%
vEMS: Automation(Multi SR & Power Bi) | 22

## 4 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 2.5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | TBD | Found issue in INT0209 & INT0210a, waiting for fix | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual test cases created | 12 | Manual test cases created | 275
WD: Ad-hoc business requests | 2.5 | Saravanan munikrishnan | 2.5 | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress Preparing additional validation list | WOR-882: Refund to use Bank Rate | Blocked | TBD | Found issue in INT0209 & INT0210a, waiting for fix | [7 empty] | Manual test cases conducted | 5 | Manual test cases conducted | 2228
WD: WOR-882 (Refund to use Bank rate) | 3.5 | Vignesh dhakshnamoorthy | 5 | AR/AP Dashboard | In Progress | 2023-12-11 | FIN Reports Phase-1: Ready to consume Prod data | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress Preparing additional validation list | [7 empty] | Automation test cases created | 6 | Automation test cases created | 268
WD: AR/AP Dashboard | 12.5 | [6 empty] | AR/AP Dashboard | In Progress | 2023-12-11 | FIN Reports Phase-1: Ready to consume Prod data. will work on vEMS data at FTP | [7 empty] | Automation test cases processed | 45 | Automation test cases processed | 9215
WD: Automation: Multi-SR & Power Bi | 6.5 | [17 empty] | Bugs identified | 0 | Bugs identified | 217
[21 empty] | Automation coverage | 97.5%

## 11 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | TBD | Found issue in INT0209 & INT0210a, waiting for fix | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_291 | INT0209 delay time for BP integration trigger is very high, need to reduce to 5 sec or less | High | Open | Ramesh |  |  | Manual test cases created | 13 | Manual test cases created | 288
WD: Ad-hoc business requests | 3 | Saravanan munikrishnan | 17 | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress Preparing additional validation list | WOR-882: Refund to use Bank Rate | Blocked | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | [7 empty] | Manual test cases conducted | 3 | Manual test cases conducted | 2231
WD: WOR-882 (Refund to use Bank rate) | 1.5 | Vignesh dhakshnamoorthy | 5 | AR/AP Dashboard | In Progress | 2023-12-18 | FIN Reports Phase-1: Completed Analyzed schedule time to run scripts for WD & vEMS | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress Review additional validation list with William | [7 empty] | Automation test cases created | 10 | Automation test cases created | 278
WD: AR/AP Dashboard | 13 | [6 empty] | AR/AP Dashboard | In Progress | 2023-12-19 | FIN Reports Phase-1: will work on vEMS data at FTP & Set up the schedule run at right time | [7 empty] | Automation test cases processed | 58 | Automation test cases processed | 9273
WD: Automation Script Enhancement | 7 | [17 empty] | Bugs identified | 1 | Bugs identified | 218
WD: Automation: Multi-SR & Power Bi | 12.5 | [19 empty] | Automation coverage | 96.5%

## 18 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 6 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | TBD | worked on WOR-927 with Ramesh, issue not yet resolved | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_292 | Approval by Cash Manager is missing in latest Settlement Run flow | Medium | Open | Ramesh |  |  | Manual test cases created | 0 | Manual test cases created | 288
WD: Ad-hoc business requests | 2 | Saravanan munikrishnan | 17.5 | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Adding scripts for vEMS allocation variants | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | Observation_293 | Settlement Run for SINV payment is taking more than usual time | High | Open | Ramesh |  |  | Manual test cases conducted | 4 | Manual test cases conducted | 2235
WD: WOR-927 (Fix INT0209) | 1.5 | Vignesh dhakshnamoorthy | 7.5 | AR/AP Dashboard | In Progress | 2023-12-19 | FIN Reports Phase-1: Completed | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Adding scripts for vEMS allocation variants | Observation_294 | ER Header & Line Count mis-matches with Finsmart count by only 1 record | Low | Open | Sundeep |  |  | Automation test cases created | 5 | Automation test cases created | 283
WD: AR/AP Dashboard | 11.5 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Initial analysis done on Test scripts from Business side and Environment readiness | AR/AP Dashboard | In Progress | 2023-12-29 | FIN Reports Phase-1: will work on vEMS data at FTP & Set up the schedule run at right time | [7 empty] | Automation test cases processed | 25 | Automation test cases processed | 9298
WD: WOR-939 SC, BR, COA mapping | 4.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | TBD | Work on keeping the test Pre-requisites ready | [7 empty] | Bugs identified | 3 | Bugs identified | 221
WD: Automation Script Enhancement | 11 | [19 empty] | Automation coverage | 98.3%
WD: Automation: Multi-SR & Power Bi | 8.5

## 26 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 4 | Pramod rayate | 12 | WOR-882: Refund to use Bank Rate | In Progress | TBD | worked on WOR-927 with Ramesh, issue not yet resolved | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_292 | Approval by Cash Manager is missing in latest Settlement Run flow | Medium | Open | Ramesh |  |  | Manual test cases created | 0 | Manual test cases created | 288
WD: WOR-927 (Fix INT0209) | 3 | Saravanan munikrishnan | 9 | WD-Regression Suite | In Progress | TBD | Phase-5:- Added scripts for vEMS allocation variations | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | [7 empty] | Manual test cases conducted | 4 | Manual test cases conducted | 2239
WD: AR/AP Dashboard | 5.5 | Vignesh dhakshnamoorthy | 4 | AR/AP Dashboard | Completed | 2024-12-29 | FIN Reports Phase-1: Completed | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Will verify scripts for WD & vEMS allocation variants | [7 empty] | Automation test cases created | 4 | Automation test cases created | 287
WD: WOR-939 SC, BR, COA mapping | 4 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Prepared and checked feasibility of the business scenarios in OAK-2 | AR/AP Dashboard | In Progress | 2024-01-04 | FIN Reports Phase-1: will work on vEMS data at FTP & Set up the schedule run at right time | [7 empty] | Automation test cases processed | 20 | Automation test cases processed | 9318
WD: Automation Script Enhancement | 8.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-15 | Work on keeping the test Pre-requisites ready and kick off once we final review completed | [7 empty] | Bugs identified | 1 | Bugs identified | 222
[21 empty] | Automation coverage | 99.7%

## 2 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 2.5 | Pramod rayate | 16 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_295 | Ledger period for year 2024 not opened which blocks SINV/ER flow | Low | Closed | Anand |  |  | Manual test cases created | 0 | Manual test cases created | 288
WD: WOR-927 (Fix INT0209) | 1 | Saravanan munikrishnan | 18 | WD-Regression Suite | In Progress | TBD | Phase-5:- Added scripts for WOR-939 having WD & vEMS allocation variations | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | Observation_296 | INT0503 for accounting adjustment is not processing file for InterCo cases | Low | Open | Sundeep |  |  | Manual test cases conducted | 3 | Manual test cases conducted | 2242
WD: AR/AP Dashboard | 5 | Vignesh dhakshnamoorthy | 4 | AR/AP Dashboard | Completed | 2024-01-02 | FIN Reports Phase-1: Completed. Monitoring data count & performance | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Will enhance scripts for WD & vEMS allocation variants | Observation_297 | CINV & CPAY Count mis-matches with Finsmart count across week | Medium | Open | Sundeep |  |  | Automation test cases created | 0 | Automation test cases created | 287
WD: WOR-939 SC, BR, COA mapping | 9.5 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Discussed & Reviewed the business scenarios in OAK-2 | AR/AP Dashboard | In Progress | TBD | FIN Reports Phase-1: will work on vEMS data at FTP & Set up the schedule run at right time | [7 empty] | Automation test cases processed | 24 | Automation test cases processed | 9342
WD: Automation Script Enhancement | 9 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-15 | Work on keeping the test Pre-requisites ready and kick off once we final review completed | [7 empty] | Bugs identified | 3 | Bugs identified | 225
WD: Enhancement for SC & COA changes in SINV and ER | 11 | [19 empty] | Automation coverage | 99.7%

## 8 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 2.5 | Pramod rayate | 30 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_299 | Given data was not available in OAK-2 | Medium | Open | Anand |  |  | Manual test cases created | 0 | Manual test cases created | 288
WD: AR/AP Dashboard | 5 | Saravanan munikrishnan | 27 | WD-Regression Suite | In Progress | TBD | Phase-5:- Added scripts for WOR-939 having WD & vEMS allocation variations- Checked & verified | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | Observation_300 | SC, EAP & BR combination issue at Workday | Medium | Open | Anand |  |  | Manual test cases conducted | 0 | Manual test cases conducted | 2242
WD: WOR-939 SC, BR, COA mapping | 33.5 | Vignesh dhakshnamoorthy | 4 | AR/AP Dashboard | Completed |  | FIN Reports Phase-1: Completed Monitoring data count & performance | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Enhance scripts for WD & vEMS allocation variants as needed | Observation_301 | Spend Category not found in OAK-2 | Medium | Open | Anand |  |  | Automation test cases created | 0 | Automation test cases created | 287
WD: Automation Script Enhancement | 4.5 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Test execution - In Progress (Blocked due to issue) | AR/AP Dashboard | In Progress | TBD | FIN Reports Phase-1: Merge Prod & Dev in single to make it centralized | Observation_304 | INT141 Issue-Paid status not reflected at vEMS | High | Open | Sundeep |  |  | Automation test cases processed | 76 | Automation test cases processed | 9418
WD: Enhancement for SC & COA changes in SINV and ER | 15.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-19 | Will get issues resolved and complete testing | Observation_305 | Woakday BP approval process has some issue as approver list is in-accurate and never ending | High | Open | Anand |  |  | Bugs identified | 5 | Bugs identified | 230
| 11 | [19 empty] | Automation coverage | 99.7%

## 15 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 2.5 | Pramod rayate | 30 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_299 | Given data was not available in OAK-2 | Medium | Open | Anand |  |  | Manual test cases created | 0 | Manual test cases created | 288
WD: AR/AP Dashboard | 5 | Saravanan munikrishnan | 27 | WD-Regression Suite | In Progress | TBD | Phase-5:- Added scripts for WOR-939 having WD & vEMS allocation variations- Checked & verified | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | Observation_300 | SC, EAP & BR combination issue at Workday | Medium | Open | Anand |  |  | Manual test cases conducted | 0 | Manual test cases conducted | 2242
WD: WOR-939 SC, BR, COA mapping | 33.5 | Vignesh dhakshnamoorthy | 4 | AR/AP Dashboard | Completed |  | FIN Reports Phase-1: Completed Monitoring data count & performance | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Enhance scripts for WD & vEMS allocation variants as needed | Observation_301 | Spend Category not found in OAK-2 | Medium | Open | Anand |  |  | Automation test cases created | 0 | Automation test cases created | 287
WD: Automation Script Enhancement | 4.5 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Test execution - In Progress (Blocked due to issue) | AR/AP Dashboard | In Progress | TBD | FIN Reports Phase-1: Merge Prod & Dev in single to make it centralized | Observation_304 | INT141 Issue-Paid status not reflected at vEMS | High | Open | Sundeep |  |  | Automation test cases processed | 56 | Automation test cases processed | 9474
WD: Enhancement for SC & COA changes in SINV and ER | 15.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-19 | Will get issues resolved and complete testing | Observation_305 | Woakday BP approval process has some issue as approver list is in-accurate and never ending | High | Open | Anand |  |  | Bugs identified | 1 | Bugs identified | 231
| 11 | [19 empty] | Automation coverage | 99.7%

## 22 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 4.5 | Pramod rayate | 18 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_309 | Geneva Accrual failed due to in-correct Allowability matrix update at vEMS | Critical | Open | Kim |  |  | Manual test cases created | 0 | Manual test cases created | 288
WD: AR/AP Dashboard | 2.5 | Saravanan munikrishnan | 19 | WD-Regression Suite | In Progress | TBD | Phase-5:- Fine tuned scripts for WOR-939 having WD & vEMS allocation variations- Checked & verified | WOR-882: Refund to use Bank Rate | On Hold | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | Observation_310 | In-valid SC, BR combination for accounting adjustment at vEMS. Due to wrong SC selection at WD | High | Open | Kim |  |  | Manual test cases conducted | 0 | Manual test cases conducted | 2242
WD: WOR-939 SC, BR, COA mapping | 20 | Vignesh dhakshnamoorthy | 2 | AR/AP Dashboard | Completed |  | FIN Reports Phase-1: Completed Monitoring data count & performance | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Enhance scripts for WD & vEMS allocation variants as needed | Observation_311 | Validation error occurred. Transaction credits or debits must be populated if the line companies have different ledger currencies. | High | Open | Sundeep |  |  | Automation test cases created | 0 | Automation test cases created | 287
WD: Automation Script Enhancement | 6 |  |  | WOR-939: SC, BR, COA mapping | In Progress | 2024-02-02 | Test execution - In Progress (Blocked due to issues) | AR/AP Dashboard | In Progress | 2024-02-02 | FIN Reports Phase-1: Merge Prod & Dev in single to make it centralized - ETA-02-Feb | Observation_312 | Validation error occurred. The Accounting Journal is posted or canceled or is an intercompany or reversal journal and cannot be submitted. | Medium | Open | Sundeep |  |  | Automation test cases processed | 25 | Automation test cases processed | 9499
WD: Enhancement for SC & COA changes in SINV and ER | 6 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-02-02 | Will get issues resolved and complete testing | Observation_313 | Validation error occurred. Invalid ID value. 'CUST-00003059' is not a valid ID value for type = 'Customer_Reference_ID' | Medium | Open | Sundeep |  |  | Bugs identified | 5 | Bugs identified | 236
[21 empty] | Automation coverage | 99.7%

## 29 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 4.5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_317 | Unable to perform allocation for SINV/ ER of type Accounting adjustment Corp to Fund | Medium | Open | Kim |  |  | Manual test cases created | 0 | Manual test cases created | 288
WD: AR/AP Dashboard | 4 | Saravanan munikrishnan | 13.5 | WD-Regression Suite | In Progress | TBD | Phase-5:- Enhanced scripts for WOR-939 having WD & vEMS allocation variations- Checked & verified | WOR-882: Refund to use Bank Rate | On Hold | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | [7 empty] | Manual test cases conducted | 15 | Manual test cases conducted | 2257
WD: WOR-939 SC, BR, COA mapping | 21 | Vignesh dhakshnamoorthy | 2.5 | AR/AP Dashboard | In Progress |  | FIN Reports Phase-2: In progress | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold | [7 empty] | Automation test cases created | 0 | Automation test cases created | 287
WD: Automation Script Enhancement | 2 | [5 empty] | Monitoring data count & performance |  |  |  | Enhance scripts for WD & vEMS allocation variants as needed | [7 empty] | Automation test cases processed | 50 | Automation test cases processed | 9549
WD: Enhancement for SC & COA changes in SINV and ER | 4.5 |  |  | WOR-939: SC, BR, COA mapping | In Progress | 2024-02-08 | Test execution - In Progress (Addressed majority issues) | AR/AP Dashboard | In Progress | 2024-02-09 | FIN Reports Phase-1: Merge Prod & Dev in single to make it centralized - ETA-09-Feb | [7 empty] | Bugs identified | 1 | Bugs identified | 237
[8 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-02-08 | Will get issues resolved and complete testing | [9 empty] | Automation coverage | 99.7%

## 5 Feb 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 2.5 | Pramod rayate | 13 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_318 |  |  | Closed | Sundeep |  |  | Manual test cases created | 0 | Manual test cases created | 288
WD: AR/AP Dashboard | 4.5 | Saravanan munikrishnan | 8 | WD-Regression Suite | In Progress | TBD | Phase-5:- Enhanced scripts for WOR-939 having WD & vEMS allocation variations - Checked & verified | WOR-882: Refund to use Bank Rate | On Hold | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | Observation_319 |  |  | Closed | Sundeep |  |  | Manual test cases conducted | 10 | Manual test cases conducted | 2267
WD: WOR-939 SC, BR, COA mapping | 9.5 | Vignesh dhakshnamoorthy | 2.5 | AR/AP Dashboard | In Progress |  | FIN Reports Phase-2: In progress | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold | Observation_320 |  |  | Open | Kim |  |  | Automation test cases created | 0 | Automation test cases created | 287
WD: Automation Script Enhancement | 5 | [5 empty] | Monitoring data count & performance |  |  |  | Enhance scripts for WD & vEMS allocation variants as needed | [7 empty] | Automation test cases processed | 25 | Automation test cases processed | 9574
WD: Enhancement for SC & COA changes in SINV and ER | 2 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Test execution - Completed (few minor issues still open) | AR/AP Dashboard | In Progress | 2024-02-15 | FIN Reports Phase-1: Merge Prod & Dev in single to make it centralized - ETA-15-Feb | [7 empty] | Bugs identified | 3 | Bugs identified | 240
[8 empty] | WOR-939: SC, BR, COA mapping | In Progress | TBD | Will get issues resolved and complete testing | [9 empty] | Automation coverage | 99.7%

## 12 Feb 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
WD: WD Team Scrum Call | 2.5 | Pramod rayate | 20 | WOR-939: SC, BR, COA mapping | In Progress | TBD | Test execution - Completed (few minor issues still open) | WOR-939: SC, BR, COA mapping | In Progress | TBD | Will get issues resolved and complete testing | Observation_321 | Ledger period for year 2024 not opened which blocked SINV/ER Intercompany journal creation | Medium | Open | Sundeep |  |  | Manual test cases created | 0 | Manual test cases created | 288
WD: AR/AP Dashboard | 8.5 | Saravanan munikrishnan | 14 | WD: WOR-956 (2 recon lines for single SINV) | In Progress | 2024-02-20 | Understood the issue and fix, Trying to replicate exact case | WD: WOR-956 (2 recon lines for single SINV) | In Progress | 2024-02-20 | Understood the issue and fix, will finish testing | [7 empty] | Manual test cases conducted | 5 | Manual test cases conducted | 2272
WD: WOR-939 SC, BR, COA mapping | 2 | Vignesh dhakshnamoorthy | 5 | WD: WOR-962 (Emp Name issue in Recon ) | In Progress | 2024-02-22 | Understood the issue and fix, Testing in Progress | WD: WOR-962 (Emp Name issue in Recon ) | In Progress | 2024-02-22 | Understood the issue and fix, will finish testing | [7 empty] | Automation test cases created | 0 | Automation test cases created | 287
WD: WOR-956 (2 recon lines- single SINV) | 3 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Adding new WD functionalities in scripts - In Progress | WD-Regression Suite | In Progress | TBD | Phase-5:- Adding new WD functionalities in scripts - In Progress | [7 empty] | Automation test cases processed | 10 | Automation test cases processed | 9584
WD: WOR-962 (Emp Name issue in Recon) | 3.5 |  |  | AR/AP Dashboard | In Progress | 2024-02-21 | FIN Reports Phase-2: In progress | AR/AP Dashboard | In Progress | 2024-02-21 | FIN Reports Phase-2: In Progress | [7 empty] | Bugs identified | 1 | Bugs identified | 241
WD: Automation Script Enhancement | 7.5 | [5 empty] | Completed new changes at WD, vEMS changes- In progress | [13 empty] | Automation coverage | 99.7%
WD: Enhancement for SC & COA changes in SINV and ER | 12