## 2 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Stand up call | 3 | Ayesha Shaik | 23.5 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective Meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 17 | Manual test cases created | 416
Attended Sizing and Backlog Refinement meeting | 2 | Venkateswaran. Karuppian Ganesan | 18.5 | Attended Sizing and Backlog Refinement | Completed |  |  | Attend Spring Planning call | Yet to attend | [9 empty] | Manual test cases conducted | 22 | Manual test cases conducted | 415
Attended Weekly call with Business | 1.5 |  |  | Attended Weekly call with Business | Completed |  |  | Attend Weekly Call with Business | Yet to attend | [9 empty] | Automation test cases created | 0 | Automation test cases created | 0
Test Scenario Preparation of HICA-2596 | 2 |  |  | HICA-2596:Test Scenario Preparation | Completed |  |  | HICA-1909:Test Scenario Preparation | Yet to Start | 2023-09-10 | [8 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
Test Scenario Preparation of HICA-2613 | 2 |  |  | HICA-2596:Test Scenario Execution | Completed |  |  | HICA-1909: Test Scenario Execution | Yet to start | 9/11/2023 | [8 empty] | Bugs identified | 0 | Bugs identified | 50
Execution of HICA-2596 | 20 |  |  | HICA-2613:Test Scenario Preparation | Completed | [15 empty] | Automation coverage | 0
Execution of HICA-2613 | 5.5 |  |  | HICA-2613:Test Scenario Execution | Completed
Prepared SDLC document for HICA-2613 | 0.5 |  |  | HICA-853: Test Scenario Preparation | Completed
Call with Venkat | 2 |  |  | HICA-853: Test Scenario Execution | Inprogress | 2023-09-10
Call with Ayesha | 2
Analysis of HICA-1909 | 1.5

## 9 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Stand up call | 3 | Ayesha Shaik | 23.5 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 2 | Manual test cases created | 418
Attended Sprint review & Retrospective meeting | 6 | Venkateswaran. Karuppian Ganesan | 2 | Sprint Review and Retrospective meeting | Completed |  |  | Attend Weekly Call with Business | Yet to attend | [9 empty] | Manual test cases conducted | 2 | Manual test cases conducted | 417
Attended Sprint Planning meeting | 2 | Hrushikeshreddy Ambati | 17 | Sprint Planning meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Automation test cases created | 0 | Automation test cases created | 0
Test Scenario Preparation of HICA-1909 | 3 |  |  | HICA-1909:Test Scenario Execution | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
Analyzed test scenario for HICA-1909 | 2 |  |  | HICA-1909: Test Scenario Execution | Completed | [13 empty] | Bugs identified | 0 | Bugs identified | 50
Test Scenario Execution of HICA-1909 | 26 | [19 empty] | Automation coverage | 0
Call with Shantanu | 0.5

## 16 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Stand up call | 3 | Ayesha Shaik | 36.45 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective Meeting | Yet to attend |  |  | HICA-2777 | Verification PointSpecialAllocation page: Modified Paying entity is not displayed in the Verification page. | Medium | Open | Sibin |  |  | Manual test cases created | 16 | Manual test cases created | 434
Attended Sizing and Backlog Refinement | 4 | Venkateswaran. Karuppian Ganesan | 27 | Attended Sizing and Backlog Refinement | Completed |  |  | Attend Spring Planning call | Yet to attend | [9 empty] | Manual test cases conducted | 22 | Manual test cases conducted | 439
Attended Weekly meeting with Business | 2 |  |  | Attended Weekly call with Business | Completed |  |  | Attend Weekly Call with Business | Yet to attend | [9 empty] | Automation test cases created | 0 | Automation test cases created | 0
Attended Business call about PE issue for PSA | 1 |  |  | HICA-1909:QA document Preparation | Completed |  |  | HICA-2493:Test Scenario Execution | Inprogress | 2023-10-25 | [8 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
QA document preparation for HICA-1909 | 1.5 |  |  | HICA-2773: Test Scenario execution | Completed |  |  | HICA-1636: Test Scenario Preparation | Inprogress | 2023-10-24 | [8 empty] | Bugs identified | 1 | Bugs identified | 51
Test case preparation for HICA-2493 | 5 |  |  | HICA-2773: QA document execution | Completed |  |  | HICA-1636: Test Scenario Execution | Yet to start | 2023-10-24 | [10 empty] | Automation coverage | 0
Test Scenario Execution of HICA-2493 | 26.45 |  |  | HICA-2493:Test Scenario Preparation | Completed
Analysis and DB queries preparation for | 2 |  |  | HICA-2493:Test Scenario Execution | Inprogress | 2023-10-25
HICA-2773
Execution of HICA-2773 | 6
QA document preparation for HICA-2773 | 1
Testcase preparation for HICA-1636 | 7
Call with Sibin | 2.5
Call with Venkat | 1
Call with Ayesha | 1

## 23 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Stand up call | 1 | Ayesha Shaik | 23.5 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 18 | Manual test cases created | 452
Attended Sprint Review and Retrospective meeting | 6 | Venkateswaran. Karuppian Ganesan | 2 | Sprint Review and Retrospective meeting | Completed |  |  | Attend Weekly Call with Business | Yet to attend | [9 empty] | Manual test cases conducted | 29 | Manual test cases conducted | 468
Attended Sprint planning meeting | 1 | Hrushikeshreddy Ambati | 32 | Sprint Planning meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Automation test cases created | 0 | Automation test cases created | 0
Attended Weekly meeting with Business | 1 |  |  | Weekly Business meeting | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
Test Scenarios preparation for HICA-1636 | 4.5 |  |  | HICA-1636:Test Scenario Preparation | Completed | [13 empty] | Bugs identified | 0 | Bugs identified | 51
Test Scenario Execution for HICA-1636 | 18 |  |  | HICA-1636:Test Scenario Execution | Completed | [15 empty] | Automation coverage | 0
Test Scenarios preparation for HICA-2771 | 2 |  |  | HICA- 2771:Test Scenario Preparation | Completed
Test Scenarios Execution for HICA-2771 | 5 |  |  | HICA- 2771: Test Scenario Execution | Completed
Performed Regression for Special Deal and view grant pages | 18
Call with Sibin | 1

## 30 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Stand up call | 4.3 | Ayesha Shaik | 32.15 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective Meeting | Yet to attend |  |  | HICA-2886 | Perform CRUD operations on newly created PEs', facilitate bulk upload of PEs with special characters, and update existing PEs in the PSA module aligning with HRIS. | High | Closed | Sibin |  | Converted into story | Manual test cases created | 43 | Manual test cases created | 495
Attended Sizzing session & Backlog Refinement | 2 | Venkateswaran. Karuppian Ganesan | 40.15 | Attended Sizing and Backlog Refinement | Completed |  |  | Attend Spring Planning call | Yet to attend | [9 empty] | Manual test cases conducted | 43 | Manual test cases conducted | 511
HICA-2810 Regression on Paying Entity | 32 |  |  | HICA-2810 Regression on Paying Entity | Completed |  |  | Attend Weekly Call with Business | Yet to attend | [9 empty] | Automation test cases created | 0 | Automation test cases created | 0
HICA-2802:Test Scenario Preparation | 1.5 |  |  | HICA-2802:Test Scenario Preparation | Completed |  |  | Work on the tickets developed by the Dev team | Yet to attend | [9 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
HICA-2802: Test data preparation and connected with Oliva | 0.5 |  |  | HICA-2802: Test Scenario Execution | Inprogress | 2023-11-06 | [12 empty] | Bugs identified | 1 | Bugs identified | 52
HICA-2802: Test Scenario Execution | 4 |  |  | HICA-2763: Test Scenario Preparation | Completed | [15 empty] | Automation coverage | 0
HICA-2763: Test Scenario Preparation | 3 |  |  | HICA-2763: Test Scenario Execution | Completed
HICA-2763: Test cases Preparation | 4 |  |  | HICA-2886:Test Scenario Preparation | Completed
HICA-2763 Test cases review | 1 |  |  | HICA-2886:Test Scenario Execution | Inprogress | 2023-12-06
HICA-2763: Test Scenario Execution | 9.5
HICA-2886:Test Scenario Preparation | 3.5
HICA-2886:Test Scenario Execution | 5
Call with Venkat | 1
Call with Sibin | 1

## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Stand up call | 3 | Ayesha Shaik | 31.5 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 15 | Manual test cases created | 510
Sprint Review and Retrospective | 6 | Venkateswaran. Karuppian Ganesan | 40.2 | Sprint Review and Retrospective meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual test cases conducted | 15 | Manual test cases conducted | 526
Sprint Planning session | 2 |  |  | Sprint Planning meeting | Completed | [13 empty] | Automation test cases created | 0 | Automation test cases created | 0
HICA-2763 -Testcases and Scenarios review | 1 | [17 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
HICA-2293 Test Scenarios Prepared | 1 | [17 empty] | Bugs identified | 0 | Bugs identified | 52
HICA-2293 Test Case prepared | 3 | [19 empty] | Automation coverage | 0
Raised bug(converted to story) ie HICA-2920 | 0.5
HICA-2886 Test case prepared | 3.5
Execution for HICA-2293 | 8
HICA-2886 Execution for Payment screen | 28
HICA-2887 test scenarios prepared | 3
HICA-2887 re test for verification screen | 4.5
Test Scenarios preparation for HICA-2885 | 2.5
Test cases preparation for HICA-2885 | 4
Test data preparation for HICA-2886 | 0.3
call with Sibin | 0.4
Call with Ayesha | 1
Call with Venkat | 1
Weekly ICS Meeting | 1

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Stand up call | 3 | Ayesha Shaik | 25.5 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective Meeting | Yet to attend |  |  | HICA-3001 | PointsPayments - Include Paying Entity in the list of fields to be reverted to their original state on the rejection of payment and make sure the status is correctly updated when editing a payment using bulk upload | High | Closed | Sibin |  | COnverted to story | Manual test cases created | 15 | Manual test cases created | 525
Attended Sizzing session & Backlog Refinement | 2 | Venkateswaran. Karuppian Ganesan | 28 | Attended Sizing and Backlog Refinement | Completed |  |  | Attend Spring Planning call | Yet to attend | [9 empty] | Manual test cases conducted | 15 | Manual test cases conducted | 541
Attended Weekly call with Business | 1 |  |  | Attended Weekly business meeting | Completed |  |  | Work on the tickets developed by the Dev team | Yet to attend | [9 empty] | Automation test cases created | 0 | Automation test cases created | 0
Prepared QA document for SDLC#26767 | 1 |  |  | QA document for SDLC#26767 | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
HICA-2886 Test cases execution | 19 |  |  | HICA-2939 Test scenarios preparation | Completed | [13 empty] | Bugs identified | 1 | Bugs identified | 53
HICA-2939 Test scenarios preparation | 2 |  |  | HICA-2939: Test cases preparation | Completed | [15 empty] | Automation coverage | 0
HICA-2939 Test cases preparation | 2 |  |  | HICA-2939: Test Scenario Execution | Completed
HICA-2939 Test cases execution | 4 |  |  | HICA-2885: Test Scenario Preparation | Completed
HICA-2885 Test scenarios preparation | 2 |  |  | HICA-2885: Test cases Preparation | Completed
HICA-2885 Test cases preparation | 8 |  |  | HICA-2885: Test cases Execution | Inprogress | 2023-11-20
HICA-2885 Test cases Execution | 9 |  |  | HICA-2886:Test Scenario Execution | completed
call with Sibin | 0.5

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Stand up call | 1.5 | Ayesha Shaik | 19.5 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective Meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 7 | Manual test cases created | 532
Attended Sprint review and Retrospective Meeting | 3 | Hrushikesh Ambati | 1.5 | Attended Sprint review and Sprint retrospective meeting | Completed |  |  | Attend Spring Planning call | Yet to attend | [9 empty] | Manual test cases conducted | 7 | Manual test cases conducted | 548
Prepared QA document for SDLC#26839 | 4 |  |  | QA document for SDLC#26839 | Completed |  |  | Work on the tickets developed by the Dev team | Yet to attend | [9 empty] | Automation test cases created | 0 | Automation test cases created | 0
HICA-3001Test scenarios preparation | 2 |  |  | HICA-3001:Test scenarios preparation | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
HICA-3001 Test cases preparation | 4 |  |  | HICA-3001: Test cases preparation | Completed | [13 empty] | Bugs identified | 0 | Bugs identified | 53
HICA-3001 Test cases execution | 6 |  |  | HICA-3001: Test Scenario Execution | Completed | [15 empty] | Automation coverage | 0
call with Sibin | 0.5

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Stand up call | 1.85 | Ayesha Shaik | 31.1 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 532
Attended Sizing and refinement meeting | 1 |  |  | Attended Sizing and Backlog Refinement meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual test cases conducted | 0 | Manual test cases conducted | 548
Weekly Business call | 1 |  |  | Attended Sprint planning meeting | Completed | [13 empty] | Automation test cases created | 0 | Automation test cases created | 0
HICA-3010 Test scenarios Preparation | 2 |  |  | Attended Weekly business meeting | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
HICA-3010 Test cases Preparation | 4 |  |  | HICA-3010 Test Scenarios Preparation | Completed | [13 empty] | Bugs identified | 0 | Bugs identified | 53
HICA-3010 Test cases Execution | 7.5 |  |  | HICA-3010 Test cases preparation | Completed | [15 empty] | Automation coverage | 0
HICA-3016 Test scenarios Preparation | 2 |  |  | HICA-3016 Test Scenarios Preparation | Completed
HICA-3016 Test cases Preparation | 4 |  |  | HICA-3016 Test cases Preparation | Completed
HICA-3016 Test cases Execution | 7 |  |  | HICA-3016 Test cases Execution | Completed
Call with Sibin | 0.5 |  |  | HICA-3016: Test Scenarios Preparation | Completed
Call with James | 0.25

## 4 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Stand up call | 1.15 | Ayesha Shaik | 34 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 532
Attended Sprint Review and Restrospective meeting | 1 |  |  | Attended Sprint Review & Retrospective meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual test cases conducted | 0 | Manual test cases conducted | 548
Atteneded Sprint planning | 1 |  |  | Attended Sprint planning meeting | Completed |  |  | HICA-3094 Test cases Execution | Inprogress | 2023-12-11 | [8 empty] | Automation test cases created | 0 | Automation test cases created | 0
Weekly Business call | 0.85 |  |  | Attended Weekly business meeting | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
WSR preparation | 0.5 |  |  | QA document prepared for SDLC #26912 | Completed | [13 empty] | Bugs identified | 0 | Bugs identified | 53
HICA-3034: Test cases Execution | 3 |  |  | HICA-3054 Test Scenarios Preparation | Completed | [15 empty] | Automation coverage | 0
HICA-3074 Test Scenarios Preparation | 2 |  |  | HICA-3054 Test cases Preparation | Completed
HICA-3074 Test cases Preparation | 3 |  |  | HICA-3094 Test cases Execution | Completed
HICA-3074 Test cases Execution | 4 |  |  | HICA-3094: Test Scenarios Preparation | Completed
QA document prepared for SDLC #26912 | 2 |  |  | HICA-3094: Test Cases Execution | Inprogress | 2023-12-11
HICA-3054 Test Scenarios Preparation | 2.5
HICA-3054 Test cases Preparation | 5
HICA-3094 Test cases Preparation | 2
HICA-3094: Test Scenarios Preparation | 4
HICA-3094: Test Cases Execution | 1
Validated Ellen issue on transaction report | 1

## 11 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Stand up call | 0.85 | Ayesha Shaik | 25 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective Meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 8 | Manual test cases created | 540
Attended Sizing and backlog Refinement | 1 |  |  | Attended Sprint review and Sprint retrospective meeting | Completed |  |  | Attend Spring Planning call | Yet to attend | [9 empty] | Manual test cases conducted | 8 | Manual test cases conducted | 556
HICA-3094 Test cases Execution | 7.65 |  |  | QA document for SDLC#26839 | Completed |  |  | Work on the tickets developed by the Dev team | Yet to attend | [9 empty] | Automation test cases created | 0 | Automation test cases created | 0
HICA-3054 Test cases Execution | 14.5 |  |  | HICA-3001:Test scenarios preparation | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
Call with Sibin | 1 |  |  | HICA-3001: Test cases preparation | Completed | [13 empty] | Bugs identified | 0 | Bugs identified | 53
|  |  |  | HICA-3001: Test Scenario Execution | Completed | [15 empty] | Automation coverage | 0

## 18 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Stand up call | 0.85 | Ayesha Shaik | 25 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective Meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 8 | Manual test cases created | 548
Attended Sizing and backlog Refinement | 1 |  |  | Attended Sprint review and Sprint retrospective meeting | Completed |  |  | Attend Spring Planning call | Yet to attend | [9 empty] | Manual test cases conducted | 8 | Manual test cases conducted | 564
HICA-3094 Test cases Execution | 7.65 |  |  | QA document for SDLC#26839 | Completed |  |  | Work on the tickets developed by the Dev team | Yet to attend | [9 empty] | Automation test cases created | 0 | Automation test cases created | 0
HICA-3054 Test cases Execution | 14.5 |  |  | HICA-3001:Test scenarios preparation | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
Call with Sibin | 1 |  |  | HICA-3001: Test cases preparation | Completed | [13 empty] | Bugs identified | 0 | Bugs identified | 53
|  |  |  | HICA-3001: Test Scenario Execution | Completed | [15 empty] | Automation coverage | 0

## 26 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Stand up call | 0.5 | Ayesha Shaik | 18.5 | Attended Daily Standup calls | Completed |  |  | Attend Sprint review and retrospective meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 65 | Manual test cases created | 613
HICA-2677 Test cases preparation | 5 |  |  | HICA-2677 Test cases preparation | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual test cases conducted | 0 | Manual test cases conducted | 564
HICA-3104 Test scenarios preparation | 3.5 |  |  | HICA-3104 Test scenarios preparation | Completed | [13 empty] | Automation test cases created | 0 | Automation test cases created | 0
HICA-3104 Test cases preparation | 4.5 |  |  | HICA-3104 Test cases preparation | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
HICA-3111 Test scearios preparation | 5 |  |  | HICA-3111 Test scearios preparation | Completed | [13 empty] | Bugs identified | 0 | Bugs identified | 53
[21 empty] | Automation coverage | 0

## 2 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Daily Standup calls | 1 | Ayesha Shaik | 24.5 | Attended Daily Standup calls | Completed |  |  | Attend Sizing and backlog refinement | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 613
Sprint Review & Retrospective meeting | 2 |  |  | Sprint Review & Retrospective meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual test cases conducted | 12 | Manual test cases conducted | 564
Sprint planning meeting | 1 |  |  | Sprint planning meeting | Completed | [13 empty] | Automation test cases created | 0 | Automation test cases created | 0
WSR preparation | 0.5 |  |  | Weekly Business meeting | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
Weekly Business meeting | 1 |  |  | HICA-3088 execution | Completed | [13 empty] | Bugs identified | 0 | Bugs identified | 53
HICA-3088 execution | 12.5 |  |  | HICA-1647 Test scenarios preparation | Completed | [15 empty] | Automation coverage | 0
HICA-1647 Test scenarios preparation | 3.5 |  |  | HICA-1647 Test cases preparation | Inprogress | 2024-01-09
Executed modification grants tocheck which modification goes to verification queue | 3 |  |  | Executed modification grants tocheck which modification goes to verification queue | Completed

## 8 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Daily Standup calls | 2 | Ayesha Shaik | 33 | Attended Daily Standup calls | Completed |  |  | Attend Sizing and backlog refinement | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 613
Sizing and Backlog Refinement | 1 |  |  | Sizing and Backlog Refinement meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual test cases conducted | 23 | Manual test cases conducted | 587
WSR preparation | 0.5 |  |  | Weekly Business meeting | Completed | [13 empty] | Automation test cases created | 0 | Automation test cases created | 0
Weekly Business meeting | 0.5 |  |  | HICA-1647 Test cases preparation | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
HICA-1647 Test cases preparation | 5 |  |  | HICA-1647 Test cases Execution | Completed | [13 empty] | Bugs identified | 1 | Bugs identified | 53
HICA-1647 Test cases Execution | 15.5 |  |  | HICA-2660 Execution | Completed | [15 empty] | Automation coverage | 0
HICA-2660 Execution | 6.5
Cal With Sibin | 2

## 15 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Daily Standup calls | 1 | Ayesha Shaik | 25.5 | Attended Daily Standup calls | Completed |  |  | Attend Sizing and backlog refinement | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 24 | Manual test cases created | 637
Sprint review and retrsopective meeting | 2 |  |  | Sprint review and retrospective meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual test cases conducted | 0 | Manual test cases conducted | 587
Sprint planning | 1 |  |  | Sprint planning | Completed | [13 empty] | Automation test cases created | 0 | Automation test cases created | 0
WSR preparation | 0.5 |  |  | Weekly Business meeting | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
Weekly Business meeting | 0.5 |  |  | Sanity Testing | Completed | [13 empty] | Bugs identified | 0 | Bugs identified | 53
Sanity Testing | 3.5 |  |  | HICA-3111 Test cases preparation | Completed | [15 empty] | Automation coverage | 0
HICA-3111 Test cases preparation | 4 |  |  | HICA-3244 Test Scenarios Execution | Completed
HICA-3244 Test Scenarios Execution | 4 |  |  | HICA-3244 Test Cases Execution | Completed
HICA-3244 Test Cases Execution | 3 |  |  | Prepared QA documents for SDLC#27027 | Completed
Worked on "Audit summary report" with ransfer/dilution on same date and different date(Masis reported issue) | 3
Prepared QA documents for SDLC#27027 | 2
Cal With Sibin | 1

## 22 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Attended Daily Standup calls | 1.5 | Ayesha Shaik | 28.5 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 6 | Manual test cases created | 643
Sizing and Backlog Refinement | 1 |  |  | Sizing and Backlog Refinement | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual test cases conducted | 37 | Manual test cases conducted | 624
HICA-3225 Test Scenarios preparation | 3 |  |  | HICA-3225 Test Scenarios preparation | Completed | [13 empty] | Automation test cases created | 0 | Automation test cases created | 0
HICA-2677 Test cases Execution | 11 |  |  | HICA-2677 Test cases Execution | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
HICA-2677 Test cases Re-Execution(Child Fund changes in Maintaince screen) | 5.5 |  |  | HICA-3011 Test cases Execution | In Progress | 1/29/2024 | [12 empty] | Bugs identified | 0 | Bugs identified | 53
HICA-3011 Test cases Execution | 6 | [19 empty] | Automation coverage | 0
Call with James | 0.5