## 2 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
call with Hrushi Overview for HICA 853 | 0.5 | Ayesha Shaik | 7.5 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective Meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 3 | Total manual | 51
Analysed the HICA-853 | 2 | Venkateswaran. Karuppian Ganesan | 1 | Sprint Review and Retrospective meeting | Completed |  |  | Attend Spring Planning call | Yet to attend | [9 empty] | Manual execution | 3 | Total manual execution | 51
Prepared Testcases for HICA-853 | 2 | Hrushikesh | 8.5 | Sprint Planning meeting | Completed |  |  | Attend Weekly Call with Business | Yet to attend | [9 empty] | Automation created | 0 | Total automation | 0
Database Issues connected with Sibin | 0.25 |  |  | HICA-2596:Test case Prepared | Completed |  |  | HICA-1909: Test Scenario Execution | Yet to start | 2023-11-09 | [8 empty] | Automation execution | 0 | Total automation execution | 0
Call with Sibin | 1.25 | [17 empty] | Bugs Identified | 0 | Total bugs | 0
Call with Hrushikesh to support o job run | 3 | [19 empty] | Automation coverage % | 0
HICA-853 Executed testing | 8

## 9 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Analyzed the test Scenario for HICA-853 | 2 | Ayesha Shaik | 11 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 51
Executed the test Scenario for HICA-853 | 2 | Venkateswaran. Karuppian Ganesan | 13.25 | Sprint Review and Retrospective meeting | Completed |  |  | Attend Weekly Call with Business | Yet to attend | [9 empty] | Manual execution | 0 | Total manual execution | 51
Execution of HICA-853 | 4 | Hrushikesh | 1 | Sprint Planning meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Automation created | 0 | Total automation | 0
Call with Sibin | 0.25 | [17 empty] | Automation execution | 0 | Total automation execution | 0
Call with Hrushikesh To run a job file | 3 | [17 empty] | Bugs Identified | 0 | Total bugs | 0
Test Scenarios preparation for HICA-2727 | 2 | [19 empty] | Automation coverage % | 0
Examine the ticket HICA-2727 | 1
Analyzed the test Scenario For HICA 2727 | 1
Test case prepared for HICA-2727 | 4
Executed the test scenario for HICA-2727 | 6

## 16 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Test Scenarios Execution for HICA-2727 | 3 | Ayesha Shaik | 5 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective Meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 3 | Total manual | 54
QA document prepaartion for HICA-853,HICA-2727 | 2 | Venkateswaran. Karuppian Ganesan | 2 | Attended Sizing and Backlog Refinement | Completed |  |  | Attend Spring Planning call | Yet to attend | [9 empty] | Manual execution | 3 | Total manual execution | 54
Test case Prepared For HICA-2727 | 2 |  |  | Attended Weekly call with Business | Completed |  |  | Attend Weekly Call with Business | Yet to attend | [9 empty] | Automation created | 0 | Total automation | 0
|  |  |  | HICA-2727: Test Case prepared | Completed | [13 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 23 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
HICA-2811 Test scenarios preparation | 1.5 | Ayesha Shaik | 9.45 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective Meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 54
Call with Hrushikesh on Eevrest UAT installation | 1 | Venkateswaran. Karuppian Ganesan | 0.25 | Sprint Review and Retrospective meeting | Completed |  |  | Attend Spring Planning call | Yet to attend | [9 empty] | Manual execution | 0 | Total manual execution | 54
HICA-2811 Test scenarios Execution | 5 |  |  | Sprint Planning meeting | Completed |  |  | Attend Weekly Call with Business | Yet to attend | [9 empty] | Automation created | 0 | Total automation | 0
Test cases preparation for HICA-2876 | 2 | [17 empty] | Automation execution | 0 | Total automation execution | 0
Call with Sibin | 0.5 | [17 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 30 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
HICA-2811 Test scenarios preparation | 1.5 | Ayesha Shaik | 9.45 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective Meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 3 | Total manual | 57
Call with Hrushikesh on Eevrest UAT installation | 1 | Venkateswaran. Karuppian Ganesan | 0.25 | Sprint Review and Retrospective meeting | Completed |  |  | Attend Spring Planning call | Yet to attend | [9 empty] | Manual execution | 3 | Total manual execution | 57
HICA-2811 Test scenarios Execution | 5 |  |  | Sprint Planning meeting | Completed |  |  | Attend Weekly Call with Business | Yet to attend | [9 empty] | Automation created | 0 | Total automation | 0
Test cases preparation for HICA-2876 | 2 | [17 empty] | Automation execution | 0 | Total automation execution | 0
Call with Sibin | 0.5 | [17 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
HICA-2876 Test scenarios execution | 6.5 | Ayesha Shaik | 7.5 | Attended Daily Standup calls | Completed |  |  | Attend Sizing and backlog refinement meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 4 | Total manual | 61
QA document preparation for HICA-2876 | 1 |  |  | Sprint Review and Retrospective meeting | Completed |  |  | Attend Weekly Call with Business | Yet to attend | [9 empty] | Manual execution | 4 | Total manual execution | 61
|  |  |  | Sprint Planning meeting | Completed | [13 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
HICA-2925 Test scenarios preparation | 2 | Ayesha Shaik | 7.5 | Attended Daily Standup calls | Completed |  |  | Attend Sprint review and Retrospective meeting | Yet to attend |  |  | HICA-2920 | Job run in Swift folder: No email notification triggered when other .fin file is placed in Inbound file | Medium | Closed | Sibin |  | Converted to story | Manual created | 6 | Total manual | 67
HICA-2925 Test cases preparation | 4 |  |  | Attend Sizing and backlog refinement meeting | Completed |  |  | Attend Sprint planning call | Yet to attend | [9 empty] | Manual execution | 6 | Total manual execution | 67
HICA-2925 Test cases execution | 1.5 |  |  | HICA-2925 Test Scenarios Preparation | Completed | [13 empty] | Automation created | 0 | Total automation | 0
|  |  |  | HICA-2925 Test cases Preparation | Completed | [13 empty] | Automation execution | 0 | Total automation execution | 0
|  |  |  | HICA-2925 Test cases Execution | In Progress | 2023-11-20 | [12 empty] | Bugs Identified | 1 | Total bugs | 1
[21 empty] | Automation coverage % | 0

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
HICA-2925 Test scenarios executi | 6 | Ayesha Shaik | 12.5 | Attended Daily Standup calls | Completed |  |  | Attend Sizing and backlog refinement meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 8 | Total manual | 75
Updation of Test scenarios and Test cases for Tier-2 | 0.5 |  |  | Sprint Review and Retrospective meeting | Completed |  |  | Attend Weekly Call with Business | Yet to attend | [9 empty] | Manual execution | 8 | Total manual execution | 75
HICA-3034 Test Scenarios preparation | 2 |  |  | Sprint Planning meeting | Completed | [13 empty] | Automation created | 0 | Total automation | 0
HICA-3034 Test cases preparation | 4 | [17 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 1
[21 empty] | Automation coverage % | 0

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
HICA-3034 Test cases execution | 3 | Ayesha Shaik | 3 | HICA-3034: Test cases Execution | Inprogress | 12/4/2023 |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 8 | Total manual | 83
|  |  |  | Attended Daily Standup calls | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 8 | Total manual execution | 83
|  |  |  | Attended Sizing and Backlog Refinement meeting | Completed |  |  | HICA-3034 Test cases Execution | Inprogress | 2023-12-04 | [8 empty] | Automation created | 0 | Total automation | 0
|  |  |  | Attended Sprint planning meeting | Completed | [13 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 1
[21 empty] | Automation coverage % | 0

## 4 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
HICA-3073 Test Scenarios Preparation | 2 | Ayesha Shaik | 13 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 4 | Total manual | 87
HICA-3073 Test cases Preparation | 3 |  |  | Attended Sprint Review & Retrospective meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 4 | Total manual execution | 87
HICA-3073 Test cases Execution | 4 |  |  | Attended Sprint planning meeting | Completed | [13 empty] | Automation created | 0 | Total automation | 0
QA document prepared for SDLC-26937 | 2 |  |  | HICA-3034: Test cases Execution | Completed | [13 empty] | Automation execution | 0 | Total automation execution | 0
Call with Sibin | 1 |  |  | HICA-3073 Test Scenarios Preparation | Completed | [13 empty] | Bugs Identified | 0 | Total bugs | 1
KT on position response | 1 |  |  | HICA-3073 Test cases Preparation | Completed | [15 empty] | Automation coverage % | 0
|  |  |  | HICA-3073 Test cases Execution | Completed
|  |  |  | HICA-3074 Test Scenarios Preparation | Completed
|  |  |  | HICA-3074 Test cases Preparation | Completed
|  |  |  | HICA-3074 Test cases Execution | Completed
|  |  |  | QA document prepared for SDLC-26937 | Completed
|  |  |  | KT document for Position response | Inprogress | 2023-12-14

## 11 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
HICA-3071 Test Scenarios Preparation | 2 | Ayesha Shaik | 14 | HICA-3071 Test Scenarios Preparation | Completed |  |  | Attend Sizing and backlog refinement meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 4 | Total manual | 91
HICA-3071 Test cases Preparation | 4 |  |  | HICA-3071 Test cases Preparation | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | In progress | [9 empty] | Manual execution | 4 | Total manual execution | 91
HICA-3071 Test cases Execution | 8 |  |  | HICA-3071 Test cases Execution | Completed |  |  | HICA-1823 Test Scenarios Preparation | Yet to start | [9 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 1
[21 empty] | Automation coverage % | 0

## 18 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
HICA-1823 Test Scenarios Preparation | 3 | Ayesha Shaik | 9.5 | HICA-1823 Test Scenarios Preparation | Completed |  |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 2 | Total manual | 93
HICA-1823 Test cases Preparation | 4.5 | [6 empty] | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 2 | Total manual execution | 93
HICA-1823 Test cases Execution | 6 | [17 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 1
[21 empty] | Automation coverage % | 0

## 26 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
Attended Stand up call | 0.5 | Ayesha Shaik | 0.5 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 93
[8 empty] | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 93
[19 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 1
[21 empty] | Automation coverage % | 0

## 2 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
HICA-3166 Test scenarios preparation | 3.5 | Ayesha Shaik | 7.5 | Attended Daily Standup calls | Completed |  |  | Attend Sizing and backlog refinement | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 93
HICA-3166 Test scearios preparation | 4 |  |  | Sprint Review & Retrospective meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 93
|  |  |  | Sprint planning meeting | Completed | [13 empty] | Automation created | 0 | Total automation | 0
|  |  |  | HICA-3166 Test scenarios preparation | Completed | [13 empty] | Automation execution | 0 | Total automation execution | 0
|  |  |  | HICA-3166 Test scenarios preparation | Completed | [13 empty] | Bugs Identified | 0 | Total bugs | 1
[21 empty] | Automation coverage % | 0

## 8 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
HICA-3166 Test cases Execution | 7 | Ayesha Shaik | 7 | Attended Daily Standup calls | Completed |  |  | Attend Sizing and backlog refinement | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 93
|  |  |  | Sizing and Backlog Refinement meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 2 | Total manual execution | 95
|  |  |  | HICA-3166 Test cases Execution | Completed | [13 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 1
[21 empty] | Automation coverage % | 0

## 15 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
Prepared QA documents for SDLC#27036 | 3 | Ayesha Shaik | 3 | Prepared QA documents for SDLC#27036 | Completed |  |  | Attend Sizing and backlog refinement | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 93
[8 empty] | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 95
[19 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 1
[21 empty] | Automation coverage % | 0

## 22 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Project Metrics | Total Count
No task | 0 | Ayesha Shaik | 0 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 93
|  |  |  | Sizing and Backlog Refinement | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 95
[19 empty] | Automation created | 0 | Total automation | 0
[19 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 1
[21 empty] | Automation coverage % | 0