## 2 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
1.Standup /Internal/Dev calls | 6 | Eswara Rao Kanakala | 8 | 1. Standup Calls/Dev Calls | In Progress |  |  | Test Scenarios, Test Cases Review | InProgress | 06- Oct |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 0
2. Application Hands on Experience | 7.5 | Samikruth Reddy | 11 | 2. Explore Application: Completed Test Scenario, Test Cases Preparation: Completed Test Plan Preparation: InProgress | In Progress | [13 empty] | Manual execution | 0 | Total manual execution | 0
3 Test Scenarios, Test Cases Preparation and review | 9 | Meenakshi | 6 | [15 empty] | Automation created | 0 | Total automation | 0
4. Test Plan Preparation | 2.5 | [17 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 9 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
1.Standup /Internal/Dev calls | 9.5 | Eswara Rao Kanakala | 5 | 1. Standup Calls/Dev Calls | In Progress |  |  | Testing Extraordinary investment loss | InProgress | 13- Oct |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 0
2. Test Scenarios, Test Cases Preparation and review and Test Plan Preparation | 15.5 | Samikruth Reddy | 16 | 2. Test cases, Scenarios and Test Plan Preparation &Review | In Progress |  |  | Automation | In Progress | TBD | [8 empty] | Manual execution | 0 | Total manual execution | 0
3. Automation | 7 | Vignesh | 7 | 3. Automation | In Progress |  |  | Test cases, Scenarios and Test Plan Preparation &Review | In Progress | TBD | [8 empty] | Automation created | 0 | Total automation | 0
|  | Meenakshi | 4 | [15 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 16 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
1.Standup /Internal/Dev calls | 13 | Eswara Rao Kanakala | 30 | 1. Standup Calls/Dev Calls | In progress |  |  | Testing Extraordinary investment loss | Completed |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 0
2. Preparing End to End Scenarios and Test Cases Execution. | 55 | Samikruth Reddy | 35 | 2. Extraordinary investment loss test cases execution | In Progress |  |  | Automation | In Progress | [9 empty] | Manual execution | 0 | Total manual execution | 0
3. Automation | 20 | Vignesh | 20 | 3. Working on Environment setup & Automation | In Progress |  |  | Documentation for Extraordinary investment loss | In Progress | [9 empty] | Automation created | 0 | Total automation | 0
|  | Meenakshi | 3 |  |  |  |  | Test Artifact review | Yet to start | [9 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 23 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
1.Standup /Internal/Dev calls | 9 | Eswara Rao Kanakala | 10 | 1. Standup Calls/Dev Calls | In progress |  |  | Testing scenarios | In Progress | 23-Oct |  |  | No defect logged for the week | [5 empty] | Manual created | 86 | Total manual | 86
2. Preparing End to End Scenarios and Test Cases for new surveillance | 14 | Samikruth Reddy | 15 | 2. Extraordinary investment loss test cases execution | In Progress |  |  | Automation | In Progress | [9 empty] | Manual execution | 86 | Total manual execution | 86
3. Automation framework | 23 | Vignesh | 18 | 3. Working on Environment setup & Automation | In Progress |  |  | Documentation for Extraordinary investment loss | completed | [9 empty] | Automation created | 0 | Total automation | 0
|  | Meenakshi | 3 | 4. Test Artifact review | Completed | [13 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 30 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
1.Standup /Internal/Dev calls | 3 | Eswara Rao Kanakala | 5 | 1. Standup Calls/Dev Calls | In progress |  |  | Automation | In Progress |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 86
2. Preparing End to End Scenarios, Test Cases and documentation | 4 | Samikruth Reddy | 16 | 2. Extraordinary investment loss test cases execution | Completed |  |  | ITEM- C test Cases Execution &Documentation | Yet to Start | [9 empty] | Manual execution | 0 | Total manual execution | 86
3. Automation POC | 31 | Vignesh | 16 | 3. Working on Environment setup & Automation | In Progress | [13 empty] | Automation created | 0 | Total automation | 0
|  | Meenakshi | 1 | 4. ITEM- C Test Scenario and test Cases Preparation | Completed | [13 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
1.Standup /Internal/Dev calls | 3 | Eswara Rao Kanakala | 3 | 1. Standup Calls/Dev Calls | In Progress |  |  | Automation | In Progress |  |  |  | No defect logged for the week | [5 empty] | Manual created | 0 | Total manual | 86
2. Automation script development POC | 23.5 | Samikruth Reddy | 12 | 2. Working on Automation POC Scripts development | In Progress |  |  | ITEM- C test Cases Execution &Documentation | Yet to Start | [9 empty] | Manual execution | 0 | Total manual execution | 86
|  | Vignesh | 10.5 | [15 empty] | Automation created | 0 | Total automation | 0
|  | Meenakshi | 1 | [15 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
1.Standup /Internal/Dev calls | 13.5 | Eswara Rao Kanakala | 24 | 1. Standup Calls/Dev Calls | In Progress |  |  | Automation POC | In Progress |  |  |  | No defects logged for the week | [5 empty] | Manual created | 92 | Total manual | 178
2. Item-c Test execution and documentation | 43 | Samikruth Reddy | 25 | 2. Extraordinary investment loss test cases execution | Completed |  |  | ITEM- H test Cases Execution | In Progress | [9 empty] | Manual execution | 92 | Total manual execution | 178
3. Automation POC | 11 | Vignesh | 5.5 | 3. Item- C Testing and documentation is Completed | Completed | [13 empty] | Automation created | 0 | Total automation | 0
|  | Meenakshi | 4 | 4. ITEM- H Test Execution, User Manual preparation for CST portal | In Progress | [13 empty] | Automation execution | 0 | Total automation execution | 0
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
1.Standup /Internal/Dev calls | 10 | Eswara Rao Kanakala | 23 | 1. Standup Calls/Dev Calls | In Progress |  |  | Automation POC | In Progress | [9 empty] | Manual created | 184 | Total manual | 362
2. Item-E &H Test execution and documentation | 39 | Samikruth Reddy | 24 | 2. Extraordinary investment loss test cases execution | Completed |  |  | ITEM- H & E test Cases Documentation | In Progress | [9 empty] | Manual execution | 184 | Total manual execution | 362
|  | Meenakshi | 2 | 3. Item- C Testing and documentation is Completed | Completed | [13 empty] | Automation created | 0 | Total automation | 0
|  |  |  | 4. ITEM- E &H Test Execution | Completed | [13 empty] | Automation execution | 0 | Total automation execution | 0
|  |  |  | 5. User Manual preparation for CST portal | Completed | [13 empty] | Bugs Identified | 0 | Total bugs | 0
|  |  |  | 6. Test Execution Documentation for ITEM-E &H | In Progress | [15 empty] | Automation coverage % | 0

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments |  | Week Data Type | Week Count | Total Data Type | Total Count
1.Standup /Internal/Dev calls | 1 | Eswara Rao Kanakala | 16 | 1. Standup Calls/Dev Calls | In Progress |  |  | Automation POC | In Progress |  |  |  | No defects logged | [6 empty] | Manual created | 0 | Total manual | 362
2. Item-E &H Test execution and documentation | 40 | Samikruth Reddy | 24 | 2. Extraordinary investment loss test cases execution | Completed | [14 empty] | Manual execution | 0 | Total manual execution | 362
|  | Meenakshi | 1 | 3. Item- C Testing and documentation is Completed | Completed | [13 empty] | 20 | Automation created | 0 | Total automation | 0
|  |  |  | 4. ITEM- E &H Test Execution | Completed | [14 empty] | Automation execution | 0 | Total automation execution | 0
|  |  |  | 5. User Manual preparation for CST portal | Completed | [14 empty] | Bugs Identified | 0 | Total bugs | 0
|  |  |  | 6. Test Execution Documentation for ITEM-E &H | Completed | [16 empty] | Automation coverage % | 0

## 18 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
1.Standup /Internal/Dev calls | 2 | Meenakshi | 1 | 1. Automation of Item B surveillance E2E Scenarios | In Progress |  |  | Automation of Item C surveillance E2E Scenarios | In Progress |  |  |  | No defects logged | [5 empty] | Manual created | 0 | Total manual | 362
2. Item-B Test Automation E2E Scenarios | 16 | Samikruth Reddy | 17 |  |  |  |  | Automation of Item E surveillance E2E Scenarios | In Progress | [9 empty] | Manual execution | 0 | Total manual execution | 362
[8 empty] | Automation of Item B surveillance E2E Scenarios | In Progress | [9 empty] | Automation created | 86 | Total automation | 86
[19 empty] | Automation execution | 10 | Total automation execution | 10
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 26 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
Standup /Internal/Dev calls | 2 | Eswara Rao Kanakala | 2 | Automation of Item C surveillance E2E Scenarios | Completed |  |  | Automation of Item E surveillance E2E Scenarios | In Progress |  |  |  | No defects logged | [5 empty] | Manual created | 0 | Total manual | 362
E2 E Test Automation scenarios | 36 | Samikruth Reddy | 35 | Automation of Item E surveillance E2E Scenarios | Completed |  |  | Report configuration | Yet to start | [9 empty] | Manual execution | 0 | Total manual execution | 362
|  | Meenakshi | 1 | Automation of Item B surveillance E2E Scenarios | In progress |  |  | Documentation | Yet to start | [9 empty] | Automation created | 86 | Total automation | 172
[19 empty] | Automation execution | 25 | Total automation execution | 35
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0

## 2 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Week Data Type | Week Count | Total Data Type | Total Count
1. Test Automation E2E Scenarios | 5 | Samikruth Reddy | 5 | Automation of Item C surveillance E2E Scenarios | Completed |  |  | 1. Automation Scripts review | In Progress |  |  |  | No defects logged | [5 empty] | Manual created | 0 | Total manual | 362
|  |  |  | Automation of Item E surveillance E2E Scenarios | Completed | [13 empty] | Manual execution | 0 | Total manual execution | 362
|  |  |  | Automation of Item B surveillance E2E Scenarios | Completed | [13 empty] | Automation created | 0 | Total automation | 172
[19 empty] | Automation execution | 8 | Total automation execution | 43
[19 empty] | Bugs Identified | 0 | Total bugs | 0
[21 empty] | Automation coverage % | 0