## 19 Feb 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 2 | Johnson Benjamin | 12 | CFU document review | Completed |  |  | CFU bulk upload testing | In Progress | 27/02/2024 | [8 empty] | Manual test cases created | 0 | Manual test cases created | 20
CFU document review | 2 | Kathir | 12 | CFU bulk upload testing | In Progress | 27/02/2024 |  | CFU JIRA tickets testing | In Progress | 27/02/2024 | [8 empty] | Manual test cases conducted | 12 | Manual test cases conducted | 12
CFU bulk upload testing | 14 |  |  | CFU JIRA tickets testing | In Progress | 27/02/2024 |  | QA Test Evidence Preparation (Sprint 2) | YTS | 27/02/2024 | [8 empty] | Automation test cases created | 0 | Automation test cases created | 0
CFU JIRA tickets testing | 4 |  |  | Testcase Updation (Sprint 2) | In Progress | 27/02/2024 |  | Testcase Updation(Sprint 2) | In Progress | 27/02/2024 | [8 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
Testcase Updation | 2 | [17 empty] | Bugs identified | 0 | Bugs identified | 0
[21 empty] | Automation coverage | 0%

## 26 Feb 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 3 | Johnson Benjamin | 30 | CFU JIRA tickets testing (Bulk upload) | Completed |  | WMT – 3468, WMT – 3098, WMT – 3099, WMT – 3100, WMT – 3104, WMT – 3105, WMT – 3106. | CFU Sprint – 3 JIRA tickets testing | Yet To Start |  | Will start to test once, tickets are deployed. | [7 empty] | Manual test cases created | 30 | Manual test cases created | 50
CFU QA Evidence Document | 8 | Kathir | 31 | Bugs retesting | Completed |  | WMT – 3733, WMT 3736 | CFU Bugs retesting | Yet To Start |  | Will start to test once, bugs are fixed and deployed. | [7 empty] | Manual test cases conducted | 36 | Manual test cases conducted | 48
CFU JIRA tickets testing (Bulk upload) | 24 |  |  | Testcase Updation (Sprint 2) | Completed |  |  | Testcase Updation (Sprint 3) | In Progress | 15/03/2024 | [8 empty] | Automation test cases created | 0 | Automation test cases created | 0
Bug retesting | 15 |  |  | Testcase Updation (Sprint 3) | In Progress | 15/03/2024 | [12 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
Testcase Updation | 11 | [17 empty] | Bugs identified | 3 | Bugs identified | 3
[21 empty] | Automation coverage | 0%