## 19 Feb 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Client Calls& Dev Calls | 8 | Samikruth Reddy | 37 | Execution of below Jira tickets EV-2499,EV-2534 | Completed |  |  | Test analysis of EV-2503 | Yet to start |  |  |  | No defects raised for the week | [5 empty] | Manual test cases created | 32 | Manual test cases created | 32
Worked on EV-2499,EV-2534 (Testcase Creation, Execution,documentation | 47 | Eswara Rao | 18 | Daily Status Calls | In progress | [13 empty] | Manual test cases conducted | 32 | Manual test cases conducted | 32
[19 empty] | Automation test cases created | 0 | Automation test cases created | 0
[19 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[19 empty] | Bugs identified | 0 | Bugs identified | 0
[21 empty] | Automation coverage | 0%

## 26 Feb 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Standup /Internal/Dev calls | 10 | Samikruth Reddy | 34 | 1.Daily Status Calls | In progress |  |  | 1.Test execution of Jira ticket EV-2739 | In progress |  |  |  | No defects raised for the week | [5 empty] | Manual test cases created | 29 | Manual test cases created | 61
Executed the below Jira tickets EV-2712,EV-2717 Jira ticket EV-2739 -Execution in progress | 47 | Eswara Rao | 23 | 2.Execution of below Jira tickets EV-2712,EV-2717 | Completed |  |  | 2. Execution of below Jira tickets EV-2731,EV-2732,EV-2739,EV-2740 | Yet To start | [9 empty] | Manual test cases conducted | 33 | Manual test cases conducted | 61
|  |  |  | 3. Test execution of Jira ticket EV-2739 | In progress | [13 empty] | Automation test cases created |  | Automation test cases created | 0
[19 empty] | Automation test cases processed |  | Automation test cases processed | 0
[19 empty] | Bugs identified |  | Bugs identified | 0
[21 empty] | Automation coverage | 0%