## 2 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 7 | Johnson Benjamin | 53 | Bug Retesting | In-progress. |  | 3 issues raised, 5 closed. | Swift payment testing | In-progress. | 2023-10-10 |  | 177 | If we update a ticket in Treasury Reprocessing screen and click on Approve/Recommend for Rejection button, we are getting error message | High | Closed | Nikhil Garg |  |  | Manual test cases created | 0 | Manual test cases created | 316
Bug Retesting | 61.5 | Kathir | 53.5 |  |  |  | 2 re-open | UAT log fixes / JIRA Tickets | In-progress. |  | 9 in progress, 6 Jira Closed, 3 Jira re-open | 178 | If we open a ticket from "In Setup Review" and directly click on Final Review tab, error message is displayed, the Error message is not displayed if we navigate using the Next button in the first tab. | Low | Open | Nikhil Garg |  | To be tested once Dev provides fix | Manual test cases conducted | 233 | Manual test cases conducted | 3687
Reprocessing | 24 | Vignesh | 6 | Reprocessing | Completed. |  |  | Bug Retesting | In Progress. |  | 10 in progress | 179 | If the amount is too big the search is not working, if the amount is small it is working as expected. It is the same for other grids also | Normal | Closed | Garg, Nikhil |  |  | Automation test cases created | 0 | Automation test cases created | 0
Swift Payment testing | 32 | Kalyan Gopi | 12 | Swift payment testing | In-progress. | 2023-10-10 | [5 empty] | 180 | In PPT it is mentioned that only Processor and Approver can see this page | High | Closed | Garg, Nikhil |  |  | Automation test cases processed | 0 | Automation test cases processed | 0
|  |  |  | UAT log fixes / JIRA Tickets | In-progress. | [13 empty] | Bugs identified | 4 | Bugs identified | 181
[21 empty] | Automation coverage | 0%

## 9 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 7 | Johnson Benjamin | 65 | Bug Retesting | Completed. |  | 1 issue raised, 13 closed. | High Level Regression on Step 2 process. | In-progress. | 16-10-2023 |  |  | No defect logged for the week. | [5 empty] | Manual test cases created | 0 | Manual test cases created | 316
Bug Retesting | 73 | Kathir | 63.5 | Reprocessing | Completed. |  |  | Detailed Regression on Step 2 process | Yet To Start | 20-10-2023 | [8 empty] | Manual test cases conducted | 200 | Manual test cases conducted | 3887
Swift Payment testing | 51.5 | Vignesh | 2 | Swift payment testing | Completed. | [13 empty] | Automation test cases created | 0 | Automation test cases created | 0
High Level Regression | 17 | Kalyan Gopi | 18 | UAT log fixes / JIRA Tickets | Completed. |  | 13 closed | [11 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[19 empty] | Bugs identified | 0 | Bugs identified | 181
[21 empty] | Automation coverage | 0%

## 16 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 3 | Johnson Benjamin | 46 | Testing the Audit changes from dev for Nov 2nd release | Completed |  |  | Testing the Audit changes from dev. | Yet to Start |  | Will test once the dev team provides it | 181 | Suggestion: By default values are displaying when the ticket is reprocessed for the second time. | Low | Open |  |  |  | Manual test cases created | 0 | Manual test cases created | 316
Regression Testing | 107 | Kathir | 46.6 | Test cases updating for step 2. | In progress |  |  | Test cases updating for step 2 | In progress | [9 empty] | Manual test cases conducted | 80 | Manual test cases conducted | 3967
|  | Vignesh | 2.5 |  |  |  |  | UAT logs | Yet to Start |  | Will test once t | [7 empty] | Automation test cases created | 0 | Automation test cases created | 0
|  | Kalyan Gopi | 15 | [15 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[19 empty] | Bugs identified | 1 | Bugs identified | 182
[21 empty] | Automation coverage | 0%

## 23 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 3 | Johnson Benjamin | 20 | Testing the Audit changes from dev for Nov 2nd release | Completed |  |  | Testing the Audit changes from dev for Nov 2nd release | Completed |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 84 | Manual test cases created | 400
Audit Enhancement Testing | 57 | Kathir | 32 | Test cases updating for step 2. | In progress |  |  | Test cases updating for step 2 | In progress | [9 empty] | Manual test cases conducted | 90 | Manual test cases conducted | 4057
|  | Vignesh | 2 |  |  |  |  | UAT logs | Yet to Start |  | We will test once the dev team provides it. | [7 empty] | Automation test cases created | 0 | Automation test cases created | 0
|  | Kalyan | 6 | [15 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[19 empty] | Bugs identified | 0 | Bugs identified | 182
[21 empty] | Automation coverage | 0%

## 30 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 1 | Johnson Benjamin | 41 | Testing the Audit changes from dev for Nov 2nd release | Completed |  |  | Test cases updating for Step 2 | In progress |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 400
New Changes Nov2 Release | 20 | Kathir | 41 | Test cases updating for step 2. | In progress |  |  | Additional Approval process in Call-back. | Yet to Start |  | We will test once the dev team provides it. | [7 empty] | Manual test cases conducted | 135 | Manual test cases conducted | 4192
Test case updating for step 2 process. | 63 | Vignesh | 2 |  |  |  |  | Warning box in both the Business Approver and Treasury Approver for payments over $1M+ or $50K. | Yet to Start |  | We will test once the dev team provides it. | [7 empty] | Automation test cases created | 0 | Automation test cases created | 0
[19 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[19 empty] | Bugs identified | 0 | Bugs identified | 182
[21 empty] | Automation coverage | 0%

## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 3 | Johnson Benjamin | 24 | Solution Update testing | In progress | 14/11/2023 |  | Test cases updating for Step 2 | In progress |  |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 400
Solution Update testing | 33 | Kathir | 42 | Test cases updating for step 2. | In progress |  |  | Solution Update testing | In progress | 14/11/2023 | [8 empty] | Manual test cases conducted | 120 | Manual test cases conducted | 4312
Test case updation for step 2 process. | 31 | Vignesh | 1 |  |  |  |  | Additional Approval process in Call-back. | Yet to Start |  | We will test once the dev team provides it. | [7 empty] | Automation test cases created | 0 | Automation test cases created | 0
[8 empty] | Making Beneficiary Address and City for HSBC bank accounts. | Yet to start |  | We will test once the dev team provides it. | [7 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[8 empty] | Warning box in both the Business Approver and Treasury Approver for payments over $1M+ or $50K. | Yet to Start |  | We will test once the dev team provides it. | [7 empty] | Bugs identified | 0 | Bugs identified | 182
[21 empty] | Automation coverage | 0%

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 3 | Johnson Benjamin | 34 | Solution Upgrade testing | In progress | 20/11/2023 | Testing completed; Issues assigned to Dev. | Test cases update for Step 2 | In progress |  |  | 182 | Requestor is able to submit a payment request without entering Financial approver. | High | Closed | Nikhil Garg |  |  | Manual test cases created | 0 | Manual test cases created | 400
Solution Update testing | 16 | Kathir | 34 | Audit Enhancement testing - Warning box in both the Business Approver and Treasury Approver for payments over $1M+ | Completed |  |  | Solution Upgrade testing | In progress | 20/11/2023 |  | 183 | Value Date is accepting Sat and Sun in Payment Failed - Treasury Reprocessing Status | Normal | New | Garg, Nikhil |  |  | Manual test cases conducted | 230 | Manual test cases conducted | 4542
Audit Enhancement testing | 22 | Vignesh | 1 | Testing Edit existing template and Revise payment template. | In progress | 20/11/2023 |  | Testing Edit existing template and Revise payment template. | In progress | 20/11/2023 |  | 184 | Edit an Existing template not working if SWIFT payment successful | High | New | Garg, Nikhil |  |  | Automation test cases created | 0 | Automation test cases created | 0
Testing Edit and Revise payment templates | 28 |  |  | Test cases updating for step 2. | In progress |  |  | Value date should not be weekend. | In progress | 21/11/2023 |  | 185 | Validation message should not be displayed when we enter amount as “-1” In the 2nd validation the message should be “Amount should be between 1 and 100 trillion”, attached screenshot | Normal | New | Garg, Nikhil |  |  | Automation test cases processed | 0 | Automation test cases processed | 0
[8 empty] | Select all check box in Payment staging interface | In progress | 20/11/2023 |  | 186 | When Age is given in two or three digit issue is still occurring. Also Age field should not be less than 0, currently when decremental button is clicked from 0 negative values are displayed. | Normal | New | Garg, Nikhil |  |  | Bugs identified | 8 | Bugs identified | 190
[8 empty] | Max length Validation message In Amount field. | In progress | 21/11/2023 |  | 187 | Payment tag type should not be displayed in green color, attached screenshot of New version and old version. | Normal | New | Garg, Nikhil |  |  |  |  | Automation coverage | 0%
[8 empty] | Additional Approval process in Call-back. | Yet to Start | 23/11/2023 | Testing will be started once deployment is done. | 188 | Calendar icon issue | Normal | New | Garg, Nikhil
[12 empty] | 189 | Age field issue. | Normal | New | Garg, Nikhil

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 5 | Johnson Benjamin | 51 | Solution Upgrade testing | In progress | 28/11/2023 |  | Test cases update for Step 2 | In progress |  |  | 190 | Calendar icon issue. | Normal | New | Garg, Nikhil |  |  | Manual test cases created | 48 | Manual test cases created | 448
Solution Update testing | 11 | Kathir | 51 | Audit Enhancement testing - Warning box in both the Business Approver and Treasury Approver for payments over $1M+ | In progress | 27/11/2023 |  | Solution Upgrade testing | In progress | 28/11/2023 | [8 empty] | Manual test cases conducted | 163 | Manual test cases conducted | 4705
Audit Enhancement testing | 70.5 | Vignesh | 5.5 | Value date should not be weekend. | Completed |  |  | Audit Enhancement testing - Warning box in both the Business Approver and Treasury Approver for payments over $1M+ | Completed | [9 empty] | Automation test cases created | 0 | Automation test cases created | 0
Testing Edit and Revise payment templates | 35 | Kalyan Gopi | 35 | Testing Edit existing template and Revise payment template. | In progress | 27/11/2023 |  | JIRA tickets testing. | In progress | 28/11/2023 | [8 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
JIRA tickets | 21 |  |  | Audit Enhancement testing - Additional Approval process in Call-back Verification. | In progress | 27/11/2023 |  | Testing Edit existing template and Revise payment template. | Completed | [9 empty] | Bugs identified | 1 | Bugs identified | 191
|  |  |  | JIRA tickets testing. | In progress | 28/11/2023 |  | Audit Enhancement testing - Additional Approval process in Call-back Verification. | Completed | [11 empty] | Automation coverage | 0%
|  |  |  | Max length Validation message In Amount field. | Completed
|  |  |  | Added Required to label for Beneficiary Address and City in Step 1 | Completed
|  |  |  | Test cases updating for step 2. | In progress

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 2 | Johnson Benjamin | 43 | Solution Upgrade testing. | Completed |  |  | Test cases update for Step 2 | In progress |  |  | 191 | User has Treasury processor and Call back verifier and user has not submitted call back verifier and approving as Treasury processor. | High | Closed | Nikhil Garg |  |  | Manual test cases created | 36 | Manual test cases created | 484
Solution Update testing | 4 | Kathir | 43 | JIRA tickets testing. | Completed |  |  | Role based testing in Grids. | In progress |  |  | 192 | Rush mail is triggered when, fund approver approves from Teams or Emails | High | Open | Nikhil Garg |  |  | Manual test cases conducted | 140 | Manual test cases conducted | 4845
Audit Enhancement testing | 28 | Vignesh | 4.5 | Audit Enhancement testing – Call back verification. | Completed |  |  | Led - User Address update. | Yet to Start |  | Will be tested, once it is deployed. | [7 empty] | Automation test cases created | 0 | Automation test cases created | 0
Testing Edit and Revise payment templates | 16.5 | Kalyan Gopi | 4 | Edit Existing and Revise template testing. | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
Role based testing | 30 |  |  | Bugs retesting. | Completed. | [13 empty] | Bugs identified | 1 | Bugs identified | 192
JIRA tickets | 14 |  |  | Role based testing in Grids. | In progress. | [15 empty] | Automation coverage | 0%
|  |  |  | Test cases updating for step 2. | In progress
|  |  |  | Added Required to label for Beneficiary Address and City in Step 1 | Completed
|  |  |  | Test cases updating for step 2. | In progress

## 4 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 2 | Johnson Benjamin | 40 | JIRA tickets testing. | Completed |  |  | Test cases update for Step 2. | In progress |  |  | 193 | LED Address is getting updated for Status: Payment Sent for SWIFT Processing | Medium | Open | Nikhil Garg |  |  | Manual test cases created | 56 | Manual test cases created | 540
Testcase updation | 12 | Kathir | 32 | Role based testing. | In progress. | 15-12-2023 |  | Role based testing. | In progress | 15-12-2023 | [8 empty] | Manual test cases conducted | 120 | Manual test cases conducted | 4965
Role based testing | 26 | Vignesh | 1.5 | Led - User Address update. | In progress | 2023-12-12 |  | Led - User Address update. | In progress | 2023-12-12 | [8 empty] | Automation test cases created | 0 | Automation test cases created | 0
Led – Address change testing | 29.5 |  |  | Test cases updating for step 2. | In progress | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
Bug retesting | 4 | [17 empty] | Bugs identified | 1 | Bugs identified | 193
[21 empty] | Automation coverage | 0%

## 11 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 5 | Johnson Benjamin | 32 | Role based testing. | In progress. |  |  | Test cases update for Step 2. | In progress | 22/12/2023 |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 30 | Manual test cases created | 570
Testcase updating | 12 | Kathir | 23 | Led - User Address update. | In progress |  | One open ticket | Role based testing. | In progress | [9 empty] | Manual test cases conducted | 110 | Manual test cases conducted | 5075
Led – Address change testing | 36 | Vignesh | 2 | Test cases updating for step 2. | In progress | 22/12/2023 |  | Led - User Address update. | In progress |  | One open ticket, waiting for Dev to fix the issue | [7 empty] | Automation test cases created | 0 | Automation test cases created | 0
Bug retesting | 4 | [6 empty] | POP (Purpose of Payment) | Yet to start |  | Will start once deployment is done | [7 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[19 empty] | Bugs identified | 0 | Bugs identified | 193
[21 empty] | Automation coverage | 0%

## 18 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 2 | Johnson Benjamin | 14 | Role based testing. | In progress. | 29/12/2023 |  | Test cases update for Step 2. | In progress | 29/12/2023 |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 570
Testcase updating | 10 | Kathir | 30 | Led - User Address update. | In progress |  | One open ticket | Role based testing. | In progress | 29/12/2023 | [8 empty] | Manual test cases conducted | 0 | Manual test cases conducted | 5075
Led – Address change testing | 17 | Vignesh | 2.5 | Call back verifier testing | Completed |  |  | Led - User Address update. | In progress |  | One open ticket, waiting for Dev to fix the issue | [7 empty] | Automation test cases created | 0 | Automation test cases created | 0
Call back verifier testing | 17.5 |  |  | Test cases updating for step 2. | In progress | 29/12/2023 |  | Call back verifier testing | Completed | [9 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[8 empty] | POP (Purpose of Payment) | Yet to start |  | Testing to be initiated on Jan 2 | [7 empty] | Bugs identified | 0 | Bugs identified | 193
[21 empty] | Automation coverage | 0%

## 26 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 2 | Johnson Benjamin | 28 | Role based testing. | In progress. | 12/01/2024 |  | Test cases update for Step 2. | In progress | 2024-12-01 |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 16 | Manual test cases created | 586
Testcase updating | 12 | Kathir | 28 | Led - User Address update (Regression). | In progress | 05/01/2024 |  | Role based testing. | In progress | 2024-12-01 | [8 empty] | Manual test cases conducted | 120 | Manual test cases conducted | 5195
Led – Address change testing | 17 | Vignesh | 2 | POP testing | In progress | 2024-08-01 |  | Bug retesting | In progress | 2024-08-01 | [8 empty] | Automation test cases created | 0 | Automation test cases created | 0
POP testing | 10 |  |  | Bug retesting | In progress | 2024-08-01 |  | Led - User Address update (Regression). | In progress | 2024-05-01 | [8 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
Bugs retesting | 17 |  |  | Test cases updating for step 2. | In progress | 2024-12-01 |  | Call back verifier – Regression | In progress | 2024-05-01 | [8 empty] | Bugs identified | 0 | Bugs identified | 193
[8 empty] | POP (Purpose of Payment) | In progress | 2024-08-01 | [10 empty] | Automation coverage | 0%

## 2 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 2 | Johnson Benjamin | 32 | Led - User Address update (Regression). | In progress | 2024-09-01 |  | Test cases update for Step 2. | In progress | 2024-12-01 |  | WMT-2975 | If only FFC Account Name is provided in OT Step 1, it is not added to SWIFT file. | Medium | New | Swikriti |  |  | Manual test cases created | 0 | Manual test cases created | 586
Led – Address change testing | 5 | Kathir | 32 | POP testing - (Purpose of Payment) | In progress | 2024-09-01 |  | Role based testing. | In progress | 2024-12-01 | [8 empty] | Manual test cases conducted | 180 | Manual test cases conducted | 5375
POP testing | 57 | Vignesh | 2 | Jira tickets/Bug retesting | In progress | 2024-12-01 |  | Jira tickets/Bug retesting | In progress | 2024-12-01 | [8 empty] | Automation test cases created | 0 | Automation test cases created | 0
Bugs retesting | 2 | [6 empty] | Led - User Address update (Regression). | In progress | 2024-09-01 | [8 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[8 empty] | Call back verifier – Regression | In progress | 2024-09-01 | [8 empty] | Bugs identified | 1 | Bugs identified | 194
[8 empty] | POP testing - (Purpose of Payment) | In progress | 2024-09-01 | [10 empty] | Automation coverage | 0%

## 8 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 2 | Johnson Benjamin | 45 | Led - User Address update (Regression). | Completed |  |  | Test cases update for Step 2. | In progress | 19/01/2024 |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 586
Led – Address change testing | 33 | Kathir | 45 | POP testing - (Purpose of Payment) | Completed |  |  | Role based testing. | In progress | 19/01/2024 | [8 empty] | Manual test cases conducted | 160 | Manual test cases conducted | 5535
POP testing | 41.5 | Vignesh | 2.5 | Call back verification (Regression) | Completed |  |  | Jira tickets/Bug retesting | In progress | 16/01/2024 | [8 empty] | Automation test cases created | 0 | Automation test cases created | 0
Call back verification | 12 |  |  | Jira tickets/Bug retesting | In progress | 16/01/2024 | [12 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
Bug retesting | 4 | [17 empty] | Bugs identified | 0 | Bugs identified | 194
[21 empty] | Automation coverage | 0%

## 15 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 1 | Johnson Benjamin | 14 | Test cases update for Step 2. | Completed |  |  | Role based testing. | In progress | 2024-01-25 |  |  | No defect logged for the week | [5 empty] | Manual test cases created | 50 | Manual test cases created | 636
Test cases update for Step 2. | 24 | Kathir | 22 | Sanity test for Jan 22 release | Completed | [13 empty] | Manual test cases conducted | 90 | Manual test cases conducted | 5625
POP testing | 3 | Vignesh | 2 | Jira tickets/Bug retesting | Completed | [13 empty] | Automation test cases created | 0 | Automation test cases created | 0
Jira ticket/Bug retesting | 10 | [17 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[19 empty] | Bugs identified | 0 | Bugs identified | 194
[21 empty] | Automation coverage | 0%

## 22 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 1 | Johnson Benjamin | 29 | CFU document review | Completed |  |  | Jira/Bug retesting | In progress | 2024-02-01 |  | WMT-3230 | Warning message is displayed as Swift BIC is not available in LED | Medium | Open | Lipi |  |  | Manual test cases created | 0 | Manual test cases created | 636
Role based testing | 55 | Kathir | 29 | Role based testing. | In progress | 29/01/2024 |  | Role based testing. | In progress | 29/01/2024 |  | WMT- 3232 | User is able to edit Calendar in Read Only screens | Medium | Open | Lipi |  |  | Manual test cases conducted | 110 | Manual test cases conducted | 5735
CFU document review | 4 | Vignesh | 2 |  |  |  |  | CFU testing | Yet to Start |  | Will start the testing once it is deployed. | WMT - 3275 | User is able to Submit a ticket as Requestor and Callback Verifier | Medium | Open | Lipi |  |  | Automation test cases created | 0 | Automation test cases created | 0
[19 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[19 empty] | Bugs identified | 3 | Bugs identified | 197
[21 empty] | Automation coverage | 0%

## 29 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 2 | Johnson Benjamin | 20 | Jira/Bug retesting | Completed |  |  | CFU document review | In progress | 2024-02-09 |  |  | No defects logged for the week | [5 empty] | Manual test cases created |  | Manual test cases created | 636
Role based Testing | 9 | Kathir | 12 | CFU document review | In progress | 2024-02-09 |  | Test case Updation | In progress | 2024-02-09 | [8 empty] | Manual test cases conducted | 60 | Manual test cases conducted | 5795
Test cases updation | 6 | Vignesh | 1.5 | Test case Updation | In progress | 2024-02-09 |  | CFU Testing (Download Blank Template/Excel Upload) | Yet to Start |  | Will start the testing once it is deployed. | [7 empty] | Automation test cases created | 0 | Automation test cases created | 0
Bug retesting | 14.5 |  |  | Role based testing. | Completed | [13 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
CFU document review | 2 | [17 empty] | Bugs identified | 0 | Bugs identified | 197
[21 empty] | Automation coverage | 0%

## 5 Feb 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 1 | Johnson Benjamin | 12 | Jira/Bug retesting | Completed |  |  | CFU Testing | YTS |  | To be started once deployment is done. | [7 empty] | Manual test cases created | 0 | Manual test cases created | 636
Bug retesting | 17.5 | Kathir | 1.5 | CFU document review | Completed |  |  | Test case Updation | In progress | 2024-02-23 | [8 empty] | Manual test cases conducted | 30 | Manual test cases conducted | 5825
CFU Testing (Download Blank Template/Excel Upload) | 7 | Vignesh | 12 | CFU Testing (Download Blank Template/ Export to Excel) | Completed | [13 empty] | Automation test cases created | 0 | Automation test cases created | 0
|  |  |  | Test case Updation | In progress | 2024-02-23 | [12 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[19 empty] | Bugs identified | 0 | Bugs identified | 197
[21 empty] | Automation coverage | 0%

## 12 Feb 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
Meetings | 0 | Johnson Benjamin | 0.5 | Documentation(QA Evidence) | Completed |  |  | CFU Testing (Excel upload) | YTS |  | To be started once deployment is done. | [7 empty] | Manual test cases created | 0 | Manual test cases created | 636
Documentation(QA Evidence) | 0.5 | Kathir | 0 | [15 empty] | Manual test cases conducted | 0 | Manual test cases conducted | 5825
|  | Vignesh | 0 | [15 empty] | Automation test cases created | 0 | Automation test cases created | 0
[19 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[19 empty] | Bugs identified | 0 | Bugs identified | 197
[21 empty] | Automation coverage | 0%

## 19 Feb 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
|  | Johnson Benjamin | [16 empty] | Manual test cases created | 0 | Manual test cases created | 636
|  | Kathir | [16 empty] | Manual test cases conducted | 20 | Manual test cases conducted | 5845
|  | Vignesh | [16 empty] | Automation test cases created | 0 | Automation test cases created | 0
[19 empty] | Automation test cases processed | 0 | Automation test cases processed | 0
[19 empty] | Bugs identified | 0 | Bugs identified | 197
[21 empty] | Automation coverage | 0%