## 2 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count.. | backup | Till2023
vEMS:Daily StandUp - Internal | 4.5 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 73 | 73
Test Case design/ Defect Tracker Update/ Jira Update | 1.5 | Saravanan munikrishnan | 8.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Manual test cases conducted | 5 | Manual test cases conducted | 8113 | 613 | 7500
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation test cases created | 0 | Automation test cases created | 73 | 73
vEMS: AR/AP Dashboard | 2.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation test cases processed | 16 | Automation test cases processed | 4736 | 816 | 3920
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 3.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs identified | 0 | Bugs identified | 158 | 41 | 117
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 3.5 | [19 empty] | Automation coverage | 100%
vEMS: Ad-hoc testing request | 5.5
vEMS: WOR-512 (Refund Status as paid) | 1.5
vEMS: Automation Script Enhancement | 6.5
vEMS: Automation(Multi SR & Power Bi) | 1

## 9 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 4.5 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 73
Test Case design/ Defect Tracker Update/ Jira Update | 1.5 | Saravanan munikrishnan | 8.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Manual test cases conducted | 6 | Manual test cases conducted | 8119
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation test cases created | 0 | Automation test cases created | 73
vEMS: AR/AP Dashboard | 2.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation test cases processed | 18 | Automation test cases processed | 4754
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 3.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs identified | 0 | Bugs identified | 158
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 3.5 | [19 empty] | Automation coverage | 100%
vEMS: Ad-hoc testing request | 5.5
vEMS: WOR-512 (Refund Status as paid) | 1.5
vEMS: Automation Script Enhancement | 6.5
vEMS: Automation(Multi SR & Power Bi) | 1

## 16 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 4.5 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 73
Test Case design/ Defect Tracker Update/ Jira Update | 1.5 | Saravanan munikrishnan | 8.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Manual test cases conducted | 7 | Manual test cases conducted | 8126
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation test cases created | 0 | Automation test cases created | 73
vEMS: AR/AP Dashboard | 2.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation test cases processed | 20 | Automation test cases processed | 4774
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 3.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs identified | 0 | Bugs identified | 158
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 3.5 | [19 empty] | Automation coverage | 100%
vEMS: Ad-hoc testing request | 5.5
vEMS: WOR-512 (Refund Status as paid) | 1.5
vEMS: Automation Script Enhancement | 6.5
vEMS: Automation(Multi SR & Power Bi) | 1

## 23 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 4.5 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 73
Test Case design/ Defect Tracker Update/ Jira Update | 1.5 | Saravanan munikrishnan | 8.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Manual test cases conducted | 6 | Manual test cases conducted | 8132
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation test cases created | 0 | Automation test cases created | 73
vEMS: AR/AP Dashboard | 2.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation test cases processed | 18 | Automation test cases processed | 4792
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 3.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs identified | 0 | Bugs identified | 158
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 3.5 | [19 empty] | Automation coverage | 100%
vEMS: Ad-hoc testing request | 5.5
vEMS: WOR-512 (Refund Status as paid) | 1.5
vEMS: Automation Script Enhancement | 6.5
vEMS: Automation(Multi SR & Power Bi) | 1

## 30 Oct 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 4.5 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 73
Test Case design/ Defect Tracker Update/ Jira Update | 1.5 | Saravanan munikrishnan | 8.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Manual test cases conducted | 6 | Manual test cases conducted | 8138
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation test cases created | 0 | Automation test cases created | 73
vEMS: AR/AP Dashboard | 2.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Automation test cases processed | 14 | Automation test cases processed | 4806
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 3.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Bugs identified | 0 | Bugs identified | 158
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 3.5 | [19 empty] | Automation coverage | 100%
vEMS: Ad-hoc testing request | 5.5
vEMS: WOR-512 (Refund Status as paid) | 1.5
vEMS: Automation Script Enhancement | 6.5
vEMS: Automation(Multi SR & Power Bi) | 1

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 3 | Pramod rayate | 8 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 73
Test Case design/ Defect Tracker Update/ Jira Update | 1 | Saravanan munikrishnan | 8.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Functionality working as expected, Pending to check in FPNA | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Will check FPNA and start Full regression | [7 empty] | Manual test cases conducted | 7 | Manual test cases conducted | 8150
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 14 | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Functionality working as expected, Pending to check in FPNA | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Will check FPNA and start Full regression | [7 empty] | Automation test cases created | 0 | Automation test cases created | 73
vEMS: AR/AP Dashboard | 14 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | [7 empty] | Automation test cases processed | 16 | Automation test cases processed | 4834
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 2 | [5 empty] | creating fresh data for validation |  |  |  | Prepare data and put more validation | [7 empty] | Bugs identified | 0 | Bugs identified | 158
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 2 |  |  | AR/AP Dashboard | In Progress | 2023-11-24 | FIN Reports: Worked on Requirement gathering & Access | AR/AP Dashboard | In Progress | 2023-11-24 | FIN Reports: Get data & Access for vEMS | [9 empty] | Automation coverage | 100%
vEMS: Automation Script Enhancement | 3 | [5 empty] | Worked on Table design, able to receive data for Workday |  |  |  | Work on feeding data in dashboard
vEMS: Automation(Multi SR & Power Bi) | 4.5

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | 2023-12-05 | started Full regression in OAK-2 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 73
Test Case design/ Defect Tracker Update/ Jira Update | 1 | Saravanan munikrishnan | 19.5 | WOR-823, 824: Refund to use Bank Rate | Completed | 2023-11-21 | Functionality working as expected, Issue found in FPNA | WOR-882: Refund to use Bank Rate | In Progress | 2023-12-05 | Continue Full regression in OAK-2 and OAK-1 | [7 empty] | Manual test cases conducted | 4 | Manual test cases conducted | 8154
vEMS: Triage / Review Meeting - Testing and Defects | 2 | Vignesh dhakshnamoorthy | 8 | WOR-817, 818: ADJ to use Bank Rate | Completed | 2023-11-21 | Functionality working as expected, Issue found in FPNA | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | [7 empty] | Automation test cases created | 0 | Automation test cases created | 73
vEMS: AR/AP Dashboard | 8 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress |  |  |  | Prepare data and put more validation | [7 empty] | Automation test cases processed | 8 | Automation test cases processed | 4842
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 2 | [5 empty] | creating fresh data for validation | AR/AP Dashboard | In Progress | 2023-12-01 | FIN Reports: Get data & Access for vEMS | [7 empty] | Bugs identified | 0 | Bugs identified | 158
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 2 |  |  | AR/AP Dashboard | In Progress | 2023-12-01 | FIN Reports: Worked on Requirement gathering & Access |  |  |  | Waiting for data from vEMS & Navision | [9 empty] | Automation coverage | 100%
vEMS: WOR-882 (Refund to use Bank rate) | 4 | [5 empty] | Table design completed, waiting for vEMS & Navision
vEMS: Automation Script Enhancement | 5
vEMS: Automation(Multi SR & Power Bi) | 18.5

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 2.5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | 2023-12-05 | started Full regression in OAK-2, Faced issue in INT0209 & INT0210a | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 73
Test Case design/ Defect Tracker Update/ Jira Update | 2.5 | Saravanan munikrishnan | 17 | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress. created fresh data for validation | WOR-882: Refund to use Bank Rate | Blocked | TBD | Waiting for fix on issue with INT0209 & INT0210a | [7 empty] | Manual test cases conducted | 4 | Manual test cases conducted | 8158
vEMS: Triage / Review Meeting - Testing and Defects | 1.5 | Vignesh dhakshnamoorthy | 8 | AR/AP Dashboard | In Progress | 2023-12-05 | FIN Reports Phase-1: Ready to consume Prod data | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress created fresh data for validation | [7 empty] | Automation test cases created | 0 | Automation test cases created | 73
vEMS: AR/AP Dashboard | 8 | [6 empty] | AR/AP Dashboard | In Progress | 2023-12-05 | FIN Reports Phase-1: Ready to consume Prod data | [7 empty] | Automation test cases processed | 10 | Automation test cases processed | 4852
vEMS: WOR-882 (Refund to use Bank rate) | 3.5 | [17 empty] | Bugs identified | 0 | Bugs identified | 158
vEMS: Automation Script Enhancement | 5 | [19 empty] | Automation coverage | 100%
vEMS: Automation(Multi SR & Power Bi) | 22

## 4 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 3.5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | TBD | Found issue in INT0209 & INT0210a, waiting for fix | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_288 | ER Line count was complete mismatch with Finsmart | Low | Closed | Vikas |  |  | Manual test cases created | 20 | Manual test cases created | 93
Test Case design/ Defect Tracker Update/ Jira Update | 1.5 | Saravanan munikrishnan | 2 | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress Preparing additional validation list | WOR-882: Refund to use Bank Rate | Blocked | TBD | Found issue in INT0209 & INT0210a, waiting for fix | [7 empty] | Manual test cases conducted | 5 | Manual test cases conducted | 8163
vEMS: Triage / Review Meeting - Testing and Defects | 2 | Vignesh dhakshnamoorthy | 5 | AR/AP Dashboard | In Progress | 2023-12-11 | FIN Reports Phase-1: Ready to consume Prod data | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress Preparing additional validation list | [7 empty] | Automation test cases created | 10 | Automation test cases created | 83
vEMS: AR/AP Dashboard | 5 | [6 empty] | AR/AP Dashboard | In Progress | 2023-12-11 | FIN Reports Phase-1: Ready to consume Prod data. will work on vEMS data at FTP | [7 empty] | Automation test cases processed | 20 | Automation test cases processed | 4872
vEMS: WOR-882 (Refund to use Bank rate) | 4.5 | [17 empty] | Bugs identified | 1 | Bugs identified | 159
vEMS: Ad-hoc business requests | 3 | [19 empty] | Automation coverage | 89.25%
vEMS: Automation(Multi SR & Power Bi) | 7.5

## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 5 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 73
Test Case design/ Defect Tracker Update/ Jira Update | 2.5 | Saravanan munikrishnan | 5 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Regression Testing will be done, once issue fixed | [7 empty] | Manual test cases conducted | 5 | Manual test cases conducted | 8143
vEMS: Triage / Review Meeting - Testing and Defects | 2.5 | Vignesh dhakshnamoorthy | 9.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Requirement got changed, waiting for new changes | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Testing will be done OAK-2, once issue fixed | [7 empty] | Automation test cases created | 0 | Automation test cases created | 73
vEMS: AR/AP Dashboard | 9.5 |  |  | WD-Regression Suite | Blocked | TBD | Phase-5:- Power Bi validation: Blocked due to INT101D issue | WD-Regression Suite | Blocked | TBD | Phase-5- Power Bi: Blocked by INT101D issue | [7 empty] | Automation test cases processed | 12 | Automation test cases processed | 4818
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 2 |  |  | AR/AP Dashboard | In Progress | 2023-11-21 | FIN Reports: Worked on Requirement gathering & Access Working on Table design | AR/AP Dashboard | In Progress | 2023-11-21 | FIN Reports: Work on Table design and waiting for Data from vEMS | [7 empty] | Bugs identified | 0 | Bugs identified | 158
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 3 | [19 empty] | Automation coverage | 100%
vEMS: Automation Script Enhancement | 2.5
vEMS: Automation(Multi SR & Power Bi) | 7.5

## 11 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 3.5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | TBD | Found issue in INT0209 & INT0210a, waiting for fix | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_289 | Missing Fx journal(Boomerang) entries in FPNA report | Medium | Open | William |  |  | Manual test cases created | 12 | Manual test cases created | 105
Test Case design/ Defect Tracker Update/ Jira Update | 2 | Saravanan munikrishnan | 14.5 | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress Preparing additional validation list | WOR-882: Refund to use Bank Rate | Blocked | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | Observation_290 | CPAY not populating at Allocation Key in FPNA report | Medium | Open | William |  |  | Manual test cases conducted | 3 | Manual test cases conducted | 8166
vEMS: Triage / Review Meeting - Testing and Defects | 2 | Vignesh dhakshnamoorthy | 5 | AR/AP Dashboard | In Progress | 2023-12-18 | FIN Reports Phase-1: Completed Analyzed schedule time to run scripts for WD & vEMS | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress Review additional validation list with William | [7 empty] | Automation test cases created | 20 | Automation test cases created | 103
vEMS: AR/AP Dashboard | 6 | [6 empty] | AR/AP Dashboard | In Progress | 2023-12-19 | FIN Reports Phase-1: will work on vEMS data at FTP & Set up the schedule run at right time | [7 empty] | Automation test cases processed | 24 | Automation test cases processed | 4896
vEMS: WOR-882 (Refund to use Bank rate) | 4.5 | [17 empty] | Bugs identified | 2 | Bugs identified | 161
vEMS: Ad-hoc business requests | 5 | [19 empty] | Automation coverage | 98.1%
vEMS: Automation Script Enhancement | 7.5
vEMS: Automation(Multi SR & Power Bi) | 9

## 18 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 3.5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | TBD | worked on WOR-927 with Ramesh, issue not yet resolved | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual test cases created | 10 | Manual test cases created | 115
Test Case design/ Defect Tracker Update/ Jira Update | 3 | Saravanan munikrishnan | 15.5 | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Adding scripts for vEMS allocation variants | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | [7 empty] | Manual test cases conducted | 4 | Manual test cases conducted | 8170
vEMS: Triage / Review Meeting - Testing and Defects | 3 | Vignesh dhakshnamoorthy | 7.5 | AR/AP Dashboard | In Progress | 2023-12-19 | FIN Reports Phase-1: Completed | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Adding scripts for vEMS allocation variants | [7 empty] | Automation test cases created | 12 | Automation test cases created | 115
vEMS: AR/AP Dashboard | 11.5 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Initial analysis done on Test scripts from Business side and Environment readiness | AR/AP Dashboard | In Progress | 2023-12-29 | FIN Reports Phase-1: will work on vEMS data at FTP & Set up the schedule run at right time | [7 empty] | Automation test cases processed | 20 | Automation test cases processed | 4916
vEMS: WOR-882 (Refund to use Bank rate) | 0.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | TBD | Work on keeping the test Pre-requisites ready | [7 empty] | Bugs identified | 0 | Bugs identified | 161
vEMS: Ad-hoc business requests | 4.5 | [19 empty] | Automation coverage | 100%
vEMS: Automation Script Enhancement | 11
vEMS: Automation(Multi SR & Power Bi) | 6

## 26 Dec 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS: Daily Stand Up - Internal | 3.5 | Pramod rayate | 12 | WOR-882: Refund to use Bank Rate | In Progress | TBD | worked on WOR-927 with Ramesh, issue not yet resolved | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual test cases created | 8 | Manual test cases created | 123
Test Case design/ Defect Tracker Update/ Jira Update | 1 | Saravanan munikrishnan | 7.5 | WD-Regression Suite | In Progress | TBD | Phase-5:- Added scripts for vEMS allocation variations | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | [7 empty] | Manual test cases conducted | 4 | Manual test cases conducted | 8174
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 4 | AR/AP Dashboard | Completed | 2024-12-29 | FIN Reports Phase-1: Completed | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Will verify scripts for WD & vEMS allocation variants | [7 empty] | Automation test cases created | 8 | Automation test cases created | 123
vEMS: AR/AP Dashboard | 4 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Prepared and checked feasibility of the business scenarios in OAK-2 | AR/AP Dashboard | In Progress | 2024-01-04 | FIN Reports Phase-1: will work on vEMS data at FTP & Set up the schedule run at right time | [7 empty] | Automation test cases processed | 16 | Automation test cases processed | 4932
vEMS: WOR-939 SC, BR, COA mapping | 5.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-15 | Work on keeping the test Pre-requisites ready and kick off once we final review completed | [7 empty] | Bugs identified | 0 | Bugs identified | 161
vEMS: Automation Script Enhancement | 5.5 | [19 empty] | Automation coverage | 100%
vEMS: Automation(Multi SR & Power Bi) | 3

## 2 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 4 | Pramod rayate | 16 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defect logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 123
Test Case design/ Defect Tracker Update/ Jira Update | 1 | Saravanan munikrishnan | 7 | WD-Regression Suite | In Progress | TBD | Phase-5:- Added scripts for WOR-939 having WD & vEMS allocation variations | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | [7 empty] | Manual test cases conducted | 2 | Manual test cases conducted | 8176
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 4 | AR/AP Dashboard | Completed | 2024-01-02 | FIN Reports Phase-1: Completed. Monitoring data count & performance | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Will enhance scripts for WD & vEMS allocation variants | [7 empty] | Automation test cases created | 0 | Automation test cases created | 123
vEMS: AR/AP Dashboard | 4 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Discussed & Reviewed the business scenarios in OAK-2 | AR/AP Dashboard | In Progress | TBD | FIN Reports Phase-1: will work on vEMS data at FTP & Set up the schedule run at right time | [7 empty] | Automation test cases processed | 14 | Automation test cases processed | 4946
vEMS: WOR-939 SC, BR, COA mapping | 7.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-15 | Work on keeping the test Pre-requisites ready and kick off once we final review completed | [7 empty] | Bugs identified | 0 | Bugs identified | 161
vEMS: Automation Script Enhancement | 5 | [19 empty] | Automation coverage | 100%
vEMS: Automation(Multi SR & Power Bi) | 4.5

## 8 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 5 | Pramod rayate | 30 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_298 | SINV & ER Allocation Count mis-matches with Finsmart count at vEMS side | Medium | Open | Vikas |  |  | Manual test cases created | 0 | Manual test cases created | 123
Test Case design/ Defect Tracker Update/ Jira Update | 1 | Saravanan munikrishnan | 17.5 | WD-Regression Suite | In Progress | TBD | Phase-5:- Added scripts for WOR-939 having WD & vEMS allocation variations- Checked & verified | WOR-882: Refund to use Bank Rate | In Progress | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | Observation_302 | Spend Category / Expense Item not found in vEMS | High | Open | Vikas |  |  | Manual test cases conducted | 0 | Manual test cases conducted | 8176
vEMS: Triage / Review Meeting - Testing and Defects | 2 | Vignesh dhakshnamoorthy | 4 | AR/AP Dashboard | Completed |  | FIN Reports Phase-1: Completed Monitoring data count & performance | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Enhance scripts for WD & vEMS allocation variants as needed | Observation_303 | SC and BR not a valid combination as per Allowability matrix | High | Open | Vikas |  |  | Automation test cases created | 0 | Automation test cases created | 123
vEMS: AR/AP Dashboard | 4 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Test execution - In Progress (Blocked due to issue) | AR/AP Dashboard | In Progress | TBD | FIN Reports Phase-1: Merge Prod & Dev in single to make it centralized | [7 empty] | Automation test cases processed | 10 | Automation test cases processed | 4956
vEMS: WOR-939 SC, BR, COA mapping | 27 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-19 | Will get issues resolved and complete testing | [7 empty] | Bugs identified | 3 | Bugs identified | 164
vEMS: Automation Script Enhancement | 3 | [19 empty] | Automation coverage | 100%
vEMS: Automation(Multi SR & Power Bi) | 9.5

## 15 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 3 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_307 | CINV Issue- getting error as "Validation error occurred. Invalid ID value. '' is not a valid ID value for type = 'Revenue_Category_ID'" | Critical | Open |  |  |  | Manual test cases created | 0 | Manual test cases created | 123
Test Case design/ Defect Tracker Update/ Jira Update | 1 | Saravanan munikrishnan | 17 | WD-Regression Suite | In Progress | TBD | Phase-5:- Added scripts for WOR-939 having WD & vEMS allocation variations- Checked & verified | WOR-882: Refund to use Bank Rate | On Hold | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | [7 empty] | Manual test cases conducted | 0 | Manual test cases conducted | 8176
vEMS: Triage / Review Meeting - Testing and Defects | 4.5 | Vignesh dhakshnamoorthy | 2 | AR/AP Dashboard | Completed |  | FIN Reports Phase-1: Completed | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold | [7 empty] | Automation test cases created | 0 | Automation test cases created | 123
[7 empty] | Monitoring data count & performance |  |  |  | Enhance scripts for WD & vEMS allocation variants as needed | [7 empty] | Automation test cases processed | 30 | Automation test cases processed | 4986
vEMS: AR/AP Dashboard | 2 |  |  | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-25 | Test execution - In Progress (Impacted due to issue) | AR/AP Dashboard | In Progress | 2024-01-30 | FIN Reports Phase-1: Merge Prod & Dev in single to make it centralized - ETA-30-Jan | [7 empty] | Bugs identified | 1 | Bugs identified | 165
vEMS: WOR-939 SC, BR, COA mapping | 11.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-01-25 | Will get issues resolved and complete testing | [9 empty] | Automation coverage | 100%
vEMS: Automation Script Enhancement | 8
vEMS: Automation(Multi SR & Power Bi) | 9

## 22 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 4 | Pramod rayate | 18 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_308 | Vichara team did not send latest prod count to FTP location | Medium | Closed | Vikas |  |  | Manual test cases created | 0 | Manual test cases created | 123
Test Case design/ Defect Tracker Update/ Jira Update | 3 | Saravanan munikrishnan | 16.5 | WD-Regression Suite | In Progress | TBD | Phase-5:- Fine tuned scripts for WOR-939 having WD & vEMS allocation variations- Checked & verified | WOR-882: Refund to use Bank Rate | On Hold | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | [7 empty] | Manual test cases conducted | 0 | Manual test cases conducted | 8176
vEMS: Triage / Review Meeting - Testing and Defects | 0.5 | Vignesh dhakshnamoorthy | 2 | AR/AP Dashboard | Completed |  | FIN Reports Phase-1: Completed Monitoring data count & performance | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Enhance scripts for WD & vEMS allocation variants as needed | [7 empty] | Automation test cases created | 0 | Automation test cases created | 123
vEMS: AR/AP Dashboard | 2 |  |  | WOR-939: SC, BR, COA mapping | In Progress | 2024-02-02 | Test execution - In Progress (Blocked due to issues) | AR/AP Dashboard | In Progress | 2024-02-02 | FIN Reports Phase-1: Merge Prod & Dev in single to make it centralized - ETA-02-Feb | [7 empty] | Automation test cases processed | 25 | Automation test cases processed | 5011
vEMS: WOR-939 SC, BR, COA mapping | 12.5 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-02-02 | Will get issues resolved and complete testing | [7 empty] | Bugs identified | 1 | Bugs identified | 166
vEMS: Automation Script Enhancement | 8 | [19 empty] | Automation coverage | 100%
vEMS: Automation(Multi SR & Power Bi) | 6.5

## 29 Jan 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | Observation_315 | SINV or ER with long dash special char getting failed at Geneva Accrual | High | Open | Harshad |  |  | Manual test cases created | 0 | Manual test cases created | 123
Test Case design/ Defect Tracker Update/ Jira Update | 3.5 | Saravanan munikrishnan | 11.5 | WD-Regression Suite | In Progress | TBD | Phase-5:- Enhanced scripts for WOR-939 having WD & vEMS allocation variations- Checked & verified | WOR-882: Refund to use Bank Rate | On Hold | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | Observation_316 | (Meals & Entertainment)- ART not valid combination at Geneva | Medium | Open | Harshad |  |  | Manual test cases conducted | 13 | Manual test cases conducted | 8189
vEMS: Triage / Review Meeting - Testing and Defects | 2 | Vignesh dhakshnamoorthy | 2.5 | AR/AP Dashboard | In Progress |  | FIN Reports Phase-2: In progress Monitoring data count & performance | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Enhance scripts for WD & vEMS allocation variants as needed | Observation_314 | Vichara team sent an empty count file to FTP location. |  | Medium | Vikas |  |  | Automation test cases created | 0 | Automation test cases created | 123
vEMS: AR/AP Dashboard | 2.5 |  |  | WOR-939: SC, BR, COA mapping | In Progress | 2024-02-08 | Test execution - In Progress (Addressed majority issues) | AR/AP Dashboard | In Progress | 2024-02-09 | FIN Reports Phase-1: Merge Prod & Dev in single to make it centralized - ETA-09-Feb | [7 empty] | Automation test cases processed | 30 | Automation test cases processed | 5041
vEMS: WOR-939 SC, BR, COA mapping | 13 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | 2024-02-08 | Will get issues resolved and complete testing | [7 empty] | Bugs identified | 3 | Bugs identified | 169
vEMS: Automation Script Enhancement | 8 | [19 empty] | Automation coverage | 100%

## 5 Feb 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 3 | Pramod rayate | 13 | WOR-882: Refund to use Bank Rate | On Hold | TBD | issue not yet resolved, Ramesh got high priority tickets | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | [7 empty] | Manual test cases created | 0 | Manual test cases created | 123
Test Case design/ Defect Tracker Update/ Jira Update | 1 | Saravanan munikrishnan | 8 | WD-Regression Suite | In Progress | TBD | Phase-5:- Enhanced scripts for WOR-939 having WD & vEMS allocation variations - Checked & verified | WOR-882: Refund to use Bank Rate | On Hold | TBD | Will work with Ramesh & William to resolve issue in INT0209 & INT0210a | [7 empty] | Manual test cases conducted | 4 | Manual test cases conducted | 8193
vEMS: Triage / Review Meeting - Testing and Defects | 1.5 | Vignesh dhakshnamoorthy | 2.5 | AR/AP Dashboard | In Progress | TBD | FIN Reports Phase-2: In progress Monitoring data count & performance | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: On Hold Enhance scripts for WD & vEMS allocation variants as needed | [7 empty] | Automation test cases created | 0 | Automation test cases created | 123
vEMS: AR/AP Dashboard | 2.5 |  |  | WOR-939: SC, BR, COA mapping | In Progress | TBD | Test execution - Completed (few minor issues still open) | AR/AP Dashboard | In Progress | 2024-02-15 | FIN Reports Phase-1: Merge Prod & Dev in single to make it centralized - ETA-15-Feb | [7 empty] | Automation test cases processed | 10 | Automation test cases processed | 5051
vEMS: WOR-939 SC, BR, COA mapping | 9 | [6 empty] | WOR-939: SC, BR, COA mapping | In Progress | TBD | Will get issues resolved and complete testing | [7 empty] | Bugs identified | 0 | Bugs identified | 169
vEMS: Automation Script Enhancement | 4 | [19 empty] | Automation coverage | 100%
vEMS: Automation(WD & vEMS changes) | 2.5

## 12 Feb 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 5 | Pramod rayate | 20 | WOR-939: SC, BR, COA mapping | In Progress | TBD | Test execution - Completed (few minor issues still open) | WOR-939: SC, BR, COA mapping | In Progress | TBD | Will get issues resolved and complete testing | Observation_322 | vEMS count old file should not be removed from FTP on Friday. It should get removed on Saturday | High | Open | Prayerna |  |  | Manual test cases created | 0 | Manual test cases created | 123
Test Case design/ Defect Tracker Update/ Jira Update | 3.5 | Saravanan munikrishnan | 12 | WD: WOR-956 (2 recon lines for single SINV) | In Progress | 2024-02-20 | Understood the issue and fix, Trying to replicate exact case | WD: WOR-956 (2 recon lines for single SINV) | In Progress | 2024-02-20 | Understood the issue and fix, will finish testing | [7 empty] | Manual test cases conducted | 2 | Manual test cases conducted | 8195
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 5 | WD: WOR-962 (Emp Name issue in Recon ) | In Progress | 2024-02-22 | Understood the issue and fix, Testing in Progress | WD: WOR-962 (Emp Name issue in Recon ) | In Progress | 2024-02-22 | Understood the issue and fix, will finish testing | [7 empty] | Automation test cases created | 0 | Automation test cases created | 123
vEMS: AR/AP Dashboard | 7 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Adding new WD functionalities in scripts - In Progress | WD-Regression Suite | In Progress | TBD | Phase-5:- Adding new WD functionalities in scripts - In Progress | [7 empty] | Automation test cases processed | 14 | Automation test cases processed | 5065
vEMS: WOR-939 SC, BR, COA mapping | 3 |  |  | AR/AP Dashboard | In Progress | 2024-02-21 | FIN Reports Phase-2: In progress Completed new changes at WD, vEMS changes- In progress | AR/AP Dashboard | In Progress | 2024-02-21 | FIN Reports Phase-2: In Progress Will finish vEMS recon report changes asap | [7 empty] | Bugs identified | 1 | Bugs identified | 170
vEMS: Automation Script Enhancement | 7.5 | [19 empty] | Automation coverage | 100%
vEMS: Automation(WD & vEMS changes) | 10

## 19 Feb 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 4.5 | Pramod rayate | 16 | WOR-939: SC, BR, COA mapping | In Progress | TBD | Test execution - Completed (few minor issues still open) | WOR-939: SC, BR, COA mapping | In Progress | TBD | Testing completed, will plan UAT |  | No defects logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 123
Test Case design/ Defect Tracker Update/ Jira Update | 2.5 | Saravanan munikrishnan | 6 | WD: WOR-956 (2 recon lines for single SINV) | In Progress | 2024-02-27 | Found issue, Waiting for fix from Sundeep & Vichara team | WD: WOR-956 (2 recon lines for single SINV) | In Progress | 2024-02-27 | Will follow up with Sundeep & Vichara team on the issue | [7 empty] | Manual test cases conducted | 3 | Manual test cases conducted | 8198
vEMS: Triage / Review Meeting - Testing and Defects | 1.5 | Vignesh dhakshnamoorthy | 2.5 | WD: WOR-962 (Emp Name issue in Recon ) | In Progress | 2024-02-27 | Found issue, Waiting for fix from Sundeep | WD: WOR-962 (Emp Name issue in Recon ) | In Progress | 2024-02-27 | Will follow up with Sundeep & Vichara team on the issue | [7 empty] | Automation test cases created | 0 | Automation test cases created | 123
vEMS: AR/AP Dashboard | 5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- added new WD functionalities in scripts - Review In Progress | WD-Regression Suite | In Progress | TBD | Phase-5:- added new WD functionalities in scripts - Review In Progress | [7 empty] | Automation test cases processed | 10 | Automation test cases processed | 5075
vEMS: Ad-hoc testing request | 2 |  |  | AR/AP Dashboard | In Progress | 2024-02-27 | FIN Reports Phase-2: In progress Sat date logic change for vEMS- In progress | AR/AP Dashboard | In Progress | 2024-02-27 | FIN Reports Phase-2: In progress Sat date logic change for vEMS- In progress | [7 empty] | Bugs identified | 0 | Bugs identified | 170
vEMS: WOR-956 (2 recon lines for single SINV) | 2.5 | [19 empty] | Automation coverage | 100%
vEMS: Automation Script Enhancement | 2
vEMS: Automation(WD & vEMS changes) | 4.5

## 26 Feb 2024
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Activity This Week | Count. | Project Metrics Since Inception | Count..
vEMS:Daily StandUp - Internal | 4.5 | Pramod rayate | 20 | WOR-939: SC, BR, COA mapping | Completed | TBD | Test execution - Completed, UAT kicked off | WOR-978: SC, BR, COA mapping | In Progress | TBD | UAT has kicked off on Mar-01, will support UAT |  | No defects logged for the week | [5 empty] | Manual test cases created | 0 | Manual test cases created | 123
Test Case design/ Defect Tracker Update/ Jira Update | 2.5 | Saravanan munikrishnan | 16.5 | WD: WOR-956 (2 recon lines for single SINV) | In Progress | 2024-03-07 | Issue resolved, waiting for new code deployment | WD: WOR-956 (2 recon lines for single SINV) | In Progress | 2024-03-07 | Issue resolved, waiting for new code deployment | [7 empty] | Manual test cases conducted | 2 | Manual test cases conducted | 8197
vEMS: Triage / Review Meeting - Testing and Defects | 2.5 | Vignesh dhakshnamoorthy | 2.5 | WD: WOR-962 (Emp Name issue in Recon ) | In Progress | 2024-03-05 | Testing completed, will do documentation | WD: WOR-962 (Emp Name issue in Recon ) | In Progress | 2024-03-05 | Post documentation, will send for business sign off | [7 empty] | Automation test cases created | 0 | Automation test cases created | 123
vEMS: AR/AP Dashboard | 4.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- added new WD functionalities in scripts - Review In Progress | WD-Regression Suite | In Progress | TBD | Phase-5:- added new WD functionalities in scripts - Review In Progress | [7 empty] | Automation test cases processed | 6 | Automation test cases processed | 5071
vEMS: WOR-939 (SC, BR, COA Mapping) | 3.5 |  |  | AR/AP Dashboard | In Progress |  | FIN Reports Phase-2: In progress Sat date logic change for vEMS- Completed | AR/AP Dashboard | In Progress | TBD | FIN Reports Phase-2: In progress Will Monitor the daily status and highlight if anything fails | [7 empty] | Bugs identified | 0 | Bugs identified | 170
vEMS: WOR-956 (2 recon lines for single SINV) | 2.5 | [19 empty] | Automation coverage | 100%
vEMS: WOR-962 (Emp Name issue in Recon ) | 2
vEMS: Automation Script Enhancement | 5.5
vEMS: Automation(WD & vEMS changes) | 11.5