## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
HICA-2811 Test scenarios preparation | 1.5 | Ayesha Shaik | 9.45 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective Meeting | Yet to attend |  |  |  | No defects logged | [5 empty] | Total Manual Execution | 5
Call with Hrushikesh on Eevrest UAT installation | 1 | Venkateswaran. Karuppian Ganesan | 0.25 | Sprint Review and Retrospective meeting | Completed |  |  | Attend Spring Planning call | Yet to attend | [9 empty] | Total Automation Execution | 0
HICA-2811 Test scenarios Execution | 5 |  |  | Sprint Planning meeting | Completed |  |  | Attend Weekly Call with Business | Yet to attend | [9 empty] | Bugs Identified | 0
Test cases preparation for HICA-2876 | 2 | [17 empty] | Total Bugs | 0
Call with Sibin | 0.5 | [17 empty] | Manual Test Created | 0
[19 empty] | Total Manual Case | 197
[19 empty] | Automation Scripts Created | 0
[19 empty] | Total Automation Scripts | 0

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
HICA-2876 Test scenarios execution | 6.5 | Ayesha Shaik | 7.5 | Attended Daily Standup calls | Completed |  |  | Attend Sizing and backlog refinement meeting | Yet to attend |  |  |  | No defects logged for the week | [5 empty] | Total Manual Execution | 6
QA document preparation for HICA-2876 | 1 |  |  | Sprint Review and Retrospective meeting | Completed |  |  | Attend Weekly Call with Business | Yet to attend | [9 empty] | Total Automation Execution | 0
|  |  |  | Sprint Planning meeting | Completed | [13 empty] | Bugs Identified | 0
[19 empty] | Total Bugs | 0
[19 empty] | Manual Test Created | 3
[19 empty] | Total Manual Case | 200
[19 empty] | Automation Scripts Created | 0
[19 empty] | Total Automation Scripts | 0

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
HICA-2925 Test scenarios preparation | 2 | Ayesha Shaik | 7.5 | Attended Daily Standup calls | Completed |  |  | Attend Sprint review and Retrospective meeting | Yet to attend |  |  | HICA-2920 | Job run in Swift folder: No email notification triggered when other .fin file is placed in Inbound file | Medium | Closed | Sibin |  | Converted to story | Total Manual Execution | 12
HICA-2925 Test cases preparation | 4 |  |  | Attend Sizing and backlog refinement meeting | Completed |  |  | Attend Sprint planning call | Yet to attend | [9 empty] | Total Automation Execution | 0
HICA-2925 Test cases execution | 1.5 |  |  | HICA-2925 Test Scenarios Preparation | Completed | [13 empty] | Bugs Identified | 1
|  |  |  | HICA-2925 Test cases Preparation | Completed | [13 empty] | Total Bugs | 1
|  |  |  | HICA-2925 Test cases Execution | In Progress | 2023-11-20 | [12 empty] | Manual Test Created | 12
[19 empty] | Total Manual Case | 212
[19 empty] | Automation Scripts Created | 0
[19 empty] | Total Automation Scripts | 0

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
HICA-2925 Test scenarios executi | 6 | Ayesha Shaik | 12.5 | Attended Daily Standup calls | Completed |  |  | Attend Sizing and backlog refinement meeting | Yet to attend |  |  |  | No defect logged for the week | [5 empty] | Total Manual Execution | 16
Updation of Test scenarios and Test cases for Tier-2 | 0.5 |  |  | Sprint Review and Retrospective meeting | Completed |  |  | Attend Weekly Call with Business | Yet to attend | [9 empty] | Total Automation Execution | 0
HICA-3034 Test Scenarios preparation | 2 |  |  | Sprint Planning meeting | Completed | [13 empty] | Bugs Identified | 0
HICA-3034 Test cases preparation | 4 | [17 empty] | Total Bugs | 1
[19 empty] | Manual Test Created | 12
[19 empty] | Total Manual Case | 224
[19 empty] | Automation Scripts Created | 0
[19 empty] | Total Automation Scripts | 0