## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
1.Standup /Internal/Dev calls | 3 | Eswara Rao Kanakala | 3 | 1. Standup Calls/Dev Calls | In Progress |  |  | Automation | In Progress |  |  |  | No defect logged for the week | [5 empty] | Total Manual Execution | 0
2. Automation script development POC | 23.5 | Samikruth Reddy | 12 | 2. Working on Automation POC Scripts development | In Progress |  |  | ITEM- C test Cases Execution &Documentation | Yet to Start | [9 empty] | Total Automation Execution | 0
|  | Vignesh | 10.5 | [15 empty] | Bugs Identified | 0
|  | Meenakshi | 1 | [15 empty] | Total Bugs | 0
[19 empty] | Manual Test Created | 92
[19 empty] | Total Manual Case | 92
[19 empty] | Automation Scripts Created | 0
[19 empty] | Total Automation Scripts | 0

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
1.Standup /Internal/Dev calls | 13.5 | Eswara Rao Kanakala | 24 | 1. Standup Calls/Dev Calls | In Progress |  |  | Automation POC | In Progress |  |  |  | No defects logged for the week | [5 empty] | Total Manual Execution | 92
2. Item-c Test execution and documentation | 43 | Samikruth Reddy | 25 | 2. Extraordinary investment loss test cases execution | Completed |  |  | ITEM- H test Cases Execution | In Progress | [9 empty] | Total Automation Execution | 0
3. Automation POC | 11 | Vignesh | 5.5 | 3. Item- C Testing and documentation is Completed | Completed | [13 empty] | Bugs Identified | 0
|  | Meenakshi | 4 | 4. ITEM- H Test Execution, User Manual preparation for CST portal | In Progress | [13 empty] | Total Bugs | 0
[19 empty] | Manual Test Created | 92
[19 empty] | Total Manual Case | 184
[19 empty] | Automation Scripts Created | 0
[19 empty] | Total Automation Scripts | 0

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
1.Standup /Internal/Dev calls | 10 | Eswara Rao Kanakala | 23 | 1. Standup Calls/Dev Calls | In Progress |  |  | Automation POC | In Progress | [9 empty] | Total Manual Execution | 92
2. Item-E &H Test execution and documentation | 39 | Samikruth Reddy | 24 | 2. Extraordinary investment loss test cases execution | Completed |  |  | ITEM- H & E test Cases Documentation | In Progress | [9 empty] | Total Automation Execution | 0
|  | Meenakshi | 2 | 3. Item- C Testing and documentation is Completed | Completed | [13 empty] | Bugs Identified | 0
|  |  |  | 4. ITEM- E &H Test Execution | Completed | [13 empty] | Total Bugs | 0
|  |  |  | 5. User Manual preparation for CST portal | Completed | [13 empty] | Manual Test Created | 184
|  |  |  | 6. Test Execution Documentation for ITEM-E &H | In Progress | [13 empty] | Total Manual Case | 368
[19 empty] | Automation Scripts Created | 0
[19 empty] | Total Automation Scripts | 0

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
1.Standup /Internal/Dev calls | 1 | Eswara Rao Kanakala | 16 | 1. Standup Calls/Dev Calls | In Progress |  |  | Automation POC | In Progress |  |  |  | No defects logged | [5 empty] | Total Manual Execution | 92
2. Item-E &H Test execution and documentation | 40 | Samikruth Reddy | 24 | 2. Extraordinary investment loss test cases execution | Completed | [13 empty] | Total Automation Execution | 0
|  | Meenakshi | 1 | 3. Item- C Testing and documentation is Completed | Completed | [13 empty] | Bugs Identified | 0
|  |  |  | 4. ITEM- E &H Test Execution | Completed | [13 empty] | Total Bugs | 0
|  |  |  | 5. User Manual preparation for CST portal | Completed | [13 empty] | Manual Test Created | 184
|  |  |  | 6. Test Execution Documentation for ITEM-E &H | Completed | [13 empty] | Total Manual Case | 368
[19 empty] | Automation Scripts Created | 0
[19 empty] | Total Automation Scripts | 0