## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
Attended Stand up call | 4.3 | Ayesha Shaik | 32.15 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective Meeting | Yet to attend |  |  | HICA-2886 | Perform CRUD operations on newly created PEs', facilitate bulk upload of PEs with special characters, and update existing PEs in the PSA module aligning with HRIS. | High | Closed | Sibin |  | Converted into story | Total Manual Execution | 59
Attended Sizzing session & Backlog Refinement | 2 | Venkateswaran. Karuppian Ganesan | 40.15 | Attended Sizing and Backlog Refinement | Completed |  |  | Attend Spring Planning call | Yet to attend | [9 empty] | Total Automation Execution | 0
HICA-2810 Regression on Paying Entity | 32 |  |  | HICA-2810 Regression on Paying Entity | Completed |  |  | Attend Weekly Call with Business | Yet to attend | [9 empty] | Bugs Identified | 1
HICA-2802:Test Scenario Preparation | 1.5 |  |  | HICA-2802:Test Scenario Preparation | Completed |  |  | Work on the tickets developed by the Dev team | Yet to attend | [9 empty] | Total Bugs | 53
HICA-2802: Test data preparation and connected with Oliva | 0.5 |  |  | HICA-2802: Test Scenario Execution | Inprogress | 2023-11-06 | [12 empty] | Manual Test Created | 35
HICA-2802: Test Scenario Execution | 4 |  |  | HICA-2763: Test Scenario Preparation | Completed | [13 empty] | Total Manual Case | 490
HICA-2763: Test Scenario Preparation | 3 |  |  | HICA-2763: Test Scenario Execution | Completed | [13 empty] | Automation Scripts Created | 0
HICA-2763: Test cases Preparation | 4 |  |  | HICA-2886:Test Scenario Preparation | Completed | [13 empty] | Total Automation Scripts | 0
HICA-2763 Test cases review | 1 |  |  | HICA-2886:Test Scenario Execution | Inprogress | 2023-12-06
HICA-2763: Test Scenario Execution | 9.5
HICA-2886:Test Scenario Preparation | 3.5
HICA-2886:Test Scenario Execution | 5
Call with Venkat | 1
Call with Sibin | 1

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
Attended Stand up call | 3 | Ayesha Shaik | 31.5 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Sizing and Backlog Refinement call | Yet to attend |  |  |  | No defects Logged for the week | [5 empty] | Total Manual Execution | 21
Sprint Review and Retrospective | 6 | Venkateswaran. Karuppian Ganesan | 40.2 | Sprint Review and Retrospective meeting | Completed |  |  | Work on the developed sprint items for Testing and Test scenarios | Yet to start | [9 empty] | Total Automation Execution | 0
Sprint Planning session | 2 |  |  | Sprint Planning meeting | Completed | [13 empty] | Bugs Identified | 0
HICA-2763 -Testcases and Scenarios review | 1 | [17 empty] | Total Bugs | 53
HICA-2293 Test Scenarios Prepared | 1 | [17 empty] | Manual Test Created | 10
HICA-2293 Test Case prepared | 3 | [17 empty] | Total Manual Case | 500
Raised bug(converted to story) ie HICA-2920 | 0.5 | [17 empty] | Automation Scripts Created | 0
HICA-2886 Test case prepared | 3.5 | [17 empty] | Total Automation Scripts | 0
Execution for HICA-2293 | 8
HICA-2886 Execution for Payment screen | 28
HICA-2887 test scenarios prepared | 3
HICA-2887 re test for verification screen | 4.5
Test Scenarios preparation for HICA-2885 | 2.5
Test cases preparation for HICA-2885 | 4
Test data preparation for HICA-2886 | 0.3
call with Sibin | 0.4
Call with Ayesha | 1
Call with Venkat | 1
Weekly ICS Meeting | 1

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
Attended Stand up call | 3 | Ayesha Shaik | 25.5 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective Meeting | Yet to attend |  |  | HICA-3001 | PointsPayments - Include Paying Entity in the list of fields to be reverted to their original state on the rejection of payment and make sure the status is correctly updated when editing a payment using bulk upload | High | Closed | Sibin |  | COnverted to story | Total Manual Execution | 21
Attended Sizzing session & Backlog Refinement | 2 | Venkateswaran. Karuppian Ganesan | 28 | Attended Sizing and Backlog Refinement | Completed |  |  | Attend Spring Planning call | Yet to attend | [9 empty] | Total Automation Execution | 0
Attended Weekly call with Business | 1 |  |  | Attended Weekly business meeting | Completed |  |  | Work on the tickets developed by the Dev team | Yet to attend | [9 empty] | Bugs Identified | 1
Prepared QA document for SDLC#26767 | 1 |  |  | QA document for SDLC#26767 | Completed | [13 empty] | Total Bugs | 54
HICA-2886 Test cases execution | 19 |  |  | HICA-2939 Test scenarios preparation | Completed | [13 empty] | Manual Test Created | 11
HICA-2939 Test scenarios preparation | 2 |  |  | HICA-2939: Test cases preparation | Completed | [13 empty] | Total Manual Case | 511
HICA-2939 Test cases preparation | 2 |  |  | HICA-2939: Test Scenario Execution | Completed | [13 empty] | Automation Scripts Created | 0
HICA-2939 Test cases execution | 4 |  |  | HICA-2885: Test Scenario Preparation | Completed | [13 empty] | Total Automation Scripts | 0
HICA-2885 Test scenarios preparation | 2 |  |  | HICA-2885: Test cases Preparation | Completed
HICA-2885 Test cases preparation | 8 |  |  | HICA-2885: Test cases Execution | Inprogress | 2023-11-20
HICA-2885 Test cases Execution | 9 |  |  | HICA-2886:Test Scenario Execution | completed
call with Sibin | 0.5

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
Attended Stand up call | 1.5 | Ayesha Shaik | 19.5 | Attended Daily Standup calls | Completed |  |  | Attend Sprint Review and Retrospective Meeting | Yet to attend | [9 empty] | Total Manual Execution | 9
Attended Sprint review and Retrospective Meeting | 3 | Hrushikesh Ambati | 1.5 | Attended Sprint review and Sprint retrospective meeting | Completed |  |  | Attend Spring Planning call | Yet to attend | [9 empty] | Total Automation Execution | 0
Prepared QA document for SDLC#26839 | 4 |  |  | QA document for SDLC#26839 | Completed |  |  | Work on the tickets developed by the Dev team | Yet to attend | [9 empty] | Bugs Identified | 0
HICA-3001Test scenarios preparation | 2 |  |  | HICA-3001:Test scenarios preparation | Completed | [13 empty] | Total Bugs | 54
HICA-3001 Test cases preparation | 4 |  |  | HICA-3001: Test cases preparation | Completed | [13 empty] | Manual Test Created | 8
HICA-3001 Test cases execution | 6 |  |  | HICA-3001: Test Scenario Execution | Completed | [13 empty] | Total Manual Case | 519
call with Sibin | 0.5 | [17 empty] | Automation Scripts Created | 0
[19 empty] | Total Automation Scripts | 0