## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. |  | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count | Week Data Type | Week Count | Total Data Type | Total Count
Meetings | 1 | Johnson Benjamin | 41 |  | Testing the Audit changes from dev for Nov 2nd release | Completed |  |  | Test cases updating for Step 2 | In progress | [9 empty] | Total Manual Execution | 108 | Manual created | 37 | Total manual | 56
New Changes Nov2 Release | 20 | Kathhir | 41 |  | Test cases updating for step 2. | In progress |  |  | Additional Approval process in Call-back. | Yet to Start |  | We will test once the dev team provides it. | [7 empty] | Total Automation Execution | 296 | Manual execution | 118 | Total manual execution | 1352
Test case updating for step 2 process. | 63 | Vignesh | 2 | [5 empty] | Warning box in both the Business Approver and Treasury Approver for payments over $1M+ or $50K. | Yet to Start |  | We will test once the dev team provides it. | [7 empty] | Bugs Identified | 17 | Automation created | 26 | Total automation | 38
[20 empty] | Total Bugs | 180 | Automation execution | 89 | Total automation execution | 732
[20 empty] | Manual Test Created | 8 | Bugs Identified | 34 | Total bugs | 62
|  |  |  | S | [15 empty] | Total Manual Case | 116 |  |  | Automation coverage % | 68
[20 empty] | Automation Scripts Created | 10
[20 empty] | Total Automation Scripts | 306

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count | Week Data Type | Week Count | Total Data Type | Total Count
Meetings | 3 | Johnson Benjamin | 24 | Solution Update testing | In progress | 14/11/2023 |  | Test cases updating for Step 2 | In progress | [9 empty] | Total Manual Execution | 109 | Manual created | 46 | Total manual | 102
Solution Update testing | 33 | Kathhir | 42 | Test cases updating for step 2. | In progress |  |  | Solution Update testing | In progress | 14/11/2023 | [8 empty] | Total Automation Execution | 297 | Manual execution | 120 | Total manual execution | 1472
Test case updation for step 2 process. | 31 | Vignesh | 1 |  |  |  |  | Additional Approval process in Call-back. | Yet to Start |  | We will test once the dev team provides it. | [7 empty] | Bugs Identified | 18 | Automation created | 37 | Total automation | 75
[8 empty] | Making Beneficiary Address and City for HSBC bank accounts. | Yet to start |  | We will test once the dev team provides it. | [7 empty] | Total Bugs | 181 | Automation execution | 150 | Total automation execution | 882
[8 empty] | Warning box in both the Business Approver and Treasury Approver for payments over $1M+ or $50K. | Yet to Start |  | We will test once the dev team provides it. | [7 empty] | Manual Test Created | 9 | Bugs Identified | 15 | Total bugs | 77
[19 empty] | Total Manual Case | 117 |  |  | Automation coverage % | 68
[19 empty] | Automation Scripts Created | 11
[19 empty] | Total Automation Scripts | 307

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count | Week Data Type | Week Count | Total Data Type | Total Count
Meetings | 3 | Johnson Benjamin | 34 | Solution Upgrade testing | In progress | 20/11/2023 | Testing completed; Issues assigned to Dev. | Test cases update for Step 2 | In progress |  |  | WMT - 2283 | Blue lines are displayed when the user clicks on any of the search fields in Payment request grid. | Low | In QA | Chaitanya |  |  | Total Manual Execution | 110 | Manual created | 8 | Total manual | 110
Solution Update testing | 16 | Kathhir | 34 | Audit Enhancement testing - Warning box in both the Business Approver and Treasury Approver for payments over $1M+ | Completed |  |  | Solution Upgrade testing | In progress | 20/11/2023 |  | WMT - 2283 | The Number entered in the "Age" search field is not displaying in the "Track Template" grid and "Approver Payment Instruction Template". | Low | In QA | Chaitanya |  |  | Total Automation Execution | 298 | Manual execution | 15 | Total manual execution | 1487
Audit Enhancement testing | 22 | Vignesh | 1 | Testing Edit existing template and Revise payment template. | In progress | 20/11/2023 |  | Testing Edit existing template and Revise payment template. | In progress | 20/11/2023 |  | WMT - 2283 | The Number entered in the "Row" search field, "Increment by 1" and “Decrement by 1" buttons are also not displaying in the "Template Uploader". | Low | In QA | Chaitanya |  |  | Bugs Identified | 19 | Automation created | 2 | Total automation | 77
Testing Edit and Revise payment templates | 28 |  |  | Test cases updating for step 2. | In progress |  |  | Value date should not be weekend. | In progress | 21/11/2023 |  | WMT - 2283 | Check box, Transmission method drop down and Pagination numbers are displayed in Blue colour in Staging screen. | Low | In QA | Chaitanya |  |  | Total Bugs | 182 | Automation execution | 23 | Total automation execution | 905
[8 empty] | Select all check box in Payment staging interface | In progress | 20/11/2023 |  | WMT - 2283 | Generically, all the Calendar icons are displaying in Black colour, whereas it was displayed in Green colour previously. | Low | In QA | Chaitanya |  |  | Manual Test Created | 10 | Bugs Identified | 5 | Total bugs | 82
[8 empty] | Max length Validation message In Amount field. | In progress | 21/11/2023 | [8 empty] | Total Manual Case | 118 |  |  | Automation coverage % | 68
[8 empty] | Additional Approval process in Call-back. | Yet to Start | 23/11/2023 | Testing will be started once deployment is done. | [7 empty] | Automation Scripts Created | 12
[19 empty] | Total Automation Scripts | 308

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count | Week Data Type | Week Count | Total Data Type | Total Count
Meetings | 5 | Johnson Benjamin | 51 | Solution Upgrade testing | In progress | 28/11/2023 |  | Test cases update for Step 2 | In progress |  |  | WMT - 2292 | The first letter of the message displayed in BL screen needs to be in Caps. | Low | Closed | Lipi |  |  | Total Manual Execution | 111 | Manual created | 10 | Total manual | 120
Solution Update testing | 11 | Kathhir | 51 | Audit Enhancement testing - Warning box in both the Business Approver and Treasury Approver for payments over $1M+ | In progress | 27/11/2023 |  | Solution Upgrade testing | In progress | 28/11/2023 |  | WMT - 2503 | Requestor is able to submit a payment request without entering Financial approver. | Medium | Closed | Lipi |  |  | Total Automation Execution | 299 | Manual execution | 23 | Total manual execution | 1510
Audit Enhancement testing | 70.5 | Vignesh | 5.5 | Value date should not be weekend. | Completed |  |  | Audit Enhancement testing - Warning box in both the Business Approver and Treasury Approver for payments over $1M+ | Completed |  |  | WMT - 2054 | Value Date is accepting Sat and Sun in Payment Failed - Treasury Reprocessing Status. | Medium | Closed | Lipi |  |  | Bugs Identified | 20 | Automation created | 5 | Total automation | 82
Testing Edit and Revise payment templates | 35 | Kalyan Gopi | 35 | Testing Edit existing template and Revise payment template. | In progress | 27/11/2023 |  | JIRA tickets testing. | In progress | 28/11/2023 |  | WMT - 1813 | Validation message should not be displayed when we enter amount as “-1”. | Low | Closed | Lipi |  |  | Total Bugs | 183 | Automation execution | 45 | Total automation execution | 950
JIRA tickets | 21 |  |  | Audit Enhancement testing - Additional Approval process in Call-back Verification. | In progress | 27/11/2023 |  | Testing Edit existing template and Revise payment template. | Completed |  |  | WMT - 1813 | Validation the message should be “Amount should be between 1 and 100 trillion”. | Low | Closed | Lipi |  |  | Manual Test Created | 11 | Bugs Identified | 11 | Total bugs | 93
|  |  |  | JIRA tickets testing. | In progress | 28/11/2023 |  | Audit Enhancement testing - Additional Approval process in Call-back Verification. | Completed |  |  | WMT - 2247 | When TA Return to Requestor, document uploaded in CB Verifier is not clearing. | High | Closed | Lipi |  |  | Total Manual Case | 119 |  |  | Automation coverage % | 68
|  |  |  | Max length Validation message In Amount field. | Completed | [6 empty] | WMT - 2247 | TP saves internal use tab, now when CB opens the same tickets, buttons are displayed in internal use tab and final review tab and CB is able to perform approve. | High | Closed | Lipi |  |  | Automation Scripts Created | 13
|  |  |  | Added Required to label for Beneficiary Address and City in Step 1 | Completed | [13 empty] | Total Automation Scripts | 309
|  |  |  | Test cases updating for step 2. | In progress