## 6 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
vEMS:Daily StandUp - Internal | 4.5 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | [7 empty] | Total Manual Execution | 12
Test Case design/ Defect Tracker Update/ Jira Update | 1.5 | Saravanan munikrishnan | 8.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | TBD | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-10 | Regression Testing will be done, once issue fixed | [7 empty] | Total Automation Execution | 30
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 2.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | TBD | Issue observed for JPY and KRW currencies | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-10 | Testing will be done OAK-2, once issue fixed | [7 empty] | Bugs Identified | 0
vEMS: AR/AP Dashboard | 2.5 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5- Power Bi: In Progress | [7 empty] | Total Bugs | 282
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 3.5 |  |  | WOR-512: Refund status as Paid | Completed | TBD | Testing completed in OAK-2 and OAK-1 | AR/AP Dashboard | Yet to Start | TBD | FIN Reports: Work on Requirement gathering & Access | [7 empty] | Manual Test Created | 0
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 3.5 | [17 empty] | Total Manual Case | 318
vEMS: Ad-hoc testing request | 5.5 | [17 empty] | Automation Scripts Created | 0
vEMS: WOR-512 (Refund Status as paid) | 1.5 | [17 empty] | Total Automation Scripts | 317
vEMS: Automation Script Enhancement | 6.5
vEMS: Automation(Multi SR & Power Bi) | 1

## 13 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
vEMS:Daily StandUp - Internal | 5 | Pramod rayate | 20 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 |  | No defects logged for the week; | [5 empty] | Total Manual Execution | 9
Test Case design/ Defect Tracker Update/ Jira Update | 2.5 | Saravanan munikrishnan | 5 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Blocked by WOR-817 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Regression Testing will be done, once issue fixed | [7 empty] | Total Automation Execution | 25
vEMS: Triage / Review Meeting - Testing and Defects | 2.5 | Vignesh dhakshnamoorthy | 9.5 | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Requirement got changed, waiting for new changes | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Testing will be done OAK-2, once issue fixed | [7 empty] | Bugs Identified | 0
vEMS: AR/AP Dashboard | 9.5 |  |  | WD-Regression Suite | Blocked | TBD | Phase-5:- Power Bi validation: Blocked due to INT101D issue | WD-Regression Suite | Blocked | TBD | Phase-5- Power Bi: Blocked by INT101D issue | [7 empty] | Total Bugs | 282
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 2 |  |  | AR/AP Dashboard | In Progress | 2023-11-21 | FIN Reports: Worked on Requirement gathering & Access Working on Table design | AR/AP Dashboard | In Progress | 2023-11-21 | FIN Reports: Work on Table design and waiting for Data from vEMS | [7 empty] | Manual Test Created | 0
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 3 | [17 empty] | Total Manual Case | 318
vEMS: Automation Script Enhancement | 2.5 | [17 empty] | Automation Scripts Created | 0
vEMS: Automation(Multi SR & Power Bi) | 7.5 | [17 empty] | Total Automation Scripts | 317

## 20 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
vEMS:Daily StandUp - Internal | 3 | Pramod rayate | 8 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | [7 empty] | Total Manual Execution | 24
Test Case design/ Defect Tracker Update/ Jira Update | 1 | Saravanan munikrishnan | 8.5 | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Functionality working as expected, Pending to check in FPNA | WOR-823, 824: Refund to use Bank Rate | In Progress | 2023-11-21 | Will check FPNA and start Full regression | [7 empty] | Total Automation Execution | 35
vEMS: Triage / Review Meeting - Testing and Defects | 1 | Vignesh dhakshnamoorthy | 14 | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Functionality working as expected, Pending to check in FPNA | WOR-817, 818: ADJ to use Bank Rate | In Progress | 2023-11-21 | Will check FPNA and start Full regression | [7 empty] | Bugs Identified | 0
vEMS: AR/AP Dashboard | 14 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | [7 empty] | Total Bugs | 285
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 2 | [5 empty] | creating fresh data for validation |  |  |  | Prepare data and put more validation | [7 empty] | Manual Test Created | 0
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 2 |  |  | AR/AP Dashboard | In Progress | 2023-11-24 | FIN Reports: Worked on Requirement gathering & Access | AR/AP Dashboard | In Progress | 2023-11-24 | FIN Reports: Get data & Access for vEMS | [7 empty] | Total Manual Case | 318
vEMS: Automation Script Enhancement | 3 | [5 empty] | Worked on Table design, able to receive data for Workday |  |  |  | Work on feeding data in dashboard | [7 empty] | Automation Scripts Created | 0
vEMS: Automation(Multi SR & Power Bi) | 4.5 | [17 empty] | Total Automation Scripts | 317

## 27 Nov 2023
Task Name | Hours. | Resources | Hours.. | Task. | Status. | ETC. | Comments. | Task.. | Status.. | ETC.. | Comments .. | Defect ID | Defect Name | Severity | Status | Assigned To | ETC | Comments | Type | Count
vEMS:Daily StandUp - Internal | 5 | Pramod rayate | 20 | WOR-882: Refund to use Bank Rate | In Progress | 2023-12-05 | started Full regression in OAK-2 | WOR-556: JE for reversal CINV missing with JPY | Blocked | TBD | Blocked by WOR-806 | [7 empty] | Total Manual Execution | 24
Test Case design/ Defect Tracker Update/ Jira Update | 1 | Saravanan munikrishnan | 19.5 | WOR-823, 824: Refund to use Bank Rate | Completed | 2023-11-21 | Functionality working as expected, Issue found in FPNA | WOR-882: Refund to use Bank Rate | In Progress | 2023-12-05 | Continue Full regression in OAK-2 and OAK-1 | [7 empty] | Total Automation Execution | 35
vEMS: Triage / Review Meeting - Testing and Defects | 2 | Vignesh dhakshnamoorthy | 8 | WOR-817, 818: ADJ to use Bank Rate | Completed | 2023-11-21 | Functionality working as expected, Issue found in FPNA | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress | [7 empty] | Bugs Identified | 0
vEMS: AR/AP Dashboard | 8 |  |  | WD-Regression Suite | In Progress | TBD | Phase-5:- Power Bi validation: In Progress |  |  |  | Prepare data and put more validation | [7 empty] | Total Bugs | 285
vEMS: WOR-817, 818 (SINV Adj to use Bank rate) | 2 | [5 empty] | creating fresh data for validation | AR/AP Dashboard | In Progress | 2023-12-01 | FIN Reports: Get data & Access for vEMS | [7 empty] | Manual Test Created | 0
vEMS: WOR-823, 824 (SINV Adj to use Bank rate) | 2 |  |  | AR/AP Dashboard | In Progress | 2023-12-01 | FIN Reports: Worked on Requirement gathering & Access |  |  |  | Waiting for data from vEMS & Navision | [7 empty] | Total Manual Case | 318
vEMS: WOR-882 (Refund to use Bank rate) | 4 | [5 empty] | Table design completed, waiting for vEMS & Navision | [11 empty] | Automation Scripts Created | 0
vEMS: Automation Script Enhancement | 5 | [17 empty] | Total Automation Scripts | 317
vEMS: Automation(Multi SR & Power Bi) | 18.5